## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 80 | 400000 | ACTION | 80 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 83.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 83.2441 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 80.0008 | 833342.0226 | ACTION | 83.2441 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 123.2441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 128.6607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 129.6607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 132.6607 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 142.6607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 143.3838 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 143.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 144.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 147.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 162.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 163.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 163.2441 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 164.3871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 165.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 166.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 170.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 175.8037 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 28 | 291666.6667 | ACTION | 203.8037 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 243.8037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 249.2204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 250.2204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 253.2204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 253.9435 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 253.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 254.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 269.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 271.9467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 272.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 273.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 277.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 283.3634 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 323.3634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 328.78 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 329.78 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 332.78 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 333.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 333.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 334.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 18 | 187500 | ACTION | 352.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 367.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 369.5064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 370.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 371.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 375.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 380.923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 420.923 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 426.3397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 427.3397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 430.3397 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 439.3397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 440.0628 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 440.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 441.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 12 | 125000 | ACTION | 453.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 468.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 470.066 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 386.8219 | 1934109.644 | ACTION | 470.066 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 470.0668 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 471.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 472.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 473.3101 | MonopileInstallation
| Feeder 1 | Queue | 310.066 | 1550330.0311 | ACTION | 473.3101 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 476.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 481.4827 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 485.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 493.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 505.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 513.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 521.4827 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 525.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 526.8993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 527.8993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 530.8993 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 531.6224 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 531.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 532.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 533.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 545.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 547.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 549.6257 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 550.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 551.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 553.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 555.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 556.5533 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 556.5542 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 561.0423 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 601.0423 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 606.459 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 607.459 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 610.459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 611.1821 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 611.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 612.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 627.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 629.1853 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 630.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 631.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 635.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 640.602 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 680.602 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 686.0186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 687.0186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 690.0186 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 690.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 690.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 691.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 706.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 708.745 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 709.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 710.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 714.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 720.1616 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 760.1616 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 765.5783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 766.5783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 769.5783 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 770.3014 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 770.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 771.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 786.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 788.3046 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 314.9945 | 1574972.5903 | ACTION | 788.3046 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 788.3054 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 789.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 790.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 791.5487 | MonopileInstallation
| Feeder 0 | Queue | 234.9945 | 1174972.5903 | ACTION | 791.5487 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 794.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 799.7213 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 803.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 811.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 823.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 831.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 839.7213 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 843.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 845.1379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 846.1379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 849.1379 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 849.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 849.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 850.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 851.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 12 | 125000 | ACTION | 862.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 863.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 871.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 874.7919 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 874.7928 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 877.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 879.8643 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 880.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 881.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 6 | 62500 | ACTION | 887.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 891.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 897.2809 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 937.2809 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 942.6976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 943.6976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 946.6976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 947.4206 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 947.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 948.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 963.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 965.4239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 966.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 967.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 971.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 976.8406 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1016.8406 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1022.2572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1023.2572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1026.2572 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1026.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1026.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1027.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1042.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1044.9835 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1045.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1046.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1050.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1056.4002 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1096.4002 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1101.8169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1102.8169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1105.8169 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1106.5399 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1106.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1107.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1122.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1124.5432 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 332.9945 | 1664972.5903 | ACTION | 1124.5432 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1124.544 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1125.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1126.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1127.7873 | MonopileInstallation
| Feeder 1 | Queue | 252.9945 | 1264972.5903 | ACTION | 1127.7873 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1130.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1135.9599 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1139.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1147.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1159.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1167.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1175.9599 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1179.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1181.3765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1182.3765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1185.3765 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1186.0996 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1186.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1187.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1187.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1199.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1202.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1204.1028 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1205.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1206.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1207.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1210.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1211.0305 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1211.0314 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1215.5195 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1255.5195 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1260.9362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1261.9362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1264.9362 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1265.6592 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1265.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1266.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1281.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1283.6625 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1284.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1285.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1289.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1295.0792 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1335.0792 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1340.4958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1341.4958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1344.4958 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1345.2189 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1345.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1346.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1361.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1363.2221 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1364.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1365.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1369.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1374.6388 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1414.6388 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1420.0555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1421.0555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1424.0555 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1424.7785 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1424.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1425.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1440.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1442.7818 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 314.9945 | 1574972.5903 | ACTION | 1442.7818 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1442.7826 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1443.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1444.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1446.0259 | MonopileInstallation
| Feeder 0 | Queue | 234.9945 | 1174972.5903 | ACTION | 1446.0259 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1448.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1454.1985 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1458.0259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1466.0259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1478.0259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1486.0259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1494.1985 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1498.0259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1499.6151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1500.6151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1503.6151 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1504.3382 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1504.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1505.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1506.0259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1518.0259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1520.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1522.3414 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1523.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1524.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1526.0259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1528.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1529.2691 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1529.2699 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1533.7581 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1573.7581 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1579.1748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1580.1748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1583.1748 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1583.8978 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1583.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1584.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1599.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1601.9011 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1602.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1603.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1607.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1613.3178 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1653.3178 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1658.7344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1659.7344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1662.7344 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1663.4575 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1663.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1664.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1679.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1681.4607 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1682.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1683.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1687.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1692.8774 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1732.8774 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1738.2941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1739.2941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1742.2941 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1743.0171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1743.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1744.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1759.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1761.0204 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 314.9945 | 1574972.5903 | ACTION | 1761.0204 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1761.0212 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1762.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1763.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1764.2645 | MonopileInstallation
| Feeder 1 | Queue | 234.9945 | 1174972.5903 | ACTION | 1764.2645 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1767.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1772.4371 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1776.2645 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1784.2645 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1796.2645 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1804.2645 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1812.4371 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1816.2645 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1817.8537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1818.8537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1821.8537 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1822.5768 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1822.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1823.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1824.2645 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1836.2645 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1838.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1840.58 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1841.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1842.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1844.2645 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1846.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1847.5077 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1847.5085 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1851.9967 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1891.9967 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1897.4134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1898.4134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1901.4134 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1902.1364 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1902.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1903.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1918.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1920.1397 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1921.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1922.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1926.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1931.5564 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1971.5564 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1976.973 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1977.973 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1980.973 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1981.6961 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1981.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1982.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1997.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1999.6993 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2000.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2001.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2005.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2011.116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2051.116 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2056.5327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2057.5327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2060.5327 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2061.2557 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2061.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2062.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2077.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2079.259 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 314.9945 | 1574972.5903 | ACTION | 2079.259 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2079.2598 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2080.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2081.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2082.5031 | MonopileInstallation
| Feeder 0 | Queue | 234.9945 | 1174972.5903 | ACTION | 2082.5031 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2085.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2090.6757 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2094.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2102.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2114.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2122.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2130.6757 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2134.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2136.0923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2137.0923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2140.0923 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2140.8154 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2140.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2141.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2142.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2154.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2156.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2158.8186 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2159.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2160.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2162.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2164.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2165.7463 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2165.7471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2170.2353 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2210.2353 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2215.652 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2216.652 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2219.652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2220.375 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2220.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2221.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2236.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2238.3783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2239.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2240.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2244.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2249.7949 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2289.7949 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2295.2116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2296.2116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2299.2116 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2299.9347 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2299.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2300.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2315.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2317.9379 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2318.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2319.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2323.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2329.3546 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2369.3546 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2374.7713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2375.7713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2378.7713 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2379.4943 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2379.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2380.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2395.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2397.4976 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 314.9945 | 1574972.5903 | ACTION | 2397.4976 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2397.4984 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2398.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2399.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2400.7417 | MonopileInstallation
| Feeder 1 | Queue | 234.9945 | 1174972.5903 | ACTION | 2400.7417 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2403.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2408.9142 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2412.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2420.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2432.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2440.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2448.9142 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2452.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2454.3309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2455.3309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2458.3309 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2459.054 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2459.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2460.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2460.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2472.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2475.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2477.0572 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2478.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2479.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2480.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2483.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2483.9849 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2483.9857 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2488.4739 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2528.4739 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2533.8906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2534.8906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2537.8906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2538.6136 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2538.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2539.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2554.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2556.6169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2557.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2558.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2562.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2568.0335 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2608.0335 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2613.4502 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2614.4502 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2617.4502 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2618.1733 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2618.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2619.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2634.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2636.1765 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2637.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2638.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2642.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2647.5932 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2687.5932 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2693.0099 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2694.0099 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2697.0099 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2697.7329 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2697.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2698.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2713.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2715.7362 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 314.9945 | 1574972.5903 | ACTION | 2715.7362 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2715.737 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2716.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2717.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2718.9803 | MonopileInstallation
| Feeder 0 | Queue | 234.9945 | 1174972.5903 | ACTION | 2718.9803 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2721.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2727.1528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2730.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2738.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 38 | 395833.3333 | ACTION | 2765.1528 | MonopileInstallation
| Feeder 1 | Delay | 33 | 165000 | ACTION | 2771.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2783.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2791.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2803.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2805.1528 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2810.5695 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2811.5695 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2811.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2814.5695 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2815.2926 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2815.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2816.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2823.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2831.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2831.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2833.2958 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2834.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2835.2235 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2835.2243 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2835.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2839.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2844.7125 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2884.7125 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2890.1292 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2891.1292 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2894.1292 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2894.8522 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2894.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2895.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2910.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2912.8555 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2913.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2914.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2918.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2924.2721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2964.2721 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2969.6888 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2970.6888 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2973.6888 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2974.4119 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2974.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2975.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2990.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2992.4151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2993.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2994.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2998.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3003.8318 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 43 | 447916.6667 | ACTION | 3046.8318 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3086.8318 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3092.2485 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3093.2485 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3096.2485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3096.9715 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3096.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3097.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3112.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3114.9748 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 395.9945 | 1979972.5903 | ACTION | 3114.9748 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3114.9756 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3115.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3116.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3118.2188 | MonopileInstallation
| Feeder 1 | Queue | 282.9945 | 1414972.5903 | ACTION | 3118.2188 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3120.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3126.3914 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3130.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3138.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3150.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3158.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3166.3914 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3170.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3171.8081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3172.8081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3175.8081 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3176.5312 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3176.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3177.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3178.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3190.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3192.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3194.5344 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3195.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3196.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3198.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3200.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3201.4621 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3201.4629 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3205.9511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3245.9511 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3251.3678 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3252.3678 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3255.3678 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3256.0908 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3256.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3257.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3272.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3274.0941 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3275.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3276.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3280.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3285.5107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3325.5107 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3330.9274 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3331.9274 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3334.9274 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3335.6505 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3336.6505 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3336.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3337.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 15 | 156250 | ACTION | 3352.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3367.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3369.6537 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3370.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3371.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3375.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3381.0704 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3421.0704 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3426.487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3427.487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3430.487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3431.2101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3431.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3432.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 3435.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3450.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3452.2134 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 333.9945 | 1669972.5903 | ACTION | 3452.2134 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3452.2142 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3453.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3454.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3455.4574 | MonopileInstallation
| Feeder 0 | Queue | 253.9945 | 1269972.5903 | ACTION | 3455.4574 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3458.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3463.63 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3467.4574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3475.4574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3487.4574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3495.4574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3503.63 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3507.4574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3509.0467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3510.0467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3513.0467 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3513.7698 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3513.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3514.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3515.4574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3527.4574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3529.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3531.773 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3532.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3533.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3535.4574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3538.7007 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3538.7015 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 62500 | ACTION | 3539.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3543.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3549.1897 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3589.1897 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3594.6063 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3595.6063 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3598.6063 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3599.3294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3599.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3600.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 30 | 312500 | ACTION | 3630.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3645.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3647.3327 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3648.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3649.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3653.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3658.7493 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 45 | 468750 | ACTION | 3703.7493 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3743.7493 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3749.166 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3750.166 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3753.166 | MonopileInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 3768.166 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3768.8891 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3768.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3769.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3784.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3786.8923 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3787.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3788.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3792.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3798.309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 36 | 375000 | ACTION | 3834.309 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3874.309 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3879.7256 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3880.7256 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3883.7256 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3884.4487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3884.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3885.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3900.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3902.452 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 446.9945 | 2234972.5903 | ACTION | 3902.452 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3902.4528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3903.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3904.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3905.696 | MonopileInstallation
| Feeder 1 | Queue | 366.9945 | 1834972.5903 | ACTION | 3905.696 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3908.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3913.8686 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3917.696 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3925.696 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3937.696 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3945.696 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3953.8686 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3959.2853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3960.2853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3963.2853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3964.0084 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3964.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3965.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3980.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3982.0116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3983.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3984.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3988.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3993.4283 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 47 | 489583.3333 | ACTION | 4040.4283 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4080.4283 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4085.8449 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4086.8449 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4089.8449 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4090.568 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4090.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4091.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4106.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4108.5713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4109.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4110.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4114.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4119.9879 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4159.9879 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4165.4046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4166.4046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4169.4046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4170.1277 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4170.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4171.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4186.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4188.1309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4189.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4190.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4194.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4199.5476 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4239.5476 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4244.9642 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4245.9642 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4248.9642 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4249.6873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4249.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4250.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4265.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4267.6906 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 361.9945 | 1809972.5903 | ACTION | 4267.6906 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4267.6914 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4268.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4269.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4270.9346 | MonopileInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 4283.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4287.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4293.1072 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 4293.1072 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4295.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4297.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4299.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4301.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4303.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4303.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4304.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4305.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4307.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4309.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4311.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4313.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4315.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4316.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4316.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4317.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4319.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4321.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4323.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4325.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4327.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4328.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4329.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4329.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4333.1005 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 4373.1005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4378.5171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4379.5171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4379.8971 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4381.8971 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4382.8971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4383.6571 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4385.6571 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4386.6571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4387.7971 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4389.7971 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4390.7971 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 4402.7971 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4404.3171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4406.3171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4407.3171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4408.3171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4409.8171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4411.8171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4412.8171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4413.3171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4414.8171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4416.3171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4416.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4418.3171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4419.8171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4420.3171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4421.8171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4423.3171 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4428.7338 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 4468.7338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4474.1505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4475.1505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4475.5305 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4477.5305 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4478.5305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4479.2905 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4481.2905 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4482.2905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4483.4305 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4485.4305 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4486.4305 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4487.9505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4489.9505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 4550.9505 | TurbineInstallation
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4551.9505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4552.9505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4554.4505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4556.4505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4557.4505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4557.9505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4559.4505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4560.9505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4561.4505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4562.9505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4564.4505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4564.9505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4566.4505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4567.9505 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4573.3671 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 129 | 2150000 | ACTION | 4702.3671 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 4742.3671 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4747.7838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4748.7838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4749.1638 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4751.1638 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4752.1638 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4752.9238 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4754.9238 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4755.9238 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4757.0638 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4759.0638 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4760.0638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4761.5838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4763.5838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4764.5838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4765.5838 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4767.0838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4769.0838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4770.0838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4770.5838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4772.0838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4773.5838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4774.0838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4775.5838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4777.0838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4777.5838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4779.0838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4780.5838 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4786.0005 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4789.2437 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4791.2437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4793.2437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4795.2437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4797.2437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4799.2437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4799.9937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4800.7437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4801.4937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4803.4937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4805.4937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4807.4937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4809.4937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4811.4937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4812.2437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4812.9937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4813.7437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4815.7437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4817.7437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4819.7437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 14 | 233333.3333 | ACTION | 4833.7437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4835.7437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4837.7437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4838.4937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4839.2437 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4839.9937 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4843.237 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 4883.237 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4888.6536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4889.6536 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4890.0336 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4892.0336 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4893.0336 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4893.7936 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4895.7936 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4896.7936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4897.9336 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4899.9336 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4900.9336 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4902.4536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4904.4536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4905.4536 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4906.4536 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4907.9536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4909.9536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4910.9536 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4911.4536 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4912.9536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4914.4536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4914.9536 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4916.4536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4917.9536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4918.4536 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4919.9536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4921.4536 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4926.8703 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 4966.8703 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4972.287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4973.287 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 4982.287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4982.667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4984.667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4985.667 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4986.427 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4988.427 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4989.427 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4991.427 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4992.567 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4994.567 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4995.567 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4997.087 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4999.087 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5000.087 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5001.087 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5002.587 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5004.587 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5005.587 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5006.087 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5007.587 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5009.087 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5009.587 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5011.087 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5012.587 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5013.087 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5014.587 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5016.087 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5021.5036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 5061.5036 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5066.9203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5067.9203 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5068.3003 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5070.3003 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5071.3003 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5072.0603 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5074.0603 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5075.0603 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5076.2003 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5078.2003 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5079.2003 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5080.7203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5082.7203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5083.7203 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5084.7203 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5086.2203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5088.2203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5089.2203 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5089.7203 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5091.2203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5092.7203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5093.2203 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5094.7203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5096.2203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5096.7203 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5098.2203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5099.7203 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5105.137 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5108.3802 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5110.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5112.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5114.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5116.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5118.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5119.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5119.8802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5120.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5122.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5124.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5126.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5128.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5130.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5131.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5132.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5132.8802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5134.8802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5136.8802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5138.8802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5140.8802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5142.8802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5143.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5144.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5145.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5148.3734 | TurbineInstallation
| WTIV | Delay | 1261 | 21016666.6667 | ACTION | 6409.3734 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 6449.3734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6454.7901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6455.7901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6456.1701 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6458.1701 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6459.1701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6459.9301 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6461.9301 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6462.9301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6464.0701 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6466.0701 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6467.0701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6468.5901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6470.5901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6471.5901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6472.5901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6474.0901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6476.0901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6477.0901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6477.5901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6479.0901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6480.5901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6481.0901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6482.5901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6484.0901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6484.5901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6486.0901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6487.5901 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6493.0068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 20 | 333333.3333 | ACTION | 6513.0068 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 6553.0068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6558.4234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6559.4234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6559.8034 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6561.8034 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6562.8034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6563.5634 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6565.5634 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6566.5634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6567.7034 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6569.7034 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6570.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6572.2234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6574.2234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6575.2234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6576.2234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6577.7234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6579.7234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6580.7234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6581.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6582.7234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6584.2234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6584.7234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6586.2234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6587.7234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6588.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6589.7234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6591.2234 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6596.6401 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 6636.6401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6642.0568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6643.0568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6643.4368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6645.4368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6646.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6647.1968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6649.1968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6650.1968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6651.3368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6653.3368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6654.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6655.8568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6657.8568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6658.8568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6659.8568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6661.3568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6663.3568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6664.3568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6665.3568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6665.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6667.3568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6668.8568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6669.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6670.8568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6672.3568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6672.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6674.3568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6675.8568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6681.2734 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6684.5167 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6686.5167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6688.5167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6690.5167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6692.5167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6694.5167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6695.2667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6696.0167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6696.7667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6698.7667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6700.7667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6702.7667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6704.7667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6706.7667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6707.5167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6708.2667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6709.0167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6711.0167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6713.0167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6715.0167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6717.0167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6719.0167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6719.7667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6720.5167 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6721.2667 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6724.5099 | TurbineInstallation
| WTIV | Delay | 21 | 350000 | ACTION | 6745.5099 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 6785.5099 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6790.9266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6791.9266 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6792.3066 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6794.3066 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6795.3066 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6796.0666 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6798.0666 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6799.0666 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6800.2066 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6802.2066 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6803.2066 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6804.7266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6806.7266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6807.7266 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6808.7266 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 6823.7266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6825.2266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6827.2266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6828.2266 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6828.7266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6830.2266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6831.7266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6832.2266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6833.7266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6835.2266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6835.7266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6837.2266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6838.7266 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6844.1433 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 6884.1433 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6889.5599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6890.5599 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6890.9399 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6892.9399 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6893.9399 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6894.6999 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6896.6999 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6897.6999 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6898.8399 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6900.8399 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6901.8399 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6903.3599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6905.3599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6906.3599 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6907.3599 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 6915.3599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6916.8599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6918.8599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6919.8599 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6920.3599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6921.8599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6923.3599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6923.8599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6925.3599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6926.8599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6927.3599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6928.8599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6930.3599 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6935.7766 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 33 | 550000 | ACTION | 6968.7766 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7008.7766 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7014.1933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7015.1933 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7015.5733 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7017.5733 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7018.5733 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7019.3333 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7021.3333 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7022.3333 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7023.4733 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7025.4733 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7026.4733 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7027.9933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7029.9933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7030.9933 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7031.9933 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7033.4933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7035.4933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7036.4933 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7036.9933 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7038.4933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7039.9933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7040.4933 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7041.9933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7043.4933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7043.9933 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7045.4933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 7049.4933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7050.9933 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7056.4099 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 2 | 33333.3333 | ACTION | 7058.4099 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7059.4099 | TurbineInstallation
| WTIV | Transit | 1.2432 | 20720.7207 | ACTION | 7060.6532 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7062.6532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7064.6532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7066.6532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7068.6532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7070.6532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7072.6532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7073.4032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7074.1532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7074.9032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7076.9032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7078.9032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7080.9032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7082.9032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7084.9032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7085.6532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7086.4032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7087.1532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7089.1532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7091.1532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7093.1532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7095.1532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7097.1532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7097.9032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7098.6532 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7099.4032 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7102.6464 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7142.6464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7148.0631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7149.0631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7149.4431 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7151.4431 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7152.4431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7153.2031 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7155.2031 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7156.2031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7157.3431 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7159.3431 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7160.3431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7161.8631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7163.8631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7164.8631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7165.8631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7167.3631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7169.3631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7170.3631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7170.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7172.3631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7173.8631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7174.3631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7175.8631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7177.3631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7177.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7179.3631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7180.8631 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7186.2797 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 35 | 583333.3333 | ACTION | 7221.2797 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7261.2797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7266.6964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7267.6964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7268.0764 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7270.0764 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7271.0764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7271.8364 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7273.8364 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7274.8364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7275.9764 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7277.9764 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7278.9764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7280.4964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7282.4964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7283.4964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7284.4964 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 7298.4964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7299.9964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7306.9964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7308.9964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7309.9964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7310.4964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7311.9964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7313.4964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7313.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7315.4964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7316.9964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7317.4964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7318.9964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7320.4964 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7325.9131 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7365.9131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7371.3297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7372.3297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7372.7097 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7374.7097 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7375.7097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7376.4697 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7378.4697 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7379.4697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7380.6097 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7382.6097 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7383.6097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7385.1297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7387.1297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7388.1297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7389.1297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7390.6297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7392.6297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7393.6297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7394.1297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7395.6297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7397.1297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7397.6297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7399.1297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7400.6297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7401.1297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7402.6297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7404.1297 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7409.5464 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7412.7897 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7414.7897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7416.7897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7418.7897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7420.7897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7422.7897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7423.5397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7424.2897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7425.0397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7427.0397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7429.0397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7431.0397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7433.0397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7435.0397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7435.7897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7436.5397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7437.2897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7439.2897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7441.2897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7443.2897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 22 | 366666.6667 | ACTION | 7465.2897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7467.2897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7469.2897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7470.0397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7470.7897 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7471.5397 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7474.7829 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7514.7829 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7520.1996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7521.1996 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7521.5796 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7523.5796 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7524.5796 | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 7549.5796 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7550.3396 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7552.3396 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7553.3396 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7554.4796 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7556.4796 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7557.4796 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7558.9996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7560.9996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7561.9996 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7562.9996 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7564.4996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7566.4996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7567.4996 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7567.9996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7569.4996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7570.9996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7571.4996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7572.9996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7574.4996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7574.9996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7576.4996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7577.9996 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7583.4162 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7623.4162 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7628.8329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7629.8329 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7630.2129 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7632.2129 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7633.2129 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7633.9729 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7635.9729 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7636.9729 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7638.1129 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7640.1129 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7641.1129 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7642.6329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7644.6329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7645.6329 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7646.6329 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7648.1329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7650.1329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7651.1329 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7651.6329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7653.1329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7654.6329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7655.1329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7656.6329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7658.1329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7658.6329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7660.1329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7661.6329 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7667.0496 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7707.0496 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7712.4662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7713.4662 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7714.4662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7714.8462 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7716.8462 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7717.8462 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7724.8462 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7725.6062 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7727.6062 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7728.6062 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 7731.6062 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7732.7462 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7734.7462 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7735.7462 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7737.2662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7739.2662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7740.2662 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7741.2662 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7742.7662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7744.7662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7745.7662 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7746.2662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7747.7662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7749.2662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7749.7662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7751.2662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7752.7662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7753.2662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7754.7662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7756.2662 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7761.6829 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7764.9261 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7766.9261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7768.9261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7770.9261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7772.9261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7774.9261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7775.6761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7776.4261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7777.1761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7779.1761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7781.1761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7783.1761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7785.1761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7787.1761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7787.9261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7788.6761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7789.4261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7791.4261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7793.4261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7795.4261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7797.4261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7799.4261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7800.1761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7800.9261 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7801.6761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7804.9194 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7844.9194 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7850.3361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7851.3361 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7851.7161 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7853.7161 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7854.7161 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7855.4761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7857.4761 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7858.4761 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7859.6161 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7861.6161 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7862.6161 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7864.1361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7866.1361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7867.1361 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7868.1361 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7869.6361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7871.6361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7872.6361 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7873.1361 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7874.6361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7876.1361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7876.6361 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7878.1361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7879.6361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7880.1361 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7881.6361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7883.1361 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7888.5527 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 7928.5527 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7933.9694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7934.9694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7935.3494 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7937.3494 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7938.3494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7939.1094 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7941.1094 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7942.1094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7943.2494 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7945.2494 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7947.2494 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7948.2494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7949.7694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7951.7694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7952.7694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7953.7694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7955.2694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7957.2694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7958.2694 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7958.7694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7960.2694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7961.7694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7962.2694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7963.7694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7965.2694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7965.7694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7967.2694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7968.7694 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7974.1861 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 8014.1861 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8019.6027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8020.6027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8020.9827 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8022.9827 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8023.9827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8024.7427 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8026.7427 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8027.7427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8028.8827 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8030.8827 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8031.8827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8033.4027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8035.4027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8036.4027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8037.4027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8038.9027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8040.9027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8041.9027 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8042.4027 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 8051.4027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8052.9027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8054.4027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8054.9027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8056.4027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8057.9027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8058.4027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8059.9027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8061.4027 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8066.8194 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8070.0626 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8072.0626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8074.0626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8076.0626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8078.0626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8080.0626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8080.8126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8081.5626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8082.3126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8084.3126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8086.3126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8088.3126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8090.3126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8092.3126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8093.0626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8093.8126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8094.5626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8096.5626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8098.5626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8100.5626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8102.5626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8104.5626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8105.3126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8106.0626 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8106.8126 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8110.0559 | TurbineInstallation
| WTIV | Delay | 62 | 1033333.3333 | ACTION | 8172.0559 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 8212.0559 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8217.4725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8218.4725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8218.8525 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8220.8525 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8221.8525 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8222.6125 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8224.6125 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8225.6125 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8226.7525 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8228.7525 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8229.7525 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8231.2725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8233.2725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8234.2725 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8235.2725 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8236.7725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8238.7725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8239.7725 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8240.2725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8241.7725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8243.2725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8243.7725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8245.2725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8246.7725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8247.2725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8248.7725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8250.2725 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8255.6892 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 8295.6892 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8301.1059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8302.1059 | TurbineInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 8315.1059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8315.4859 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8317.4859 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8319.4859 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8320.4859 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8321.2459 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8323.2459 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8324.2459 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8325.3859 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8327.3859 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8328.3859 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8329.9059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8331.9059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8332.9059 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8333.9059 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 8341.9059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8343.4059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8345.4059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8346.4059 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8346.9059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8348.4059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8349.9059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8350.4059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8351.9059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8353.4059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8353.9059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8355.4059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8356.9059 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8362.3225 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 8402.3225 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8407.7392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8408.7392 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8409.1192 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8411.1192 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8412.1192 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8412.8792 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8414.8792 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8415.8792 | TurbineInstallation
| WTIV | Delay | 36 | 600000 | ACTION | 8451.8792 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8453.0192 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8455.0192 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8456.0192 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8457.5392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8459.5392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8460.5392 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8461.5392 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8463.0392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8465.0392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8466.0392 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8466.5392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8468.0392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8469.5392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8470.0392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8471.5392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8473.0392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8473.5392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8475.0392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8476.5392 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8481.9559 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8485.1991 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8487.1991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8489.1991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8491.1991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8493.1991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8495.1991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8495.9491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8496.6991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8497.4491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8499.4491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8501.4491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8503.4491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8505.4491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8507.4491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8508.1991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8508.9491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8509.6991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8511.6991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8513.6991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8515.6991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8517.6991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8519.6991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8520.4491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8521.1991 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8521.9491 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8525.1924 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 8565.1924 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8570.609 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8571.609 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8571.989 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8573.989 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8574.989 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8575.749 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8577.749 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8578.749 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8579.889 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 23 | 383333.3333 | ACTION | 8602.889 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8604.889 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8605.889 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8607.409 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8609.409 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8610.409 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8611.409 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8612.909 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8614.909 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8615.909 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8616.409 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8617.909 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8619.409 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8619.909 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8621.409 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8622.909 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8623.409 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8624.909 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8626.409 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8631.8257 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 90 | 1500000 | ACTION | 8721.8257 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 8761.8257 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8767.2424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8768.2424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8768.6224 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8770.6224 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8771.6224 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8772.3824 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8774.3824 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8775.3824 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8776.5224 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8778.5224 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8779.5224 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8781.0424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8783.0424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8784.0424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8785.0424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8786.5424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8788.5424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8789.5424 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8790.0424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8791.5424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8793.0424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8793.5424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8795.0424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8796.5424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8797.0424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8798.5424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8800.0424 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8805.459 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 8845.459 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8850.8757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8851.8757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8852.2557 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8854.2557 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8855.2557 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8856.0157 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8858.0157 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8859.0157 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8860.1557 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8862.1557 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8863.1557 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8864.6757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8866.6757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8867.6757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8868.6757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8870.1757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8872.1757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8873.1757 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8873.6757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8875.1757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8876.6757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8877.1757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8878.6757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8880.1757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8880.6757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8882.1757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8883.6757 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8889.0924 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8892.3356 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8894.3356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8896.3356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8898.3356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8900.3356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8902.3356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8903.0856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8903.8356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8904.5856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8906.5856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8908.5856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8910.5856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8912.5856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8914.5856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8915.3356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8916.0856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8916.8356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8918.8356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8920.8356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8922.8356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8924.8356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8926.8356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8927.5856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8928.3356 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8929.0856 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8932.3288 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 8972.3288 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8977.7455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8978.7455 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8979.1255 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8980.1255 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8982.1255 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8983.1255 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8984.1255 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8984.8855 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 14 | 233333.3333 | ACTION | 8998.8855 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9000.8855 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9001.8855 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9003.0255 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9005.0255 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9006.0255 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9007.5455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9009.5455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9010.5455 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9011.5455 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9013.0455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9015.0455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9016.0455 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9016.5455 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 9021.5455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9023.0455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9024.5455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9025.0455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9026.5455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9028.0455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9028.5455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9030.0455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9031.5455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9036.9622 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9076.9622 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9082.3788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9083.3788 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9083.7588 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9085.7588 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9086.7588 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9087.5188 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9089.5188 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9090.5188 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9091.6588 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9093.6588 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9094.6588 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9096.1788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9098.1788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9099.1788 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9100.1788 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9101.6788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9103.6788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9104.6788 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9105.1788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9106.6788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9108.1788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9108.6788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9110.1788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9112.1788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9113.6788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9114.1788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9115.6788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9117.1788 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9122.5955 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9162.5955 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9168.0122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9169.0122 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9169.3922 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9171.3922 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9172.3922 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9173.1522 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9175.1522 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9176.1522 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9180.1522 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9181.2922 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9183.2922 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9184.2922 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9185.2922 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9186.8122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9188.8122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9189.8122 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9190.8122 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9192.8122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9194.3122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9196.3122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9197.3122 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9197.8122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9199.3122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9200.8122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9201.3122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9202.8122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9204.3122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9204.8122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9206.3122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9207.8122 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9213.2288 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9216.4721 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9218.4721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9220.4721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9222.4721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9224.4721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9226.4721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9227.2221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9227.9721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9228.7221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9230.7221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9232.7221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9234.7221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9236.7221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9238.7221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9239.4721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9240.2221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9240.9721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9242.9721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9244.9721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9246.9721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9248.9721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9250.9721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9251.7221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9252.4721 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9253.2221 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9256.4653 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9296.4653 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9301.882 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9302.882 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9303.262 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9305.262 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9306.262 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9307.022 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9309.022 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9310.022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9311.162 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 9319.162 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9321.162 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9322.162 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 9328.162 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9329.682 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9331.682 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9332.682 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9333.682 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9335.182 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9337.182 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9338.182 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9338.682 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9340.182 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9341.682 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9342.182 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9343.682 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9345.182 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9345.682 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9347.182 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9348.682 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9354.0987 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9394.0987 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9399.5153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9400.5153 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9400.8953 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9402.8953 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9403.8953 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9404.6553 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9406.6553 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9407.6553 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9408.6553 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9409.7953 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9411.7953 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9412.7953 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9414.3153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9416.3153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9417.3153 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9418.3153 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9419.8153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9421.8153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9422.8153 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9423.3153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9424.8153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9426.3153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9426.8153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9428.3153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9429.8153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9430.3153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9431.8153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9433.3153 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9438.732 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9478.732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9484.1487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9485.1487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9485.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9487.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9488.5287 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9489.2887 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9491.2887 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9492.2887 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9493.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9495.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9496.4287 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9497.9487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9499.9487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9500.9487 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9501.9487 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9503.4487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9505.4487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9506.4487 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9506.9487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9508.4487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9509.9487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9510.4487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9511.9487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9513.4487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9513.9487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9515.4487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9516.9487 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9522.3653 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 2 | 33333.3333 | ACTION | 9524.3653 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9525.3653 | TurbineInstallation
| WTIV | Transit | 1.2432 | 20720.7207 | ACTION | 9526.6086 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9528.6086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9530.6086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9532.6086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9534.6086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9536.6086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9537.3586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9538.1086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9538.8586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9540.8586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9542.8586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9544.8586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9546.8586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9548.8586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9549.6086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9550.3586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9551.1086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9553.1086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9555.1086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9557.1086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9559.1086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9561.1086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9561.8586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9562.6086 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9563.3586 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9566.6018 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9606.6018 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9612.0185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9613.0185 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9613.3985 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9615.3985 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9616.3985 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9617.1585 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9619.1585 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9620.1585 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9621.2985 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9623.2985 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9624.2985 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9625.8185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9627.8185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9628.8185 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9629.8185 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9631.3185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9633.3185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9634.3185 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9634.8185 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9636.3185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9637.8185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9638.3185 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9639.8185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9641.3185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9641.8185 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9643.3185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9644.8185 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9650.2352 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9690.2352 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9695.6518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9696.6518 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9697.6518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9698.0318 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9700.0318 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9701.0318 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9701.7918 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9703.7918 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9704.7918 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9705.9318 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9707.9318 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9708.9318 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9710.4518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9712.4518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9713.4518 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9714.4518 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9715.9518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9717.9518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9718.9518 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9719.4518 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9721.4518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9722.9518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9724.4518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9724.9518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9726.4518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9727.9518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9728.4518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9729.9518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9731.4518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9736.8685 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9776.8685 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9782.2852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9783.2852 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9783.6652 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9785.6652 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9786.6652 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9787.4252 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9789.4252 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9790.4252 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9791.5652 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9793.5652 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9794.5652 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9796.0852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9798.0852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9799.0852 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9800.0852 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9801.5852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9803.5852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9804.5852 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9805.0852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9806.5852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9808.0852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9808.5852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9810.0852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9811.5852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9812.0852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9813.5852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9815.0852 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9820.5018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9823.7451 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9825.7451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9827.7451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9829.7451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9831.7451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9833.7451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9834.4951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9835.2451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9835.9951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9837.9951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9839.9951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9841.9951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9843.9951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9845.9951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9846.7451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9847.4951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9848.2451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9850.2451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9852.2451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9854.2451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9856.2451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9858.2451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9858.9951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9859.7451 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9860.4951 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9863.7383 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9903.7383 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9909.155 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9910.155 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9910.535 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9912.535 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9913.535 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9914.295 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9916.295 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9917.295 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9918.435 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9920.435 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9921.435 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9922.955 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9924.955 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9925.955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9926.955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9928.455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9930.455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9931.455 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9931.955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9933.455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9934.955 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9935.455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9936.955 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9938.455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9938.955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9940.455 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9941.955 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9947.3716 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 9987.3716 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9992.7883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9993.7883 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9994.1683 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9996.1683 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9997.1683 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9997.9283 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9999.9283 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10000.9283 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10002.0683 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10004.0683 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10005.0683 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10006.5883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10008.5883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10009.5883 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10010.5883 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10012.0883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10014.0883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10015.0883 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10015.5883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10017.0883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10018.5883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10019.0883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10020.5883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10022.0883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10022.5883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10024.0883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10025.5883 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10031.005 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10071.005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10076.4216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10077.4216 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10077.8016 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10079.8016 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10080.8016 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10081.5616 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10083.5616 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10084.5616 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10085.7016 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10087.7016 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10088.7016 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10090.2216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10092.2216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10093.2216 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10094.2216 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10095.7216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10097.7216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10098.7216 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10099.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10100.7216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10102.2216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10102.7216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10104.2216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10105.7216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10106.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10107.7216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10109.2216 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10114.6383 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 10117.8815 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10119.8815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10121.8815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10123.8815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10125.8815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10127.8815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10128.6315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10129.3815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10130.1315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10132.1315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10134.1315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10136.1315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10138.1315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10140.1315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10140.8815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10141.6315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10142.3815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10144.3815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10146.3815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10148.3815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10150.3815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10152.3815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10153.1315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10153.8815 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10154.6315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 10157.8748 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10197.8748 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10203.2915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10204.2915 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10204.6715 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10206.6715 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10207.6715 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10208.4315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10210.4315 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10211.4315 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10212.5715 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10214.5715 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10215.5715 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10217.0915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10219.0915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10220.0915 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10221.0915 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10222.5915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10224.5915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10225.5915 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10226.0915 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10227.5915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10229.0915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10229.5915 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10231.0915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10232.5915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10233.0915 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10234.5915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10236.0915 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10241.5081 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10281.5081 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10286.9248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10287.9248 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10288.3048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10290.3048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10291.3048 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10292.0648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10294.0648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10295.0648 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10296.2048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10298.2048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10299.2048 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10300.7248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10302.7248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10303.7248 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10304.7248 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10306.2248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10308.2248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10309.2248 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10309.7248 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10311.2248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10312.7248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10313.2248 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10314.7248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10316.2248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10316.7248 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10318.2248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10319.7248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10325.1415 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10365.1415 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10370.5581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10371.5581 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10371.9381 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10373.9381 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10374.9381 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10375.6981 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10377.6981 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10378.6981 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10379.8381 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10381.8381 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10382.8381 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10384.3581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10386.3581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10387.3581 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10388.3581 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10389.8581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10391.8581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10392.8581 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10393.3581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10394.8581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10396.3581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10396.8581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10398.3581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10399.8581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10400.3581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10401.8581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10403.3581 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10408.7748 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 10412.018 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10414.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10416.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10418.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10420.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10422.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10422.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10423.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10424.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10426.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10428.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10430.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10432.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10434.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10435.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10435.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10436.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10438.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10440.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10442.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10444.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10446.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10447.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10448.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10448.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 10452.0113 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10492.0113 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10497.4279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10498.4279 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10498.8079 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10500.8079 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10501.8079 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10502.5679 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10504.5679 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10505.5679 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10506.7079 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10508.7079 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10509.7079 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10511.2279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10513.2279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10514.2279 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10515.2279 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10516.7279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10518.7279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10519.7279 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10520.2279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10521.7279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10523.2279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10523.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10525.2279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10526.7279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10527.2279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10528.7279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10530.2279 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10535.6446 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10575.6446 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10581.0613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10582.0613 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10582.4413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10584.4413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10585.4413 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10586.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10588.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10589.2013 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10590.3413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10592.3413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10593.3413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10594.8613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10596.8613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10597.8613 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10598.8613 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10600.3613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10602.3613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10603.3613 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10603.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10605.3613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10606.8613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10607.3613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10608.8613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10610.3613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10610.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10612.3613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10613.8613 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10619.2779 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10659.2779 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10664.6946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10665.6946 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10666.0746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10668.0746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10669.0746 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10669.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10671.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10672.8346 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10673.9746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10675.9746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10676.9746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10678.4946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10680.4946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10681.4946 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10682.4946 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10683.9946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10685.9946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10686.9946 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10687.4946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10688.9946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10690.4946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10690.9946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10692.4946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10693.9946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10694.4946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10695.9946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10697.4946 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10702.9113 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 10706.1545 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10708.1545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10710.1545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10712.1545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10714.1545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10716.1545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10716.9045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10717.6545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10718.4045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10720.4045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10722.4045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10724.4045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10726.4045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10728.4045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10729.1545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10729.9045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10730.6545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10732.6545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10734.6545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10736.6545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 10738.6545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 10740.6545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10741.4045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10742.1545 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 10742.9045 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 10746.1478 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10786.1478 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10791.5644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10792.5644 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10792.9444 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10794.9444 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10795.9444 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10796.7044 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10798.7044 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10799.7044 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10800.8444 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10802.8444 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10803.8444 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10805.3644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10807.3644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10808.3644 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10809.3644 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10810.8644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10812.8644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10813.8644 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10814.3644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10815.8644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10817.3644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10817.8644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10819.3644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10820.8644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10821.3644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10822.8644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10824.3644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10829.7811 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10869.7811 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10875.1978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10876.1978 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10876.5778 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10878.5778 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10879.5778 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10880.3378 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10882.3378 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10883.3378 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10884.4778 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10886.4778 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10887.4778 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10888.9978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10890.9978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10891.9978 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10892.9978 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10894.4978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10896.4978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10897.4978 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10897.9978 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10899.4978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10900.9978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10901.4978 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10902.9978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10904.4978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10904.9978 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10906.4978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10907.9978 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10913.4144 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 10953.4144 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 10958.8311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10959.8311 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10960.2111 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10962.2111 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10963.2111 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10963.9711 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10965.9711 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10966.9711 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10968.1111 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10970.1111 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 10971.1111 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10972.6311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 10974.6311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 10975.6311 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10976.6311 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10978.1311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 10980.1311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10981.1311 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10981.6311 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10983.1311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10984.6311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10985.1311 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10986.6311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10988.1311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 10988.6311 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10990.1311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 10991.6311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 10997.0478 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 11000.291 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 11002.291 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 11004.291 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 11006.291 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 11008.291 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 11010.291 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 11011.041 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 11011.791 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 11012.541 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 11014.541 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 11016.541 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 11018.541 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 11020.541 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 11022.541 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 11023.291 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 11024.041 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 11024.791 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 11028.0343 | TurbineInstallation
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 11068.0343 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 11073.4509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 11074.4509 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 11074.8309 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 11076.8309 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 11077.8309 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 11078.5909 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 11080.5909 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 11081.5909 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 11082.7309 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 11084.7309 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 11085.7309 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 11087.2509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 11089.2509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 11090.2509 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 11091.2509 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 11092.7509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 11094.7509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 11095.7509 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 11096.2509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 11097.7509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 11099.2509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 11099.7509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 11101.2509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 11102.7509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 11103.2509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 11104.7509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 11106.2509 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 11111.6676 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 666666.6667 | ACTION | 11151.6676 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 11157.0843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 11158.0843 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 11158.4643 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 11160.4643 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 11161.4643 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 11162.2243 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 11164.2243 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 11165.2243 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 11166.3643 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 11168.3643 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 11169.3643 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 11170.8843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 11172.8843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 11173.8843 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 11174.8843 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 11176.3843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 11178.3843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 11179.3843 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 11179.8843 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 11181.3843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 11182.8843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 11183.3843 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 11184.8843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 11186.3843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 11186.8843 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 11188.3843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 11189.8843 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 11195.3009 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150