## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 72 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 80 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 83.2432 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 88.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 93.6599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 94.6599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 97.6599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 98.383 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 101.383 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 101.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 102.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 117.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 119.3862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 120.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 121.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 125.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 130.8029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 135.8029 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 141.2196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 142.2196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 145.2196 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 147.2196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 147.9426 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 147.9459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 148.9459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 163.9459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 165.9459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 166.9459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 167.9459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 171.9459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 177.3625 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 182.3625 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 187.7792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 188.7792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 191.7792 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 196.7792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 197.5023 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 208.5023 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 208.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 209.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 220.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 235.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 237.5055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 238.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 239.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 243.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 248.9222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 253.9222 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 259.3389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 260.3389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 263.3389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 264.0619 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 264.0652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 265.0652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 280.0652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 282.0652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 283.0652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 284.0652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 288.0652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 293.4818 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 296.7251 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 308.7251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 316.7251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 328.7251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 336.7251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 348.7251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 356.7251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 368.7251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 376.7251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 379.9683 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 384.9683 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 390.385 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 391.385 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 394.385 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 395.1081 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 395.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 396.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 411.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 413.1113 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 414.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 415.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 419.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 424.528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 429.528 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 434.9446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 435.9446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 438.9446 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 439.9446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 440.6677 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 440.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 441.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 12 | 200000 | ACTION | 453.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 468.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 470.671 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 471.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 472.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 476.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 482.0876 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 487.0876 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 492.5043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 493.5043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 496.5043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 497.2274 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 497.2306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 498.2306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 513.2306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 515.2306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 516.2306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 517.2306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 521.2306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 526.6473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 531.6473 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 537.0639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 538.0639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 541.0639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 541.787 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 541.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 542.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 557.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 559.7903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 560.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 561.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 565.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 571.2069 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 574.4502 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 586.4502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 594.4502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 606.4502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 614.4502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 626.4502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 634.4502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 646.4502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 654.4502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 657.6934 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 662.6934 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 668.1101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 669.1101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 672.1101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 672.8331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 672.8364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 673.8364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 688.8364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 690.8364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 691.8364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 692.8364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 696.8364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 702.2531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 707.2531 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 712.6697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 713.6697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 716.6697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 717.3928 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 717.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 718.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 733.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 735.396 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 736.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 737.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 741.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 746.8127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 751.8127 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 757.2294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 758.2294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 761.2294 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 766.2294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 766.9524 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 766.9557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 767.9557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 782.9557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 784.9557 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 785.9557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 786.9557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 790.9557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 796.3724 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 801.3724 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 806.789 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 807.789 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 810.789 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 811.5121 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 811.5153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 812.5153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 827.5153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 829.5153 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 830.5153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 831.5153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 835.5153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 840.932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 844.1752 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 856.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 864.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 876.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 885.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 893.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 905.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 913.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 925.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 933.1752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 936.4185 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 941.4185 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 946.8352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 947.8352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 950.8352 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 951.5582 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 951.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 952.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 967.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 969.5615 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 970.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 971.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 975.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 980.9781 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 985.9781 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 991.3948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 992.3948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 995.3948 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 996.1179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 996.1211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 997.1211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1012.1211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1014.1211 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1015.1211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1016.1211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1020.1211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1025.5378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1030.5378 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1035.9545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1036.9545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1039.9545 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1040.6775 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1040.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1041.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1056.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1058.6808 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1059.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1060.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1064.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1070.0974 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1075.0974 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1080.5141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1081.5141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1084.5141 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1085.2372 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1085.2404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1086.2404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1101.2404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1103.2404 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1104.2404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1105.2404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1109.2404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1114.6571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1117.9003 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1129.9003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1137.9003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1149.9003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1157.9003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1169.9003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1177.9003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1189.9003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1197.9003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1201.1436 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1206.1436 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1211.5602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1212.5602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1215.5602 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1216.2833 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1216.2866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1217.2866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1232.2866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1234.2866 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1235.2866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1236.2866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1240.2866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1245.7032 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1250.7032 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1256.1199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1257.1199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1260.1199 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1260.843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1260.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1261.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1276.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1278.8462 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1279.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1280.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1284.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1290.2629 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1295.2629 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1300.6795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1301.6795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1304.6795 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1305.4026 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1305.4059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1306.4059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 1317.4059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1332.4059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1334.4059 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1335.4059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1336.4059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1340.4059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1345.8225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1350.8225 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1356.2392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1357.2392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1360.2392 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1360.9622 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1360.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1361.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1376.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1378.9655 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1379.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1380.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1384.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1390.3822 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1393.6254 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1405.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1413.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1425.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1433.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1445.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1453.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1465.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1473.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1476.8687 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1481.8687 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1487.2853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1488.2853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1491.2853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1492.0084 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1492.0116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1493.0116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1508.0116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1510.0116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1511.0116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1512.0116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1516.0116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1521.4283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1526.4283 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1531.845 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1532.845 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1535.845 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1536.568 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1536.5713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1537.5713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1552.5713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1554.5713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1555.5713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1556.5713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 1560.5713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1564.5713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1569.988 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1574.988 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1580.4046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1581.4046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1584.4046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1585.1277 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1585.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1586.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1601.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1603.1309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1604.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1605.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1609.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1614.5476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1619.5476 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1624.9643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1625.9643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1628.9643 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1629.6873 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1629.6906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1630.6906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1645.6906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1647.6906 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1648.6906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1649.6906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1653.6906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1659.1072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1662.3505 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1674.3505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1682.3505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1694.3505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1702.3505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1714.3505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1722.3505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1734.3505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1742.3505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1745.5937 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1750.5937 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1756.0104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1757.0104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1760.0104 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1760.7335 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1760.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1761.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1776.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1778.7367 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1779.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1780.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1784.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1790.1534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1795.1534 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1800.5701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1801.5701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1804.5701 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1805.2931 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1805.2964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1806.2964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1821.2964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1823.2964 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1824.2964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1825.2964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1829.2964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1834.713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1839.713 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1845.1297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1846.1297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1849.1297 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1849.8528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1849.856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1850.856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1865.856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1867.856 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1868.856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1869.856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1873.856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1879.2727 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1884.2727 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1889.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1890.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1893.6893 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1894.4124 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1894.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1895.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1910.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1912.4157 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1913.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1914.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1918.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1923.8323 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1927.0756 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1939.0756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1947.0756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1959.0756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1967.0756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1979.0756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1987.0756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1999.0756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2007.0756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2010.3188 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2015.3188 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2020.7355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2021.7355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2024.7355 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2025.4585 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2025.4618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2026.4618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2041.4618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2043.4618 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2044.4618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2045.4618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2049.4618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2054.8785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2059.8785 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2065.2951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2066.2951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2069.2951 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2070.0182 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2070.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2071.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2086.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2088.0214 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2089.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2090.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2094.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2099.4381 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2104.4381 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2109.8548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2110.8548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2113.8548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2114.5778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2114.5811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2115.5811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2130.5811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2132.5811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2133.5811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2134.5811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2138.5811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2143.9978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2148.9978 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2154.4144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2155.4144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2158.4144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2159.1375 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2159.1407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2160.1407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2175.1407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2177.1407 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2178.1407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2179.1407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2183.1407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2188.5574 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2191.8007 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2203.8007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2211.8007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2223.8007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2231.8007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2243.8007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2251.8007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2263.8007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2271.8007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2275.0439 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2280.0439 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2285.4606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2286.4606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2289.4606 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2290.1836 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2290.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2291.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2306.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2308.1869 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2309.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2310.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2314.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2319.6035 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2324.6035 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2330.0202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2331.0202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2334.0202 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2334.7433 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2334.7465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2335.7465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2350.7465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2352.7465 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2353.7465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2354.7465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2358.7465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2364.1632 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2369.1632 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2374.5799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2375.5799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2378.5799 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2379.3029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2379.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2380.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2395.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2397.3062 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2398.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2399.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2403.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2408.7228 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2413.7228 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2419.1395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2420.1395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2423.1395 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2423.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2423.8658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2424.8658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2439.8658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2441.8658 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2442.8658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2443.8658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2447.8658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2453.2825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2456.5257 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2468.5257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2476.5257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2488.5257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2496.5257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2508.5257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2516.5257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2528.5257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2536.5257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2539.769 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2544.769 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2550.1856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2551.1856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2554.1856 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2554.9087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2554.912 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2555.912 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2570.912 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2572.912 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2573.912 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2574.912 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2578.912 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2584.3286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2589.3286 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2594.7453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2595.7453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2598.7453 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2599.4684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2599.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2600.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2615.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2617.4716 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2618.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2619.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2623.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2628.8883 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2633.8883 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2639.3049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2640.3049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2643.3049 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2644.028 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2644.0313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2645.0313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2660.0313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2662.0313 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2663.0313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2664.0313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2668.0313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2673.4479 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2678.4479 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2683.8646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2684.8646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2687.8646 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2688.5877 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2688.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2689.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2704.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2706.5909 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2707.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2708.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2712.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2718.0076 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2721.2508 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2733.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 32 | 533333.3333 | ACTION | 2765.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2773.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2785.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2793.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2805.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2813.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2825.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2833.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2836.4941 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2841.4941 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2846.9107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2847.9107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2850.9107 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2851.6338 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2851.637 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2852.637 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2867.637 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2869.637 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2870.637 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2871.637 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2875.637 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2881.0537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2886.0537 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2891.4704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2892.4704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2895.4704 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2896.1934 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2896.1967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2897.1967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2912.1967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2914.1967 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2915.1967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2916.1967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2920.1967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2925.6134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2930.6134 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2936.03 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2937.03 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2940.03 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2940.7531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2940.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2941.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2956.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2958.7563 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2959.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2960.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2964.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2970.173 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2975.173 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2980.5897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2981.5897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2984.5897 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2985.3127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2985.316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2986.316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3001.316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3003.316 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3004.316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3005.316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3009.316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 24 | 400000 | ACTION | 3033.316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3038.7327 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3041.9759 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3046.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3058.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3066.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3078.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3086.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3098.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3106.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3118.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3126.9759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3130.2191 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3135.2191 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3140.6358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3141.6358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3144.6358 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3145.3589 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3145.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3146.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3161.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3163.3621 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3164.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3165.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3169.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3174.7788 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3179.7788 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3185.1955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3186.1955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3189.1955 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3189.9185 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3189.9218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3190.9218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3205.9218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3207.9218 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3208.9218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3209.9218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3213.9218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3219.3384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3224.3384 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3229.7551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3230.7551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3233.7551 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3234.4782 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3234.4814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3235.4814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3250.4814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3252.4814 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3253.4814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3254.4814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3258.4814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3263.8981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3268.8981 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3274.3148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3275.3148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3278.3148 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3279.0378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3279.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3280.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3295.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3297.0411 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3298.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3299.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3303.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3308.4577 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3311.701 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3323.701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3331.701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3343.701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 3352.701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3360.701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3363.9442 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3368.9442 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3374.3609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3375.3609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3378.3609 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3379.084 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3379.0872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3380.0872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3395.0872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3397.0872 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3398.0872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3399.0872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3403.0872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3408.5039 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3413.5039 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3418.9205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3419.9205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3422.9205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3423.6436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3423.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3424.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 3435.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3450.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3452.6469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3453.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3454.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3458.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 3464.0635 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3464.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3466.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3468.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3470.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3472.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3474.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3474.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3475.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3476.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3478.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3480.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3482.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3484.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3486.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3487.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3487.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3488.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3490.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3492.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3494.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3496.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3498.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3499.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3500.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3500.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3504.0568 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3509.0568 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3514.4734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3515.4734 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3515.8534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3517.8534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3518.8534 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3519.6134 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3521.6134 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3522.6134 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3523.7534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3525.7534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3526.7534 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3528.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3530.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3531.2734 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3532.2734 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 3538.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3539.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3541.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3542.7734 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3543.2734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3544.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3546.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3546.7734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3548.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3549.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3550.2734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3551.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3553.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3558.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3563.6901 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3569.1068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3570.1068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3570.4868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3572.4868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3573.4868 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3574.2468 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3576.2468 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3577.2468 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3578.3868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3580.3868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3581.3868 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3582.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3584.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3585.9068 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3586.9068 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3588.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3590.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3591.4068 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3591.9068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3593.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3594.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3595.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3596.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3598.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3598.9068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3600.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3601.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3607.3234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3612.3234 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3617.7401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3618.7401 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3626.7401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3627.1201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3629.1201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3631.1201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3632.1201 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3632.8801 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3634.8801 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3635.8801 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3637.0201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3639.0201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3640.0201 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3641.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3643.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3644.5401 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3645.5401 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3647.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3649.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3650.0401 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3650.5401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3652.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3653.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3654.0401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3655.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3657.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3657.5401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3659.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3660.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3665.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3669.2 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3671.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3673.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3675.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3677.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 25 | 416666.6667 | ACTION | 3702.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3704.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3704.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3705.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3706.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3708.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3710.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3712.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3714.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3716.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3717.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3717.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3718.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3720.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3722.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3724.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3726.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3728.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3729.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3730.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3730.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3734.1933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3739.1933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3744.6099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3745.6099 | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 3767.6099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3767.9899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3769.9899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3770.9899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3771.7499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3773.7499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3774.7499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3775.8899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3777.8899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3778.8899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3780.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3782.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3783.4099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3784.4099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3785.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3787.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3788.9099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3789.4099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3790.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3792.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3792.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3794.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3795.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3796.4099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3797.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3799.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3804.8266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3809.8266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3815.2433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3816.2433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3816.6233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3818.6233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3819.6233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3820.3833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3822.3833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3823.3833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3824.5233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3826.5233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3827.5233 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 3830.5233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3832.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3834.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3836.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3837.0433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3838.0433 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3840.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3841.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3843.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3844.5433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3845.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3846.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3848.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3848.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3850.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3851.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3852.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3853.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3855.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3860.4599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3865.4599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3870.8766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3871.8766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3872.2566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3874.2566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3875.2566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3876.0166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3878.0166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3879.0166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3880.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3882.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3883.1566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3884.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3886.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3887.6766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3888.6766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3890.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3892.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3893.1766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3893.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3895.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3896.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3897.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3898.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3900.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3900.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3902.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3903.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3909.0933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3912.3365 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3914.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3916.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3918.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3920.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3922.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3923.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3923.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3924.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3926.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3928.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3930.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3932.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3934.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3935.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3936.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3936.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3938.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3940.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3942.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3944.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3946.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3947.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3948.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3949.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3952.3297 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3957.3297 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3962.7464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3963.7464 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3964.1264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3966.1264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3967.1264 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3967.8864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3969.8864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3970.8864 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3972.0264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3974.0264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3975.0264 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3976.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3978.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3979.5464 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3980.5464 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3982.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3984.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3985.0464 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3985.5464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3987.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3988.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3989.0464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3990.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3992.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3992.5464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3994.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3995.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4000.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4005.9631 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4011.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4012.3797 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4012.7597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4014.7597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4015.7597 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4016.5197 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 44 | 733333.3333 | ACTION | 4060.5197 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4062.5197 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4063.5197 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4064.6597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4066.6597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4067.6597 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4069.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4071.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4072.1797 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4073.1797 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4074.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4076.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4077.6797 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4078.1797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4079.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4082.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4084.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4084.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4086.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4087.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4088.1797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4089.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4091.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4096.5964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4101.5964 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4107.0131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4108.0131 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4108.3931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4110.3931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4111.3931 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4112.1531 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4114.1531 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4115.1531 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4116.2931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4118.2931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4119.2931 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4120.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4122.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4123.8131 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4124.8131 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4126.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4128.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4129.3131 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4129.8131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4131.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4132.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4133.3131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4134.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4136.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4136.8131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4138.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4139.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4145.2297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4148.473 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4150.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4152.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4154.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4156.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4158.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4159.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4159.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4160.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4162.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4164.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4166.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4168.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4170.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4171.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4172.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4172.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4174.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4176.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4178.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4180.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4182.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4183.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4184.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4185.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4188.4662 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4193.4662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4198.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4199.8829 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4202.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4203.2629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4205.2629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4206.2629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4207.0229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4209.0229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4210.0229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4211.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4213.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4214.1629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4215.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4217.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4218.6829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4219.6829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4221.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4223.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4224.1829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4224.6829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4226.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4227.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4228.1829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4229.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4231.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4231.6829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4233.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4234.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4240.0996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4245.0996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4250.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4251.5162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4251.8962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4253.8962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4254.8962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4255.6562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4257.6562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4258.6562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4259.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4261.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4262.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4264.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4266.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4267.3162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4268.3162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4269.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 4279.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4281.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4282.8162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4283.3162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4284.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4286.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4286.8162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4288.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4289.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4290.3162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4291.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4293.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4298.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4303.7329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4309.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4310.1496 | TurbineInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 4327.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4327.5296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4329.5296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4330.5296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4331.2896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4333.2896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4334.2896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4335.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4337.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4338.4296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4339.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4341.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4342.9496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4343.9496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4345.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4347.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4348.4496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4348.9496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4350.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4351.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4352.4496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4353.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4355.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4355.9496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4357.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4358.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4364.3662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4367.6095 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4369.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4371.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4373.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4375.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4377.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4378.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4379.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4379.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4381.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4383.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4385.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4387.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4389.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4390.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4391.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4392.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 4402.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4404.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4406.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4408.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4410.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4412.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4412.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4413.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4414.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4417.6027 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4422.6027 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4428.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4429.0194 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4429.3994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4431.3994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4432.3994 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4433.1594 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4435.1594 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4436.1594 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4437.2994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4439.2994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4440.2994 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4441.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4443.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4444.8194 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4445.8194 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4447.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4449.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4450.3194 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4450.8194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4452.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4453.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4454.3194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4455.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4457.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4457.8194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4459.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4460.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4466.236 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4471.236 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4476.6527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4477.6527 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4478.0327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4480.0327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4481.0327 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4481.7927 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4483.7927 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4484.7927 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4485.9327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4487.9327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4488.9327 | TurbineInstallation
| WTIV | Delay | 62 | 1033333.3333 | ACTION | 4550.9327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4552.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4554.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4555.4527 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4556.4527 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4557.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4559.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4560.9527 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4561.4527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4562.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4564.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4564.9527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4566.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4567.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4568.4527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4569.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4571.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4576.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4581.8694 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4587.286 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4588.286 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 4603.286 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4603.666 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4605.666 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4607.666 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4608.666 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4609.426 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4611.426 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4612.426 | TurbineInstallation
| WTIV | Delay | 86 | 1433333.3333 | ACTION | 4698.426 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4699.566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4702.566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4704.566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4705.566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4707.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4709.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4710.086 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4711.086 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4712.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4714.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4715.586 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4716.086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4717.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4719.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4719.586 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4721.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4722.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4723.086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4724.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4726.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4731.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4734.746 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4736.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4738.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4740.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4742.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4744.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4745.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4746.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4746.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4748.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4750.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4752.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4754.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4756.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4757.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4758.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4759.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4761.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4763.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4765.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4767.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4769.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4769.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4770.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4771.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4774.7392 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4779.7392 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4785.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4786.1559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4786.5359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4788.5359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4789.5359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4790.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4792.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4793.2959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4794.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4796.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4797.4359 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4798.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4800.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4801.9559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4802.9559 | TurbineInstallation
| WTIV | Delay | 32 | 533333.3333 | ACTION | 4834.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4836.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4838.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4839.4559 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4839.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4841.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4842.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4843.4559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4844.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4846.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4846.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4848.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4849.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4855.3725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4860.3725 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4865.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4866.7892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4867.1692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4869.1692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4870.1692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4870.9292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4872.9292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4873.9292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4875.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4877.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4878.0692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4879.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4881.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4882.5892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4883.5892 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4888.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4890.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4892.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4893.0892 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4893.5892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4895.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4896.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4897.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4898.0892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4899.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4901.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4901.5892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4903.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4904.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4910.0059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4915.0059 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4920.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4921.4225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4921.8025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4923.8025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4924.8025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4925.5625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4927.5625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4928.5625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4929.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4931.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4932.7025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4934.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4936.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4937.2225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4938.2225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4939.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4941.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4942.7225 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4943.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4944.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4946.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4946.7225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4948.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4949.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4950.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4951.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4953.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4958.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4961.8824 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4963.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4965.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4967.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4969.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4971.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4972.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4973.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4974.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4976.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4978.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4980.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4982.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4984.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4984.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4985.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4986.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4988.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4990.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4992.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4994.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4996.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4997.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4997.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4998.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5001.8757 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5006.8757 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5012.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5013.2924 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5013.6724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5015.6724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5016.6724 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5017.4324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5019.4324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5020.4324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5021.5724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5023.5724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5024.5724 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 5030.5724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5032.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5034.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5035.0924 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5036.0924 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5037.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5039.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5040.5924 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5041.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5042.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5044.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5044.5924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5046.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5047.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5048.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5049.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5051.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5056.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5061.509 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5066.9257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5067.9257 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5068.3057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5070.3057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5071.3057 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5072.0657 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5074.0657 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5075.0657 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5076.2057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5078.2057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5079.2057 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5080.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5082.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5083.7257 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5084.7257 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5086.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5088.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5089.2257 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5089.7257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5091.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5092.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5093.2257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5094.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5096.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5096.7257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5098.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5099.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5105.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5110.1424 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5115.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5116.559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5116.939 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5118.939 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5119.939 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5120.699 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5122.699 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5123.699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5124.839 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5126.839 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5127.839 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5129.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5131.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5132.359 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5133.359 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5134.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5136.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5137.859 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5138.359 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5139.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5141.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5141.859 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5143.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5144.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5145.359 | TurbineInstallation
| WTIV | Delay | 1264 | 21066666.6667 | ACTION | 6409.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6410.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6412.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6417.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6421.0189 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6423.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6425.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6427.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6429.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6431.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6431.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6432.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6433.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6435.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6437.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6439.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6441.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6443.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6444.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6444.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6445.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6447.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6449.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6451.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6453.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6455.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6456.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6457.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6457.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6461.0122 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6466.0122 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6471.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6472.4288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6472.8088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6474.8088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6475.8088 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6476.5688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6478.5688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6479.5688 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6480.7088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6482.7088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6483.7088 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6485.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6487.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6488.2288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6489.2288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6490.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6492.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6493.7288 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6494.2288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6495.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6497.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6497.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6499.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 17 | 283333.3333 | ACTION | 6516.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6517.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6518.2288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6519.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6521.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6526.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6531.6455 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6537.0622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6538.0622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6538.4422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6540.4422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6541.4422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6542.2022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6544.2022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6545.2022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6546.3422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6548.3422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6549.3422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6550.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6552.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6553.8622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6554.8622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6556.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6558.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6559.3622 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6559.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6561.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6562.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6563.3622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6564.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6566.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6566.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6568.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6569.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6575.2788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6580.2788 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6585.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6586.6955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6587.0755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6589.0755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6590.0755 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6590.8355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6592.8355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6593.8355 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6594.9755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6596.9755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6597.9755 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6599.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6601.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6602.4955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6603.4955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6604.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6606.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6607.9955 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6608.4955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6609.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6611.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6611.9955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6613.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6614.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6615.4955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6616.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6618.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6623.9122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6627.1554 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6629.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6631.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6633.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6635.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6637.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6637.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6638.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6639.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6641.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6643.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6645.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6647.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6649.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6650.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6650.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6651.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6653.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6655.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6657.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6659.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6661.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6662.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6663.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6664.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6664.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6668.1487 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6673.1487 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6678.5653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6679.5653 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6679.9453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6681.9453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6682.9453 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6683.7053 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6685.7053 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6686.7053 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6687.8453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6689.8453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6690.8453 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6692.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6694.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6695.3653 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6696.3653 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6697.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6699.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6700.8653 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6701.3653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6702.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6704.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6704.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6706.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6707.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6708.3653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6709.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6711.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6716.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6721.782 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6727.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6728.1987 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6728.5787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6730.5787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6731.5787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6732.3387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6734.3387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6735.3387 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6736.4787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6738.4787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6739.4787 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6740.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 17 | 283333.3333 | ACTION | 6757.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6759.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6760.9987 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6761.9987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6763.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6765.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6766.4987 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6766.9987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6768.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6769.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6770.4987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6771.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6773.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6773.9987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6775.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6776.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6782.4153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6787.4153 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6792.832 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6793.832 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6794.212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6796.212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6797.212 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6797.972 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6799.972 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6800.972 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6802.112 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6804.112 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6805.112 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6806.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6808.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6809.632 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6810.632 | TurbineInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 6823.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6825.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6827.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6828.132 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6828.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6830.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6831.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6832.132 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6833.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6835.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6835.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6837.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6838.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6844.0487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6847.2919 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6849.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6851.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6853.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6855.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6857.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6858.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6858.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6859.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6861.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6863.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6865.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6867.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6869.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6870.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6871.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6871.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6873.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6875.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6877.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6879.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6881.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6882.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6883.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6884.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6887.2851 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6892.2851 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6897.7018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6898.7018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6899.0818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6901.0818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6902.0818 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6902.8418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6904.8418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6905.8418 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6906.9818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 6915.9818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6917.9818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6918.9818 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6920.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6922.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6923.5018 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6924.5018 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6926.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6928.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6929.0018 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6929.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6931.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6932.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6933.0018 | TurbineInstallation
| WTIV | Delay | 43 | 716666.6667 | ACTION | 6976.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6977.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 6983.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6985.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6985.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6987.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6988.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6993.9185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6998.9185 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7004.3351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7005.3351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7005.7151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7007.7151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7008.7151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7009.4751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7011.4751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7012.4751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7013.6151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7015.6151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7016.6151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7018.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7020.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7021.1351 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7022.1351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7023.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7025.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7026.6351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7027.1351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7028.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7030.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7030.6351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7032.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7033.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7034.1351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7035.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7037.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7042.5518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7047.5518 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7052.9685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7053.9685 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7054.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7055.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7057.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7058.3485 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7060.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7061.1085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 31 | 516666.6667 | ACTION | 7092.1085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7094.1085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7095.1085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7096.2485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7098.2485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7099.2485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7100.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7102.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7103.7685 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7104.7685 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7106.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7108.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7109.2685 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7109.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7111.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7112.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7113.2685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7114.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7116.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7116.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7118.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7119.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7125.1851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7128.4284 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7130.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7132.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7134.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7136.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7138.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7139.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7139.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7140.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7142.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7144.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7146.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7148.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7150.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7151.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7152.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7152.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7154.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7156.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7158.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7160.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7162.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7163.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7164.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7165.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7168.4216 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7173.4216 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7178.8383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7179.8383 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7180.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7182.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7183.2183 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7183.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7185.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7186.9783 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7188.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7190.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7191.1183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7192.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7194.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7195.6383 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7196.6383 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7198.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7200.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7201.1383 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7201.6383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7203.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7204.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7205.1383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7206.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7208.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7208.6383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7210.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7211.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 7221.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7227.055 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7232.055 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7237.4716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7238.4716 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7238.8516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7240.8516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7241.8516 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7242.6116 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7244.6116 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7245.6116 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7246.7516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7248.7516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7249.7516 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7251.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7253.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7254.2716 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7255.2716 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7256.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7258.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7259.7716 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7260.2716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7261.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7263.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7263.7716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7265.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7266.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7267.2716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7268.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7270.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7275.6883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7280.6883 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7286.105 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7288.105 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7289.105 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7296.105 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7296.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7298.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7300.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7301.485 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7306.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7307.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7309.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7310.245 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7311.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7313.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7314.385 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7315.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7317.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7318.905 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7319.905 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7321.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7323.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7324.405 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7324.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7326.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7327.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7328.405 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7329.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7331.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7331.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7333.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7334.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7340.3216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7343.5649 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7345.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7347.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7349.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7351.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7353.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7354.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7355.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7355.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7357.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7359.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7361.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7363.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7365.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7366.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7367.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7368.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7370.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7372.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7374.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7376.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7378.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7378.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7379.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7380.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7383.5581 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7388.5581 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7393.9748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7394.9748 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7395.3548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7397.3548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7398.3548 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7399.1148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7401.1148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7402.1148 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7403.2548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7405.2548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7406.2548 | TurbineInstallation
| WTIV | Delay | 59 | 983333.3333 | ACTION | 7465.2548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7466.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7468.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7469.7748 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7470.7748 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7472.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7474.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7475.2748 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7475.7748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7477.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7478.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7479.2748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7480.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7482.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7482.7748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7484.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7485.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7491.1915 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7496.1915 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7501.6081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7502.6081 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7502.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7504.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7505.9881 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7506.7481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7508.7481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7509.7481 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7510.8881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7512.8881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7513.8881 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7515.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7517.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7518.4081 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7519.4081 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7520.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7522.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7523.9081 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7524.4081 | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 7549.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7550.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7552.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7552.9081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7554.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7555.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7556.4081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7557.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7559.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7564.8248 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7569.8248 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7575.2415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7576.2415 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7576.6215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7578.6215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7579.6215 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7580.3815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7582.3815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7583.3815 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7584.5215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7586.5215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7587.5215 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7589.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7591.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7592.0415 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7593.0415 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7594.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7596.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7597.5415 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7598.0415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7599.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7601.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7601.5415 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7603.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7605.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7606.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7607.0415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7608.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7610.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7615.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7618.7014 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7620.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7622.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7624.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7626.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7628.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7629.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7630.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7630.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7632.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7634.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7636.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7638.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7640.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7641.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7642.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7643.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7645.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7647.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7649.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7651.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7653.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7653.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7654.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7655.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7658.6946 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7663.6946 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7669.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7670.1113 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 7674.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7674.4913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7676.4913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7677.4913 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7678.2513 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7680.2513 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7681.2513 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7682.3913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7684.3913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7685.3913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7686.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7688.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7689.9113 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7690.9113 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7692.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7694.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7695.4113 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7695.9113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7697.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7698.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7699.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7700.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7702.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7702.9113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7704.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7705.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7711.3279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7716.3279 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7721.7446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7722.7446 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7724.7446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7725.1246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7727.1246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7728.1246 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7728.8846 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 7731.8846 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7733.8846 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7734.8846 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7736.0246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7738.0246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7739.0246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7740.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7742.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7743.5446 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7744.5446 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7746.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7748.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7749.0446 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7749.5446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7751.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7752.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7753.0446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7754.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7756.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7756.5446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7758.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7759.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7764.9613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7769.9613 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7775.3779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7776.3779 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7776.7579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7778.7579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7779.7579 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7780.5179 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7782.5179 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7783.5179 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7784.6579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7786.6579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7787.6579 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7789.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7791.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7792.1779 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7793.1779 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7794.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7796.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7797.6779 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7798.1779 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7799.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7801.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7801.6779 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7803.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7804.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7805.1779 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7806.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7808.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7813.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7816.8378 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7818.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7820.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7822.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7824.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7826.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7827.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7828.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7829.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7831.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7833.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7835.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7837.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7839.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7839.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7840.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7841.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7843.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7845.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7847.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7849.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7851.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7852.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7852.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7853.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7856.8311 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7861.8311 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7867.2478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7868.2478 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7868.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7870.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7871.6278 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7872.3878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7874.3878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7875.3878 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7876.5278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7878.5278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7879.5278 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7881.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7883.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7884.0478 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7885.0478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7886.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7888.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7889.5478 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7890.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7891.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7893.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7893.5478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7895.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7896.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7897.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7898.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7900.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7905.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7910.4644 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7915.8811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7916.8811 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7917.2611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7919.2611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7920.2611 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7921.0211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7923.0211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7924.0211 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7925.1611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7927.1611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7928.1611 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7929.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7931.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7932.6811 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7933.6811 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7935.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7937.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7938.1811 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7938.6811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7940.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7941.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7942.1811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7943.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7945.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7947.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7947.6811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7949.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7950.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7956.0978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7961.0978 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7966.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7967.5144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7967.8944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7969.8944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7970.8944 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7971.6544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7973.6544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7974.6544 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7975.7944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7977.7944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7978.7944 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7980.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7982.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7983.3144 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7984.3144 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7985.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7987.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7988.8144 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7989.3144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7990.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7992.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7992.8144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7994.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7995.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7996.3144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7997.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7999.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8004.7311 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8007.9743 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8009.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8011.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8013.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8015.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8017.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8018.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8019.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8020.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8022.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8024.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8026.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8028.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8030.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8030.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8031.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8032.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8034.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8036.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8038.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8040.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8042.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8043.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8043.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8044.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 1 | 16666.6667 | ACTION | 8045.7243 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 8051.7243 | TurbineInstallation
| WTIV | Transit | 2.2432 | 37387.3874 | ACTION | 8053.9676 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8058.9676 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8064.3842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8065.3842 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8066.3842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8066.7642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8068.7642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8069.7642 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8070.7642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8071.5242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8072.5242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8074.5242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8075.5242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8076.6642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8078.6642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8079.6642 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8081.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8085.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8087.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8088.1842 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8089.1842 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8090.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8092.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8093.6842 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8094.1842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8095.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8097.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8097.6842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8099.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8100.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8101.1842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8102.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8104.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8109.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8114.6009 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8120.0176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8121.0176 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8121.3976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8123.3976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8124.3976 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8125.1576 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8127.1576 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8128.1576 | TurbineInstallation
| WTIV | Delay | 43 | 716666.6667 | ACTION | 8171.1576 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8172.2976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8174.2976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8175.2976 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8176.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8178.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8179.8176 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8180.8176 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8181.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8183.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8185.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8186.3176 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8186.8176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8188.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8189.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8190.3176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8191.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8193.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8193.8176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8195.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8196.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8202.2342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8207.2342 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8212.6509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8213.6509 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8214.0309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8216.0309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8217.0309 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8217.7909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8219.7909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8220.7909 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8221.9309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8223.9309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8224.9309 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8226.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8228.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8229.4509 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8230.4509 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8231.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8233.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8234.9509 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8235.4509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8236.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8238.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8238.9509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8240.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8241.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8242.4509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8243.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8245.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8250.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8254.1108 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8256.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8258.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8260.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8262.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8264.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8264.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8265.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8266.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8268.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8270.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8272.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8274.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8276.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8277.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8277.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8278.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8280.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8282.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8284.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8286.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8288.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8289.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8290.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8290.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8294.1041 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8299.1041 | TurbineInstallation
| WTIV | Delay | 18 | 300000 | ACTION | 8317.1041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8322.5207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8323.5207 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8323.9007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8325.9007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8326.9007 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8327.6607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8329.6607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8330.6607 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 8341.6607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8342.8007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8344.8007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8345.8007 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8347.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8349.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8350.3207 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8351.3207 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8352.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8354.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8355.8207 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8356.3207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8357.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8359.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8359.8207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8361.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8362.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8363.3207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8364.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8366.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8371.7374 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8376.7374 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8382.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8383.1541 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8383.5341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8385.5341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8386.5341 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8387.2941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8389.2941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8390.2941 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8391.4341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8393.4341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8394.4341 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8395.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8397.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8398.9541 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8399.9541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8401.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8403.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8404.4541 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8404.9541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8406.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8407.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8408.4541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8409.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8411.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8411.9541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8413.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8414.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 34 | 566666.6667 | ACTION | 8448.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8454.3707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8459.3707 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8464.7874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8465.7874 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8466.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8468.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8469.1674 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8469.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8471.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8472.9274 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8474.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8476.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8477.0674 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8478.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8480.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8481.5874 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8482.5874 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8484.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8486.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8487.0874 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8487.5874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8489.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8490.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8491.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8492.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8494.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8494.5874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8496.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8497.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8503.0041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8506.2473 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8508.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8510.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8512.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8514.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8516.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8516.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8517.7473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8518.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8520.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8522.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8524.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8526.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8528.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8529.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8529.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8530.7473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8533.9906 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8538.9906 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8544.4072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8545.4072 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8545.7872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8547.7872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8548.7872 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8549.5472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8551.5472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8552.5472 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8553.6872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8555.6872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8556.6872 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8558.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8560.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8561.2072 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8562.2072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8563.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8565.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8566.7072 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8567.2072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8568.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8570.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8570.7072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8572.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8573.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8574.2072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8575.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8577.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8582.6239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8587.6239 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8593.0406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8594.0406 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 8603.0406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8603.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8605.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8606.4206 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8607.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8609.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8610.1806 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8611.3206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8613.3206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8614.3206 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8615.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8617.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8618.8406 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8619.8406 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8621.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8623.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8624.3406 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8624.8406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8626.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8627.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8628.3406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8629.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8631.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8631.8406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8633.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8634.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8640.2572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5