## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 120 | 600000 | ACTION | 120 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 123.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 123.2441 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 120.0008 | 1250008.6892 | ACTION | 123.2441 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 163.2441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 168.6607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 169.6607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 172 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 172.6607 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 173.3838 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 173.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 174.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 180 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 192 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 19 | 95000 | ACTION | 211 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 219 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 46 | 479166.6667 | ACTION | 220.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 231 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 235.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 237.3871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 238.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 239.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 243.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 248.8037 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 251 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 262.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 262.2441 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 288.8037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 294.2204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 295.2204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 298.2204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 298.9435 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 298.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 299.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 314.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 316.9467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 317.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 318.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 322.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 328.3634 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 368.3634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 373.78 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 374.78 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 377.78 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 378.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 378.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 379.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 394.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 396.5064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 397.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 398.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 402.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 407.923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 46 | 479166.6667 | ACTION | 453.923 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 493.923 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 499.3397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 500.3397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 503.3397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 504.0628 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 504.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 505.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 520.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 522.066 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 523.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 524.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 528.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 533.4827 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 573.4827 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 578.8993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 579.8993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 582.8993 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 583.6224 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 583.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 584.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 599.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 601.6257 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 602.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 603.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 607.6257 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 613.0423 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 653.0423 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 658.459 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 659.459 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 662.459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 663.1821 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 663.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 664.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 679.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 681.1853 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 557.9412 | 2789706.1327 | ACTION | 681.1853 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 681.1861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 682.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 683.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 684.4294 | MonopileInstallation
| Feeder 1 | Queue | 422.1853 | 2110926.5198 | ACTION | 684.4294 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 687.1853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 692.602 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 696.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 704.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 716.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 724.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 732.602 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 736.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 738.0186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 739.0186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 742.0186 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 742.7417 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 742.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 743.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 744.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 756.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 758.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 760.745 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 761.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 764.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 766.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 767.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 771.745 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 776.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 777.1616 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 784.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 796.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 804.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 807.6726 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 807.6735 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 817.1616 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 822.5783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 823.5783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 826.5783 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 827.3014 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 827.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 828.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 843.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 845.3046 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 846.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 847.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 851.3046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 856.7213 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 29 | 302083.3333 | ACTION | 885.7213 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 925.7213 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 931.1379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 932.1379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 935.1379 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 935.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 935.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 936.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 951.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 953.8643 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 954.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 955.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 959.8643 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 965.2809 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1005.2809 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1010.6976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1011.6976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1014.6976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1015.4206 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1015.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1016.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1031.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1033.4239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1034.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1035.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1039.4239 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1044.8406 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1084.8406 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1090.2572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1091.2572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1094.2572 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1094.9803 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1094.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1095.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1110.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1112.9835 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1113.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1114.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1118.9835 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1124.4002 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1164.4002 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1169.8169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1170.8169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1173.8169 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1174.5399 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1174.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1175.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1190.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1192.5432 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 508.1138 | 2540569.079 | ACTION | 1192.5432 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1192.544 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1193.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1194.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1195.7873 | MonopileInstallation
| Feeder 0 | Queue | 388.1138 | 1940569.079 | ACTION | 1195.7873 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1198.5432 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1203.9599 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1207.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1215.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1227.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1235.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1243.9599 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1247.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1249.3765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1250.3765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1253.3765 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1254.0996 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1254.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1255.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1255.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1267.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1270.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1272.1028 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1273.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1274.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1275.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1278.1028 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1283.5195 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1287.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1295.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1307.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1315.7873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1319.0305 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1319.0314 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1323.5195 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1328.9362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1329.9362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1332.9362 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1333.6592 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1333.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1334.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1349.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1351.6625 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1352.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1353.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1357.6625 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1363.0792 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1403.0792 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1408.4958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1409.4958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1412.4958 | MonopileInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 1416.4958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1417.2189 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1417.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1418.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1433.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1435.2221 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1436.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1437.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1441.2221 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1446.6388 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1486.6388 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1492.0555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1493.0555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1496.0555 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1496.7785 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1496.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1497.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1512.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1514.7818 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1515.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1516.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1520.7818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1526.1985 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1566.1985 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1571.6151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1572.6151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1575.6151 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1576.3382 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1576.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1577.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1592.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1594.3414 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1595.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1596.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1600.3414 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1605.7581 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1645.7581 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1651.1748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1652.1748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1655.1748 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1655.8978 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1655.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1656.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1671.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1673.9011 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 478.1138 | 2390569.079 | ACTION | 1673.9011 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1673.9019 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1674.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1675.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1677.1452 | MonopileInstallation
| Feeder 1 | Queue | 358.1138 | 1790569.079 | ACTION | 1677.1452 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1679.9011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1685.3178 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1689.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1697.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1709.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1717.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1725.3178 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1729.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1730.7344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1731.7344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1734.7344 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1735.4575 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1735.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1736.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1737.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1749.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1751.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1753.4607 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1754.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1755.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1757.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1759.4607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1764.8774 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1769.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1777.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1789.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1797.1452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1800.3884 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1800.3892 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1804.8774 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1810.2941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1811.2941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1814.2941 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1815.0171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1815.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1816.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1831.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1833.0204 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1834.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1835.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1839.0204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1844.4371 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1884.4371 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1889.8537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1890.8537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1893.8537 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1894.5768 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1894.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1895.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1910.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1912.58 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1913.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1914.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1918.58 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1923.9967 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1963.9967 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1969.4134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1970.4134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1973.4134 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1974.1364 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1974.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1975.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1990.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1992.1397 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1993.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1994.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1998.1397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2003.5564 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2043.5564 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2048.973 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2049.973 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2052.973 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2053.6961 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2053.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2054.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2069.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2071.6993 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2072.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2073.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2077.6993 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2083.116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2123.116 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2128.5327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2129.5327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2132.5327 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2133.2557 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2133.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2134.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2149.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2151.259 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 474.1138 | 2370569.079 | ACTION | 2151.259 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2151.2598 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2152.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2153.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2154.5031 | MonopileInstallation
| Feeder 0 | Queue | 354.1138 | 1770569.079 | ACTION | 2154.5031 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2157.259 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2162.6757 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2166.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2174.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2186.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2194.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2202.6757 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2206.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2208.0923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2209.0923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2212.0923 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2212.8154 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2212.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2213.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2214.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2226.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2228.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2230.8186 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2231.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2232.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2234.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2236.8186 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2242.2353 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2246.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2254.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2266.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2274.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2277.7463 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2277.7471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2282.2353 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2287.652 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2288.652 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2291.652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2292.375 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2292.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2293.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2308.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2310.3783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2311.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2312.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2316.3783 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2321.7949 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2361.7949 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2367.2116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2368.2116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2371.2116 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2371.9347 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2371.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2372.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2387.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2389.9379 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2390.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2391.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2395.9379 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2401.3546 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2441.3546 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2446.7713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2447.7713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2450.7713 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2451.4943 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2451.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2452.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2467.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2469.4976 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2470.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2471.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2475.4976 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2480.9142 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2520.9142 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2526.3309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2527.3309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2530.3309 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2531.054 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2531.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2532.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2547.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2549.0572 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2550.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2551.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2555.0572 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2560.4739 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2600.4739 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2605.8906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2606.8906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2609.8906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2610.6136 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2610.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2611.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2626.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2628.6169 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 474.1138 | 2370569.079 | ACTION | 2628.6169 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2628.6177 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2629.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2630.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2631.861 | MonopileInstallation
| Feeder 1 | Queue | 354.1138 | 1770569.079 | ACTION | 2631.861 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2634.6169 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2640.0335 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2643.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2651.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2663.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2671.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2680.0335 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2683.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2685.4502 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2686.4502 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2689.4502 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2690.1733 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2690.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2691.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2691.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2703.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2706.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2708.1765 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2709.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2710.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2711.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2714.1765 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2719.5932 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2723.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2731.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 46 | 479166.6667 | ACTION | 2765.5932 | MonopileInstallation
| Feeder 0 | Delay | 40 | 200000 | ACTION | 2771.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2783.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2791.861 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2795.1042 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2795.105 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2805.5932 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2811.0099 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2812.0099 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2815.0099 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2815.7329 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2815.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2816.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2831.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2833.7362 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2834.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2835.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2839.7362 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2845.1528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2885.1528 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2890.5695 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2891.5695 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2894.5695 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2895.2926 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2895.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2896.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2911.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2913.2958 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2914.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2915.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2919.2958 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2924.7125 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2964.7125 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2970.1292 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2971.1292 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2974.1292 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2974.8522 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2974.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2975.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2990.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2992.8555 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2993.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2994.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2998.8555 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3004.2721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 42 | 437500 | ACTION | 3046.2721 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3086.2721 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3091.6888 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3092.6888 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3095.6888 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3096.4119 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3096.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3097.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3112.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3114.4151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3115.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3116.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3120.4151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3125.8318 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3165.8318 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3171.2485 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3172.2485 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3175.2485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3175.9715 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3175.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3176.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3191.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3193.9748 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 562.1138 | 2810569.079 | ACTION | 3193.9748 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3193.9756 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3194.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3195.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3197.2188 | MonopileInstallation
| Feeder 0 | Queue | 402.1138 | 2010569.079 | ACTION | 3197.2188 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3199.9748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3205.3914 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3209.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3217.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3229.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3237.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3245.3914 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3249.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3250.8081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3251.8081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3254.8081 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3255.5312 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3255.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3256.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3257.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3269.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3271.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3273.5344 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3274.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3275.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3277.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3279.5344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3284.9511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3289.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3297.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3309.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3317.2188 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3320.4621 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3320.4629 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3324.9511 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3330.3678 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3331.3678 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3334.3678 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3335.0908 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3336.0908 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3336.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3337.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 15 | 156250 | ACTION | 3352.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3367.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3369.0941 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3370.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3371.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3375.0941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3380.5107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3420.5107 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3425.9274 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3426.9274 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3429.9274 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3430.6505 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3430.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3431.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 3435.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3450.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3452.6537 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3453.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3454.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3458.6537 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3464.0704 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3504.0704 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3509.487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3510.487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3513.487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3514.2101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3514.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3515.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3530.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3532.2134 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3533.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 6 | 62500 | ACTION | 3539.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3540.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3544.2134 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3549.63 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3589.63 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3595.0467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3596.0467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3599.0467 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3599.7698 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3599.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3600.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 30 | 312500 | ACTION | 3630.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3645.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3647.773 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3648.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3649.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3653.773 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3659.1897 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 44 | 458333.3333 | ACTION | 3703.1897 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3743.1897 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3748.6063 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3749.6063 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3752.6063 | MonopileInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 3768.6063 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3769.3294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3769.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3770.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3785.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3787.3327 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 590.1138 | 2950569.079 | ACTION | 3787.3327 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3787.3335 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3788.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3789.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3790.5767 | MonopileInstallation
| Feeder 1 | Queue | 470.1138 | 2350569.079 | ACTION | 3790.5767 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3793.3327 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3798.7493 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3802.5767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3810.5767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3822.5767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3830.5767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 36 | 375000 | ACTION | 3834.7493 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3874.7493 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3880.166 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3881.166 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3884.166 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3884.8891 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3884.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3885.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3900.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3902.8923 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3903.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3904.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3908.8923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3914.309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3954.309 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3959.7256 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3960.7256 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3963.7256 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3964.4487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3964.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3965.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3980.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3982.452 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3983.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3984.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3988.452 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3993.8686 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 47 | 489583.3333 | ACTION | 4040.8686 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4080.8686 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4086.2853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4087.2853 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4090.2853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4091.0084 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4091.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4092.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4107.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4109.0116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4110.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4111.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4115.0116 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4120.4283 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4160.4283 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4165.8449 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4166.8449 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4169.8449 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4170.568 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4170.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4171.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4186.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4188.5713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4189.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4190.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4194.5713 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4199.9879 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4239.9879 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4245.4046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4246.4046 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4249.4046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4250.1277 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4250.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4251.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4266.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4268.1309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4269.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4270.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 13 | 135416.6667 | ACTION | 4283.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4287.1309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4292.5476 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4332.5476 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4337.9642 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4338.9642 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4341.9642 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4342.6873 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4342.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4343.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4358.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4360.6906 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 570.1138 | 2850569.079 | ACTION | 4360.6906 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4360.6914 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4361.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4362.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4363.9346 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4366.6906 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4372.1072 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 4372.1072 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 4372.1072 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 4372.1072 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4374.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4375.3505 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4376.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4378.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4380.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4382.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4382.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4383.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4384.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4386.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4388.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4390.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 16 | 80000 | ACTION | 4406.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4408.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4410.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4411.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4411.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4412.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4414.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4416.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4418.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4420.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4422.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4423.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4424.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4424.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4426.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4428.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4430.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4432.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4434.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4435.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4436.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4437.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4439.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4441.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4443.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4445.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4447.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4447.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4448.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4449.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4451.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4453.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4455.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4457.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4459.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4460.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4460.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4461.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 89.5 | 447500 | ACTION | 4461.6072 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4463.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 4464.8505 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4464.8513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 89.5008 | 932300.3559 | ACTION | 4464.8513 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4465.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4467.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4469.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4471.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4472.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4473.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4473.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4475.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4477.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4479.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4481.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4483.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4484.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4485.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4486.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4488.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4490.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 86 | 895833.3333 | ACTION | 4550.8513 | TurbineInstallation
| Feeder 1 | Delay | 65 | 325000 | ACTION | 4555.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4557.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 8 | 40000 | ACTION | 4565.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4567.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4569.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4569.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4570.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4571.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4573.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4575.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4577.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4579.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4581.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4582.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4582.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4583.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4585.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4587.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4589.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4590.8513 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4591.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4593.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4596.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4597.268 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4598.268 | TurbineInstallation
| Feeder 1 | Delay | 9 | 45000 | ACTION | 4602.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 4603.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4603.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4603.648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4604.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4604.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4605.648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4606.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4607.648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4608.648 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4608.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4609.408 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4610.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4611.408 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4612.408 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4612.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4614.8572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4615.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 3 | 15000 | ACTION | 4618.6072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4619.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 1 | 5000 | ACTION | 4620.3572 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4621.1072 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 2 | 10000 | ACTION | 4623.1072 | TurbineInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4626.3505 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4626.3513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 86 | 895833.3333 | ACTION | 4698.408 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4699.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 4702.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4704.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4705.548 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4707.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4709.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4710.068 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4711.068 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4712.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4714.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4715.568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4716.068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4717.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4719.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4719.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4721.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4722.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4723.068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4724.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4726.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4731.4846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4771.4846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4776.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4777.9013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4778.2813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4780.2813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4781.2813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4782.0413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4784.0413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4785.0413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4786.1813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4788.1813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4789.1813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4790.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4792.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4793.7013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4794.7013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4796.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4798.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4799.2013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4799.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4801.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4802.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4803.2013 | TurbineInstallation
| WTIV | Delay | 31 | 322916.6667 | ACTION | 4834.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4835.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4837.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4837.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4839.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4840.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4846.118 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4886.118 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4891.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4892.5346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4892.9146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4894.9146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4895.9146 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4896.9146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4897.6746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4899.6746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4900.6746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4901.8146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4903.8146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4904.8146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4906.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4908.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4909.3346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4910.3346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4911.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4913.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4914.8346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4915.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4916.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4918.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4918.8346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4920.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4921.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4922.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4923.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4925.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4930.7513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4970.7513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4976.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4977.168 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 4982.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4982.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4984.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4985.548 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4986.308 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4988.308 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4989.308 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4991.308 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4992.448 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4994.448 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4995.448 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4996.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4998.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4999.968 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5000.968 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5002.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5004.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5005.468 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5005.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5007.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5008.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5009.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5010.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5012.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5012.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5014.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5015.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5021.3846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 5061.3846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5066.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5067.8013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5068.1813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5070.1813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5071.1813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5071.9413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5073.9413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5074.9413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5076.0813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5078.0813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5079.0813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5080.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5082.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5083.6013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5084.6013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5086.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5088.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5089.1013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5089.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5091.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5092.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5093.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5094.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5096.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5096.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5098.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5099.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5105.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 5145.018 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5150.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5151.4346 | TurbineInstallation
| WTIV | Delay | 1258 | 13104166.6667 | ACTION | 6409.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6409.8146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6411.8146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6412.8146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6413.5746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6415.5746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6416.5746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6417.7146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6419.7146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6420.7146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6422.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6424.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6425.2346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6426.2346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6427.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6429.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6430.7346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6431.2346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6432.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6434.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6434.7346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6436.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6437.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6438.2346 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 1973.3833 | 9866916.6667 | ACTION | 6438.2346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 1811.8833 | 9059416.6667 | ACTION | 6438.2346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6438.2355 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6439.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6441.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6441.4787 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6443.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6445.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6446.6513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6447.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6449.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6451.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6452.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6452.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6453.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6455.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6457.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6459.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6461.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6463.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6464.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6465.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6465.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6467.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6469.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6471.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6473.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6475.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6476.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6477.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6478.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6480.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6482.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6484.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6486.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6486.6513 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6488.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6488.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6489.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6490.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6492.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6492.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6493.068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6493.448 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6494.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6495.448 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6496.448 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6496.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6497.208 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6498.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6499.208 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6500.208 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6500.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6501.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6501.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6502.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6504.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 2 | 10000 | ACTION | 6506.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6508.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 4 | 20000 | ACTION | 6512.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6514.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 16 | 166666.6667 | ACTION | 6516.208 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6516.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6517.348 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6518.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6519.348 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6519.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6520.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6520.348 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6520.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6521.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6523.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6524.222 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6524.2228 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6524.868 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6525.868 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6527.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6529.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6530.368 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6530.868 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6532.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6533.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6534.368 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6535.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6537.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6537.868 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6539.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6540.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6546.2846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6586.2846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6591.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6592.7013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6593.0813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6595.0813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6596.0813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6596.8413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6598.8413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6599.8413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6600.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6602.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6603.9813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6605.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6607.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6608.5013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6609.5013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6611.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6613.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6614.0013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6614.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6616.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6617.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6618.0013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6619.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6621.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6621.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6623.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6624.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6629.918 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 35 | 364583.3333 | ACTION | 6664.918 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6704.918 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6710.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6711.3346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6711.7146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6713.7146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6714.7146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6715.4746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6717.4746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6718.4746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6719.6146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6721.6146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6722.6146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6724.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6726.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6727.1346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6728.1346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6729.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6731.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6732.6346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6733.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6734.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6736.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6736.6346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6738.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6739.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6740.1346 | TurbineInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 6757.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6758.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6760.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6765.5513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6805.5513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6810.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6811.968 | TurbineInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 6823.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6824.348 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6826.348 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6827.348 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6828.108 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6830.108 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6831.108 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6832.248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6834.248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6835.248 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6836.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6838.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6839.768 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6840.768 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6842.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6844.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6845.268 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6845.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6847.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6848.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6849.268 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6850.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6852.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6852.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6854.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6855.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6861.1846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6901.1846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6906.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6907.6013 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 6913.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6913.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 6915.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6917.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6918.9813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6919.7413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6921.7413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6922.7413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6923.8813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6925.8813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6926.8813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6928.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6930.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6931.4013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6932.4013 | TurbineInstallation
| WTIV | Delay | 43 | 447916.6667 | ACTION | 6975.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6976.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6978.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6979.9013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6980.4013 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 6983.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6984.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6986.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6986.9013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6988.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6989.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6990.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6991.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6993.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6998.818 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7038.818 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7044.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7045.2346 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 7049.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7049.6146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7051.6146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7052.6146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7053.3746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 7055.3746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7057.3746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7058.3746 | TurbineInstallation
| WTIV | Delay | 34 | 354166.6667 | ACTION | 7092.3746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7093.5146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7095.5146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7096.5146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7098.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7100.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7101.0346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7102.0346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7103.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7105.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7106.5346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7107.0346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7108.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7110.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7110.5346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7112.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7113.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7114.0346 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 675.8 | 3379000 | ACTION | 7114.0346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 589.8118 | 2949059.2259 | ACTION | 7114.0346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7114.0355 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7115.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7117.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7117.2787 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7119.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7121.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7122.4513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7123.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7125.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7127.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7128.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7128.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7129.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7131.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7133.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7135.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7137.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7139.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7140.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7141.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7141.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7143.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7145.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7147.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7149.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7151.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7152.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7153.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7154.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7156.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7158.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7160.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7162.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7162.4513 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7164.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7164.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7165.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7166.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7167.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7168.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7168.868 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7169.248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7170.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7171.248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7172.248 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7172.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7173.008 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7174.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7175.008 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7176.008 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7176.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7177.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7177.148 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7177.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7178.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7179.148 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7180.148 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7180.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7181.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7182.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7183.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7184.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7184.668 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7185.668 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7186.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7187.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7188.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7189.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7189.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7190.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7190.168 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7190.668 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7190.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7192.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7193.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7194.022 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7194.0228 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7194.168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7195.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7197.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7197.668 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7199.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7200.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7206.0846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 16 | 166666.6667 | ACTION | 7222.0846 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7262.0846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7267.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7268.5013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7268.8813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7270.8813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7271.8813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7272.6413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7274.6413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7275.6413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7276.7813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7278.7813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7279.7813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7281.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7283.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7284.3013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7285.3013 | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 7298.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7299.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 7 | 72916.6667 | ACTION | 7306.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7308.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7309.8013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7310.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7311.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7313.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7313.8013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7315.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7316.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7317.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7318.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7320.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7325.718 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7365.718 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7371.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7372.1346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7372.5146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7374.5146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7375.5146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7376.2746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7378.2746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7379.2746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7380.4146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7382.4146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7383.4146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7384.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7386.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7387.9346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7388.9346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7390.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7392.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7393.4346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7393.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7395.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7396.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7397.4346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7398.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7400.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7400.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7402.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7403.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7409.3513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 56 | 583333.3333 | ACTION | 7465.3513 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7505.3513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7510.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7511.768 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7512.148 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7514.148 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7515.148 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7515.908 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7517.908 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7518.908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7520.048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7522.048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7523.048 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7524.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 25 | 260416.6667 | ACTION | 7549.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7551.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7552.568 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7553.568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7555.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7557.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7558.068 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7558.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7560.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7561.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7562.068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7563.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7565.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7565.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7567.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7568.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7573.9846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7613.9846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7619.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7620.4013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7620.7813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7622.7813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7623.7813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7624.5413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7626.5413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7627.5413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7628.6813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7630.6813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7631.6813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7633.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7635.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7636.2013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7637.2013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7638.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7640.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7641.7013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7642.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7643.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7645.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7645.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7647.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7648.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7649.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7650.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7652.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7657.618 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7697.618 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7703.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7704.0346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7704.4146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7706.4146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7707.4146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7708.1746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7710.1746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7711.1746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7712.3146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 7714.3146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7716.3146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7717.3146 | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 7724.3146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7725.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7727.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7728.8346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7729.8346 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 7731.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7733.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7735.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7736.3346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7736.8346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7738.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7739.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7740.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7741.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7743.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7743.8346 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 629.8 | 3149000 | ACTION | 7743.8346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 549.8118 | 2749059.2259 | ACTION | 7743.8346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7743.8355 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7745.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7746.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7747.0787 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7749.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7751.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7752.2513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7753.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7755.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7757.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7757.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7758.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7759.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7761.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7763.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7765.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7767.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7769.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7770.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7770.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7771.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7773.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7775.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7777.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7779.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7781.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7782.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7783.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7783.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7785.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7787.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7789.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7791.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7792.2513 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7793.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7794.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7795.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7796.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7797.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7798.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7798.668 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7799.048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7800.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7801.048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7802.048 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7802.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7802.808 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7804.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7804.808 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7805.808 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7806.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7806.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7806.948 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7807.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7808.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7808.948 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7809.948 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7810.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7811.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7812.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7813.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7814.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7814.468 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7815.468 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7816.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7816.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7818.3287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7818.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7819.0787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7819.8287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7819.968 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7820.468 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7820.5787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7821.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7823.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7823.822 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7823.8228 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7823.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7825.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7826.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7827.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7828.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7830.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7835.8846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7875.8846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7881.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7882.3013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7882.6813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7884.6813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7885.6813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7886.4413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7888.4413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7889.4413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7890.5813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7892.5813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7893.5813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7895.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7897.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7898.1013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7899.1013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7900.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7902.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7903.6013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7904.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7905.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7907.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7907.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7909.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7910.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7911.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7912.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7914.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7919.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7959.518 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7964.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7965.9346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7966.3146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7968.3146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7969.3146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7970.0746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7972.0746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7973.0746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7974.2146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7976.2146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7977.2146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7978.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7980.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7981.7346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7982.7346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7984.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7986.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7987.2346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7987.7346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7989.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7990.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7991.2346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7992.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7994.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7994.7346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7996.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7997.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8003.1513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8043.1513 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 8051.1513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8056.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8057.568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8057.948 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8059.948 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8060.948 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8061.708 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8063.708 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8064.708 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8066.708 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8067.848 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 5 | 52083.3333 | ACTION | 8072.848 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8074.848 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8075.848 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8077.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8079.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8080.368 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8081.368 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 8085.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8086.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8088.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8089.868 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8090.368 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8091.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8093.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8093.868 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8094.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8096.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8097.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8098.368 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8099.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8101.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8106.7846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 65 | 677083.3333 | ACTION | 8171.7846 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8211.7846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8217.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8218.2013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8218.5813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8220.5813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8221.5813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8222.3413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8224.3413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8225.3413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8226.4813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8228.4813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8229.4813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8231.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8233.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8234.0013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8235.0013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8236.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8238.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8239.5013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8240.0013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8241.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8243.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8243.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8245.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8246.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8247.0013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8248.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8250.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8255.418 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8295.418 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8300.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8301.8346 | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 8314.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8315.2146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8317.2146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8319.2146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8320.2146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8320.9746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8322.9746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8323.9746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8325.1146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8327.1146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8328.1146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8329.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8331.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8332.6346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8333.6346 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 8341.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8343.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8345.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8346.1346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8346.6346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8348.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8349.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8350.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8351.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8353.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8353.6346 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 609.8 | 3049000 | ACTION | 8353.6346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 529.8118 | 2649059.2259 | ACTION | 8353.6346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8353.6355 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8355.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8356.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8356.8787 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8358.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8360.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8362.0513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8362.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8364.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8366.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8367.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8368.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8369.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8371.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8373.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8375.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8377.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8379.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8379.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8380.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8381.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8383.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8385.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8387.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8389.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8391.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8392.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8392.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8393.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8395.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8397.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8399.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8401.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8402.0513 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8403.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8404.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8405.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8405.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8407.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8407.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8408.468 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8408.848 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8409.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8410.848 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8411.848 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8411.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8412.608 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8413.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8414.608 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8415.608 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8415.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 1 | 5000 | ACTION | 8416.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8417.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 33 | 165000 | ACTION | 8450.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8451.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 36 | 375000 | ACTION | 8451.608 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 1 | 5000 | ACTION | 8452.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8452.748 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8453.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8454.748 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8455.748 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8457.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 6 | 30000 | ACTION | 8459.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8459.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8460.268 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8461.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8461.268 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8462.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8463.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8464.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8465.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8465.768 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8466.268 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8467.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8467.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8469.1287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8469.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8469.768 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8469.8787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8470.6287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8471.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8471.3787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8472.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8473.268 | TurbineInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8474.622 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8474.6228 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8474.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8476.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8481.6846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8521.6846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8527.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8528.1013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8528.4813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8530.4813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8531.4813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8532.2413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8534.2413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8535.2413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8536.3813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8538.3813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8539.3813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8540.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8542.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8543.9013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8544.9013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8546.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8548.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8549.4013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8549.9013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8551.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8552.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8553.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8554.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8556.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8556.9013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8558.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8559.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8565.318 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 33 | 343750 | ACTION | 8598.318 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8638.318 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8643.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8644.7346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8645.1146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8647.1146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8648.1146 | TurbineInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 8672.1146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8672.8746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8674.8746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8675.8746 | TurbineInstallation
| WTIV | Delay | 42 | 437500 | ACTION | 8717.8746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8719.0146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8721.0146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8722.0146 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8723.0146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8724.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8726.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8727.5346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8728.5346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8730.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8732.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8733.0346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8733.5346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8735.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8736.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8737.0346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8738.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8740.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8740.5346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8742.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8743.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8748.9513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8788.9513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8794.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8795.368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8795.748 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8797.748 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8798.748 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8799.508 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8801.508 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8802.508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8803.648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8805.648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8806.648 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8808.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8810.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8811.168 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8812.168 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8813.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8815.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8816.668 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8817.168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8818.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8820.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8820.668 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8822.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8823.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8824.168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8825.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8827.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8832.5846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8872.5846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8878.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8879.0013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8879.3813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8881.3813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8882.3813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8883.1413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8885.1413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8886.1413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8887.2813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8889.2813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8890.2813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8891.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8893.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8894.8013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8895.8013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8897.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8899.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8900.3013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8900.8013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8902.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8903.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8904.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8905.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8907.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8907.8013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8909.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8910.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8916.218 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8956.218 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8961.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8962.6346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8963.0146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8965.0146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8966.0146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8966.7746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8968.7746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8969.7746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8970.9146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8972.9146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8973.9146 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8974.9146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8976.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8978.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8979.4346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8980.4346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8981.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8983.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8984.9346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8985.4346 | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 8998.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8999.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9001.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9001.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9003.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9004.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9005.4346 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 651.8 | 3259000 | ACTION | 9005.4346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 530.8118 | 2654059.2259 | ACTION | 9005.4346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9005.4355 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9006.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9008.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9008.6787 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9010.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9012.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9013.8513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9014.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9016.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9018.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9019.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9020.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9020.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9022.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9024.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9026.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9028.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9030.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9031.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9032.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9033.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9035.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9037.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9039.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9041.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9043.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9043.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9044.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9045.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9047.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9049.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9051.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9053.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9053.8513 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9055.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9056.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9056.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9057.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9059.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9059.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9060.268 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9060.648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9061.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9062.648 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9063.648 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9063.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9064.408 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9065.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9066.408 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9067.408 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9067.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9068.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9068.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9069.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9069.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9070.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9071.548 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9071.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9073.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9073.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9075.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9075.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9076.068 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9077.068 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9077.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9078.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9079.9287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9080.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9080.6787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9081.4287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9081.568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9082.068 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9082.1787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9083.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9085.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9085.422 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9085.4228 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9085.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9087.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9088.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9089.068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9090.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9092.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9097.4846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9137.4846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9142.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9143.9013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9144.2813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9146.2813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9147.2813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9148.0413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9150.0413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9151.0413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9152.1813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9154.1813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9155.1813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9156.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9158.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9159.7013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9160.7013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9162.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9164.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9166.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9167.2013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9167.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9169.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9170.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9171.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9172.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9174.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9174.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9176.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 4 | 41666.6667 | ACTION | 9180.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9181.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9187.118 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9227.118 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9232.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9233.5346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9233.9146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9235.9146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9236.9146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9237.6746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9239.6746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9240.6746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9241.8146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9243.8146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9244.8146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9246.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9248.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9249.3346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9250.3346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9251.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9253.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9254.8346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9255.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9256.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9258.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9258.8346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9260.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9261.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9262.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9263.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9265.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9270.7513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9310.7513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9316.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9317.168 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9319.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9319.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9321.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9322.548 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 9328.548 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9329.308 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9331.308 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9332.308 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9333.448 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9335.448 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9336.448 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9337.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9339.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9340.968 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9341.968 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9343.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9345.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9346.468 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9346.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9348.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9349.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9350.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9351.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9353.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9353.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9355.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9356.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9362.3846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9402.3846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9407.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9408.8013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9409.1813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9411.1813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9412.1813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9412.9413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9414.9413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9415.9413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9417.0813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9419.0813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9420.0813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9421.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9423.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9424.6013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9425.6013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9427.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9429.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9430.1013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9430.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9432.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9433.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9434.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9435.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9437.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9437.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9439.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9440.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9446.018 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9486.018 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9491.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9492.4346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9492.8146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9494.8146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9495.8146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9496.5746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9498.5746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9499.5746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9500.7146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9502.7146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9503.7146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9505.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9507.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9508.2346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9509.2346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9510.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9512.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9513.7346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9514.2346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9515.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9517.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9517.7346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9519.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 13 | 135416.6667 | ACTION | 9532.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9533.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9534.2346 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 528.8 | 2644000 | ACTION | 9534.2346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 448.8118 | 2244059.2259 | ACTION | 9534.2346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9534.2355 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9535.7346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9537.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9537.4787 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9539.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9541.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9542.6513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9543.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9545.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9547.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9548.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9548.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9549.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9551.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9553.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9555.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9557.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9559.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9560.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9561.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9561.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9563.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9565.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9567.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9569.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9571.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9572.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9573.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9574.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9576.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9578.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9580.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9582.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9582.6513 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9584.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9584.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9585.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9586.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9588.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9588.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9589.068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9589.448 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9590.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9591.448 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9592.448 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9592.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9593.208 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9594.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9595.208 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9596.208 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9596.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9597.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9597.348 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9597.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9598.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9599.348 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9600.348 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9600.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9601.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9602.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9603.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9604.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9604.868 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9605.868 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9606.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9607.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9608.7287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9609.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9609.4787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9610.2287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9610.368 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9610.868 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9610.9787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9612.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9613.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9614.222 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9614.2228 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9614.368 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9615.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9617.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9617.868 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9619.368 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9620.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9626.2846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9666.2846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9671.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9672.7013 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9674.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9675.0813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9677.0813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9678.0813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9678.8413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9680.8413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9681.8413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9682.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9684.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9685.9813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9687.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9689.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9690.5013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9691.5013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9693.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9695.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9696.0013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9696.5013 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9697.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9699.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9700.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9701.0013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9702.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9704.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9704.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9706.0013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9707.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9712.918 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9752.918 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9758.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9759.3346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9759.7146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9761.7146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9762.7146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9763.4746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9765.4746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9766.4746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9767.6146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9769.6146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9770.6146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9772.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9774.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9775.1346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9776.1346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9777.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9779.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9780.6346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9781.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9782.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9784.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9784.6346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9786.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9787.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9788.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9789.6346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9791.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9796.5513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9836.5513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9841.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9842.968 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9843.348 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9845.348 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9846.348 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9847.108 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9849.108 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9850.108 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9851.248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9853.248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9854.248 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9855.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9857.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9858.768 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9859.768 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9861.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9863.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9864.268 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9864.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9866.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9867.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9868.268 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9869.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9871.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9871.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9873.268 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9874.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9880.1846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9920.1846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9925.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9926.6013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9926.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9928.9813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9929.9813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9930.7413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9932.7413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9933.7413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9934.8813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9936.8813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9937.8813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9939.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9941.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9942.4013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9943.4013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9944.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9946.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9947.9013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9948.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9949.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9951.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9951.9013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9953.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9954.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9955.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9956.9013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9958.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9963.818 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10003.818 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10009.2346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10010.2346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10010.6146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10012.6146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10013.6146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10014.3746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10016.3746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10017.3746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10018.5146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10020.5146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10021.5146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10023.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10025.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10026.0346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10027.0346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10028.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10030.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10031.5346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10032.0346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10033.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10035.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10035.5346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10037.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10038.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10039.0346 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 504.8 | 2524000 | ACTION | 10039.0346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 424.8118 | 2124059.2259 | ACTION | 10039.0346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10039.0355 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10040.5346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10042.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10042.2787 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10044.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10046.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10047.4513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10048.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10050.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10052.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10053.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10053.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10054.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10056.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10058.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10060.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10062.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10064.5287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10065.2787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10066.0287 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10066.7787 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10070.022 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10070.0228 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10087.4513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10092.868 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10093.868 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10094.248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10096.248 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10097.248 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10098.008 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10100.008 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10101.008 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10102.148 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10104.148 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10105.148 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10106.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10108.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10109.668 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10110.668 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10112.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10114.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10115.168 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10115.668 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10117.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10118.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10119.168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10120.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10122.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10122.668 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10124.168 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10125.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10131.0846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10171.0846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10176.5013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10177.5013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10177.8813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10179.8813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10180.8813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10181.6413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10183.6413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10184.6413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10185.7813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10187.7813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10188.7813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10190.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10192.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10193.3013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10194.3013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10195.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10197.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10198.8013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10199.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10200.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10202.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10202.8013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10204.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10205.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10206.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10207.8013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10209.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10214.718 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10254.718 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10260.1346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10261.1346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10261.5146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10263.5146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10264.5146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10265.2746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10267.2746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10268.2746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10269.4146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10271.4146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10272.4146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10273.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10275.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10276.9346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10277.9346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10279.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10281.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10282.4346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10282.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10284.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10285.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10286.4346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10287.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10289.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10289.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10291.4346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10292.9346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10298.3513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10338.3513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10343.768 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10344.768 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10345.148 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10347.148 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10348.148 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10348.908 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10350.908 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10351.908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10353.048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10355.048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10356.048 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10357.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10359.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10360.568 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10361.568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10363.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10365.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10366.068 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10366.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10368.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10369.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10370.068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10371.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10373.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10373.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10375.068 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10376.568 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10381.9846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10421.9846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10427.4013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10428.4013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10428.7813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10430.7813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10431.7813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10432.5413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10434.5413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10435.5413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10436.6813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10438.6813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10439.6813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10441.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10443.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10444.2013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10445.2013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10446.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10448.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10449.7013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10450.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10451.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10453.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10453.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10455.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10456.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10457.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10458.7013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10460.2013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10465.618 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10505.618 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10511.0346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10512.0346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10512.4146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10514.4146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10515.4146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10516.1746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10518.1746 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10519.1746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10520.3146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10522.3146 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10523.3146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10524.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10526.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10527.8346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10528.8346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10530.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10532.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10533.3346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10533.8346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10535.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10536.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10537.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10538.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10540.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10540.8346 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 501.8 | 2509000 | ACTION | 10540.8346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 470.8118 | 2354059.2259 | ACTION | 10540.8346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10540.8355 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10542.3346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10543.8346 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10544.0787 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10549.2513 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10589.2513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10594.668 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10595.668 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10596.048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10598.048 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10599.048 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10599.808 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10601.808 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10602.808 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10603.948 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10605.948 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10606.948 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10608.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10610.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10611.468 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10612.468 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10613.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10615.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10616.968 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10617.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10618.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10620.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10620.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10622.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10623.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10624.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10625.968 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10627.468 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10632.8846 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10672.8846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10678.3013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10679.3013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10679.6813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10681.6813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10682.6813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10683.4413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10685.4413 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10686.4413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10687.5813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10689.5813 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10690.5813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10692.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10694.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10695.1013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10696.1013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10697.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10699.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10700.6013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10701.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10702.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10704.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10704.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10706.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10707.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10708.1013 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 167.2667 | 836333.3333 | ACTION | 10708.1013 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10708.1021 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10709.6013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10711.1013 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10711.3454 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10716.518 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 10719.7612 | TurbineInstallation