## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 72 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 80 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 92 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 100 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 112 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 120 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 163.2432 | MonopileInstallation
| WTIV | Delay | 40 | 416666.6667 | ACTION | 203.2432 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 243.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 248.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 249.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 252.6599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 253.383 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 253.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 254.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 269.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 271.3862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 272.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 273.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 277.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 282.8029 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 322.8029 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 328.2196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 329.2196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 332.2196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 332.9426 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 332.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 333.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 19 | 197916.6667 | ACTION | 352.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 367.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 369.9459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 370.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 371.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 375.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 381.3625 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 421.3625 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 426.7792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 427.7792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 430.7792 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 439.7792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 440.5023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 440.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 441.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 12 | 125000 | ACTION | 453.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 468.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 470.5055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 471.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 472.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 476.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 481.9222 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 521.9222 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 527.3389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 528.3389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 531.3389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 532.0619 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 532.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 533.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 548.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 550.0652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 551.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 552.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 556.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 561.4818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 601.4818 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 606.8985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 607.8985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 610.8985 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 611.6216 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 611.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 612.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 627.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 629.6248 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 630.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 631.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 635.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 641.0415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 681.0415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 686.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 687.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 690.4582 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 691.1812 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 691.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 692.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 707.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 709.1845 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 710.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 711.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 715.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 720.6011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 763.8444 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 775.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 783.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 795.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 803.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 815.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 823.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 835.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 843.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 855.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 863.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 875.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 883.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 885.8444 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 929.0876 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 969.0876 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 974.5043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 975.5043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 978.5043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 979.2274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 979.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 980.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 995.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 997.2306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 998.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 999.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1003.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1008.6473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1048.6473 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1054.0639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1055.0639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1058.0639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1058.787 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1058.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1059.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1074.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1076.7903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1077.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1078.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1082.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1088.2069 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1128.2069 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1133.6236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1134.6236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1137.6236 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1138.3467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1138.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1139.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1154.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1156.3499 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1157.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1158.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1162.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1167.7666 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1207.7666 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1213.1832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1214.1832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1217.1832 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1217.9063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1217.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1218.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1233.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1235.9096 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1236.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1237.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1241.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1247.3262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1287.3262 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1292.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1293.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1296.7429 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1297.466 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1297.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1298.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1313.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1315.4692 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1316.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1317.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1318.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1322.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1327.8859 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1367.8859 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1373.3025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1374.3025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1377.3025 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1378.0256 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1378.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1379.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1394.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1396.0288 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1397.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1398.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1402.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1407.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1450.6888 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1462.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1470.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1482.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1490.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1502.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1510.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1522.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1530.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1542.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1550.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1562.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1570.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1613.932 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1653.932 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1659.3487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1660.3487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1663.3487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1664.0717 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1664.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1665.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1680.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1682.075 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1683.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1684.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1688.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1693.4917 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1733.4917 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1738.9083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1739.9083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1742.9083 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1743.6314 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1743.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1744.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1759.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1761.6346 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1762.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1763.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1767.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1773.0513 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1813.0513 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1818.468 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1819.468 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1822.468 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1823.191 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1823.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1824.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1839.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1841.1943 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1842.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1843.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1847.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1852.6109 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1892.6109 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1898.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1899.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1902.0276 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1902.7507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1902.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1903.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1918.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1920.7539 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1921.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1922.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1926.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1932.1706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1972.1706 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1977.5873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1978.5873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1981.5873 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1982.3103 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1982.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1983.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1998.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2000.3136 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2001.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2002.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2006.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2011.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2051.7302 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2057.1469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2058.1469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2061.1469 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2061.87 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2061.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2062.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2077.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2079.8732 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2080.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2081.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2085.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2091.2899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2134.5331 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2146.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2154.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2166.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2174.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2186.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2194.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2206.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2214.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2226.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2234.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2246.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2254.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2297.7764 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2337.7764 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2343.193 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2344.193 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2347.193 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2347.9161 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2347.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2348.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2363.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2365.9194 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2366.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2367.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2371.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2377.336 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2417.336 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2422.7527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2423.7527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2426.7527 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2427.4758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2427.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2428.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2443.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2445.479 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2446.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2447.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2451.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2456.8957 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2496.8957 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2502.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2503.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2506.3123 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2507.0354 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2507.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2508.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2523.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2525.0387 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2526.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2527.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2531.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2536.4553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2576.4553 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2581.872 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2582.872 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2585.872 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2586.5951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2586.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2587.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2602.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2604.5983 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2605.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2606.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2610.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2616.015 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2656.015 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2661.4316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2662.4316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2665.4316 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2666.1547 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2666.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2667.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2682.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2684.158 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2685.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2686.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2690.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2695.5746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2735.5746 | MonopileInstallation
| WTIV | Delay | 30 | 312500 | ACTION | 2765.5746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2770.9913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2771.9913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2774.9913 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 2777.9913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2778.7144 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2780.7144 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2780.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2781.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2796.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2798.7176 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2799.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2800.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2804.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2810.1343 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2853.3775 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2865.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2873.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2885.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2893.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2905.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2913.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2925.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2933.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2945.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2953.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2965.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2973.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 41 | 427083.3333 | ACTION | 3014.3775 | MonopileInstallation
| WTIV | Delay | 19 | 197916.6667 | ACTION | 3033.3775 | MonopileInstallation
| WTIV | Transit | 2.2432 | 23367.1171 | ACTION | 3035.6208 | MonopileInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 3046.6208 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3086.6208 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3092.0374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3093.0374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3096.0374 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3096.7605 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3096.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3097.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3112.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3114.7637 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3115.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3116.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3120.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3126.1804 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3166.1804 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3171.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3172.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3175.5971 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3176.3201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3176.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3177.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3192.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3194.3234 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3195.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3196.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3200.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3205.7401 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3245.7401 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3251.1567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3252.1567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3255.1567 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3255.8798 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3255.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3256.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3271.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3273.883 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3274.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3275.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3279.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3285.2997 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3325.2997 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3330.7164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3331.7164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3334.7164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3335.4394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3336.4394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3336.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3337.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 15 | 156250 | ACTION | 3352.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3367.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3369.4427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3370.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3371.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3375.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3380.8594 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3420.8594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3426.276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3427.276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3430.276 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3430.9991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3431.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3432.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 31250 | ACTION | 3435.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3450.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3452.0023 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3453.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3454.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3458.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3463.419 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3503.419 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3508.8357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3509.8357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3512.8357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3513.5587 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3513.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3514.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3529.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3531.562 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3532.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3533.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 62500 | ACTION | 3539.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3543.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3548.9787 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3592.2219 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3604.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3612.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3624.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3632.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3644.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3652.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3664.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3672.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 31 | 322916.6667 | ACTION | 3703.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3715.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3723.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3735.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3743.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 15 | 156250 | ACTION | 3758.2219 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 3761.2219 | MonopileInstallation
| WTIV | Transit | 28.2432 | 294200.4505 | ACTION | 3789.4651 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3829.4651 | MonopileInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 3834.4651 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3839.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3840.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3843.8818 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3844.6049 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3844.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3845.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3860.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3862.6081 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3863.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3864.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3866.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3870.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3876.0248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3916.0248 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3921.4415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3922.4415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3925.4415 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3926.1645 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3926.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3927.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3942.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3944.1678 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3945.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3946.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3950.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3955.5844 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3995.5844 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4001.0011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4002.0011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4005.0011 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4005.7242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4005.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4006.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 55 | 572916.6667 | ACTION | 4061.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4076.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4078.7274 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4079.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4080.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 31250 | ACTION | 4083.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4087.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4093.1441 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4133.1441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4138.5608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4139.5608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4142.5608 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4143.2838 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4143.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4144.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4159.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4161.2871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4162.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4163.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4167.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4172.7037 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4212.7037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4218.1204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4219.1204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4222.1204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4222.8435 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4222.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4223.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4238.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4240.8467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4241.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4242.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4246.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4252.2634 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 26 | 270833.3333 | ACTION | 4278.2634 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4318.2634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4323.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4324.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4327.6801 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4328.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4329.4031 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4329.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4330.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4345.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4347.4064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4348.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4349.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4353.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4358.823 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 36 | 375000 | ACTION | 4394.823 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 4403.823 | MonopileInstallation
| WTIV | Transit | 7.2432 | 75450.4505 | ACTION | 4411.0663 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4423.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4431.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4443.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4451.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4463.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4471.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4483.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 68 | 708333.3333 | ACTION | 4551.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4559.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4571.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4579.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4591.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 12 | 125000 | ACTION | 4603.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4611.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 5 | 52083.3333 | ACTION | 4616.0663 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4617.0663 | MonopileInstallation
| WTIV | Transit | 23 | 239583.3333 | ACTION | 4640.0663 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4641.0663 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 4642.0663 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4643.0663 | MonopileInstallation
| WTIV | Transit | 7 | 72916.6667 | ACTION | 4650.0663 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4652.0663 | MonopileInstallation
| WTIV | Transit | 5 | 52083.3333 | ACTION | 4657.0663 | MonopileInstallation
| WTIV | Delay | 18 | 187500 | ACTION | 4675.0663 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 4676.0663 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4677.0663 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 4678.0663 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4679.0663 | MonopileInstallation
| WTIV | Transit | 0.24324 | 2533.7838 | ACTION | 4679.3095 | MonopileInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 4703.3095 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4743.3095 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4748.7262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4749.7262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4752.7262 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4753.4493 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4753.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4754.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4769.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4771.4525 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4772.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4773.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4777.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4782.8692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 52 | 541666.6667 | ACTION | 4834.8692 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4874.8692 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4880.2858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4881.2858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4884.2858 | MonopileInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 4889.2858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4890.0089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4890.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4891.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 62500 | ACTION | 4897.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4912.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4914.0122 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4915.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4916.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4920.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4925.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4965.4288 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4970.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4971.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4974.8455 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 4983.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4984.5686 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4984.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4985.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 4992.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 5007.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5009.5718 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5010.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5011.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5015.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5020.9885 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 5060.9885 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5066.4051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5067.4051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5070.4051 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5071.1282 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5071.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5072.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 5087.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5089.1315 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5090.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5091.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5095.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5100.5481 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 5140.5481 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5145.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5146.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5149.9648 | MonopileInstallation
| WTIV | Delay | 1261 | 13135416.6667 | ACTION | 6410.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6411.6878 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6411.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6412.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 6427.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6429.6911 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6430.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6431.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6432.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6436.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6442.1078 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6482.1078 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6487.5244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6488.5244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6491.5244 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6492.2475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6492.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6493.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 24 | 250000 | ACTION | 6517.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 6532.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6534.2507 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6535.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6536.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6540.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6545.6674 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6588.9107 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6600.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6608.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6620.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6628.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6640.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6648.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6660.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 6665.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6673.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6685.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6693.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6705.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6713.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 32 | 333333.3333 | ACTION | 6745.9107 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6746.9107 | MonopileInstallation
| WTIV | Transit | 11.2432 | 117117.1171 | ACTION | 6758.1539 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6798.1539 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6803.5706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6804.5706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6807.5706 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6808.2936 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6808.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6809.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 15 | 156250 | ACTION | 6824.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 6839.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6841.2969 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6842.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6843.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6847.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6852.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6892.7136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6898.1302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6899.1302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6902.1302 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6902.8533 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6902.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6903.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 13 | 135416.6667 | ACTION | 6916.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 6931.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6933.8565 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6934.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 83333.3333 | ACTION | 6942.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6943.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 41 | 427083.3333 | ACTION | 6984.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6988.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6994.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7034.2732 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7039.6899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7040.6899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 7043.6899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7044.4129 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7044.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7045.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 48 | 500000 | ACTION | 7093.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 7108.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 7110.4162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7111.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7112.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7116.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7121.8328 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7161.8328 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7167.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7168.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 7171.2495 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7171.9726 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7171.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7172.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 7187.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 7189.9758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7190.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7191.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7195.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7201.3925 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 21 | 218750 | ACTION | 7222.3925 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7262.3925 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7267.8092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7268.8092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 7271.8092 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7272.5322 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7272.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7273.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 34 | 354166.6667 | ACTION | 7307.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 7322.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 7324.5355 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7325.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7326.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7330.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7335.9521 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7375.9521 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7381.3688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7382.3688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 7385.3688 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7386.0919 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7386.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7387.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 7402.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 7404.0951 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7405.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7406.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 60 | 625000 | ACTION | 7466.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7470.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7475.5118 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7518.755 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 7530.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 7538.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 7550.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 7558.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7601.9983 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7641.9983 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7647.4149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7648.4149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 7651.4149 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7652.138 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7652.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7653.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 7668.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 7670.1413 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7671.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 7675.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7676.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7680.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7685.5579 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7725.5579 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7730.9746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7731.9746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 7734.9746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7735.6977 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7735.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7736.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 7751.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 7753.7009 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7754.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7755.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7759.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7765.1176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 7765.1176 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 7765.1176 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 7765.1176 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7767.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7769.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7771.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7773.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7775.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7775.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7776.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7777.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7779.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7781.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7783.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7785.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7787.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7788.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7788.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7789.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7791.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7793.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7795.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7797.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7799.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7800.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7801.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7801.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7803.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7805.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7807.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7808.3608 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7809.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7811.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7812.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7813.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7814.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7816.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7818.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7820.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7822.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7824.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7824.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7825.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7826.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7828.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7830.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7832.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7834.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7836.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7837.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7837.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7838.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 73.5 | 367500 | ACTION | 7838.6176 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7840.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7842.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7844.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7846.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7848.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7849.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7850.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7850.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7852.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7854.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7856.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7858.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7860.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7861.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7862.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7863.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7865.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7867.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7869.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7871.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7873.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7873.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7874.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7875.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7877.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7879.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7881.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7881.8608 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7881.8617 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 73.5008 | 765633.6892 | ACTION | 7881.8617 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7883.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7885.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7886.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7886.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7887.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7889.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7891.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7893.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7895.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7897.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7898.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7899.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7899.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7901.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7903.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7905.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7907.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7909.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7910.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7911.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7912.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7921.8617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7927.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7928.2783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7928.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7930.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7931.6583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7932.4183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7934.4183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7935.4183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7936.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7938.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7939.5583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7941.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7943.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7944.0783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7945.0783 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7946.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7947.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7949.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7950.5783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7951.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7952.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7954.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7954.5783 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7955.3608 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7955.3617 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7956.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7957.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7958.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7959.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7961.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7966.495 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8006.495 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8011.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8012.9117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8013.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8015.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8016.2917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8017.0517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8019.0517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8020.0517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8021.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8023.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8024.1917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8025.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8027.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8028.7117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8029.7117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8031.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8033.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8034.2117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8034.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8036.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8037.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8038.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8039.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8041.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8041.7117 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 8051.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8053.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8054.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8060.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8100.1283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8105.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8106.545 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8106.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8108.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8109.925 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8110.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8112.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8113.685 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8114.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8116.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8117.825 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8119.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8121.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8122.345 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8123.345 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8124.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8126.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8127.845 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8128.345 | TurbineInstallation
| WTIV | Delay | 43 | 447916.6667 | ACTION | 8171.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8172.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8174.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8174.845 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8176.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8177.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8178.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8179.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8181.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8183.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8188.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8228.7617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8234.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8235.1783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8235.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8237.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8238.5583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8239.3183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8241.3183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8242.3183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8243.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8245.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8246.4583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8247.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8249.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8250.9783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8251.9783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8253.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8255.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8256.4783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8256.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8258.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8259.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8260.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8261.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8263.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8263.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8265.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8266.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8272.395 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 66 | 687500 | ACTION | 8338.395 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8378.395 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8383.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8384.8117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8385.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8387.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8388.1917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8388.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8390.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8391.9517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8393.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8395.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8396.0917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8397.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8399.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8400.6117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8401.6117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8403.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8405.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8406.1117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8406.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8408.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8409.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8410.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8411.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8413.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8413.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8415.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8416.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 32 | 333333.3333 | ACTION | 8448.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8454.0283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8494.0283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8499.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8500.445 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8500.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8502.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8503.825 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8504.585 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8506.585 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8507.585 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8508.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8510.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8511.725 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8513.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8515.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8516.245 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8517.245 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8518.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8520.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8521.745 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8522.245 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8523.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8525.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8525.745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8527.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8528.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8529.245 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 647.3833 | 3236916.6667 | ACTION | 8529.245 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Queue | 573.8833 | 2869416.6667 | ACTION | 8529.245 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8529.2458 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8530.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8532.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8537.6617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8572.4891 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8574.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8576.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8577.6617 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8578.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8580.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8582.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8583.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8583.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8583.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8584.0783 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8584.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8586.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8588.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8590.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 83333.3333 | ACTION | 8592.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8592.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8592.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 8602.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8604.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 12 | 60000 | ACTION | 8604.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8605.4583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8606.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8606.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8607.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8608.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8608.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8608.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8609.2183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8610.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8610.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8612.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8612.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8613.3583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8614.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8614.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8616.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8616.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8617.8783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8618.8783 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8618.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8619.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8620.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8620.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8621.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8622.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8623.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8623.3783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8623.8783 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8625.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8625.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8626.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8627.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8627.3783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8628.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8629.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8630.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8630.8783 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8631.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8631.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8632.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8632.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8633.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8633.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8635.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8637.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8639.295 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8639.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8641.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8643.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8644.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8644.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8645.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8647.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8649.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8651.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8653.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8655.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8656.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8657.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8657.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 82 | 854166.6667 | ACTION | 8721.295 | TurbineInstallation
| Feeder 0 | Delay | 78 | 390000 | ACTION | 8735.9891 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8761.295 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8766.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8767.7117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8768.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8770.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8771.0917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8771.8517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8773.8517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8774.8517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8775.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8777.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8778.9917 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8779.2323 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8779.2331 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8780.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8782.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8783.5117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8784.5117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8786.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8788.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8789.0117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8789.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8791.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8792.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8793.0117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8794.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8796.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8796.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8798.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8799.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8804.9283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8844.9283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8850.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8851.345 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8851.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8853.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8854.725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8855.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8857.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8858.485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8859.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8861.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8862.625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8864.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8866.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8867.145 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8868.145 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8869.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8871.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8872.645 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8873.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8874.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8876.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8876.645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8878.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8879.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8880.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8881.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8883.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8888.5617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8928.5617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8933.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8934.9783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8935.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8937.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8938.3583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8939.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8941.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8942.1183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8943.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8945.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8946.2583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8947.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8949.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8950.7783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8951.7783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8953.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8955.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8956.2783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8956.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8958.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8959.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8960.2783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8961.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8963.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8963.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8965.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8966.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8972.195 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9012.195 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9017.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9018.6117 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 9021.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9021.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9023.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9024.9917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9025.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9027.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9028.7517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9029.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9031.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9032.8917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9034.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9036.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9037.4117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9038.4117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9039.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9041.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9042.9117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9043.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9044.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9046.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9046.9117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9048.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9049.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9050.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9051.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9053.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9058.8283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9098.8283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9104.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9105.245 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9105.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9107.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9108.625 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9109.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9111.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9112.385 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9113.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9115.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9116.525 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9118.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9120.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9122.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9123.045 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9124.045 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9125.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9127.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9128.545 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9129.045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9130.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9132.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9132.545 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9134.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9135.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9136.045 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 606.8 | 3034000 | ACTION | 9136.045 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Queue | 356.8118 | 1784059.2259 | ACTION | 9136.045 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9136.0458 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9137.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9139.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9144.4617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9179.2891 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9181.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9183.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9184.4617 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9185.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9187.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9189.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9189.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9190.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9190.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9190.8783 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9191.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9192.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9193.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9193.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9195.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9195.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9196.2583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9197.0183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9197.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9199.0183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9199.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9200.0183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9201.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9201.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9202.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9203.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9203.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9203.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9204.1583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9205.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9205.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9207.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9207.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9208.6783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9209.6783 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9209.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9211.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9211.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9213.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9213.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9214.1783 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9214.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9214.6783 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9215.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9216.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9216.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9217.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9218.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9218.1783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9219.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9220.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9221.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9221.6783 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9222.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9223.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9224.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9224.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9226.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9226.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9227.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9228.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9230.095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9230.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9232.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9234.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9236.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9238.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9239.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9239.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9240.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9242.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9244.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9246.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9248.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9250.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9251.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9252.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9252.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9270.095 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9275.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9276.5117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9276.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9278.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9279.8917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9280.6517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9282.6517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9283.6517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9284.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9286.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9287.7917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9289.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9291.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9292.3117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9293.3117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9294.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9296.0323 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9296.0331 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9296.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9297.8117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9298.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9299.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9301.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9301.8117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9303.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9304.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9305.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9306.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9308.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9313.7283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9353.7283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9359.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9360.145 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9360.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9362.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9363.525 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9364.285 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9366.285 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9367.285 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9368.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9370.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9371.425 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9372.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9374.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9375.945 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9376.945 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9378.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9380.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9381.445 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9381.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9383.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9384.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9385.445 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9386.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9388.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9388.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9390.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9391.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9397.3617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9437.3617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9442.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9443.7783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9444.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9446.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9447.1583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9447.9183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9449.9183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9450.9183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9452.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9454.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9455.0583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9456.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9458.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9459.5783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9460.5783 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9461.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9463.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9465.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9466.0783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9466.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9468.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9469.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9470.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9471.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9473.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9473.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9475.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9476.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9481.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9521.995 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 9525.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9531.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9532.4117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9532.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9534.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9535.7917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9536.5517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9538.5517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9539.5517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9540.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9542.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9543.6917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9545.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9546.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9548.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9549.2117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9550.2117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9551.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9553.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9555.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9556.7117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9557.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9558.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9560.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9560.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9562.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9563.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9564.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9565.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9567.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9572.6283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9612.6283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9618.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9619.045 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9619.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9621.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9622.425 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9623.185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9625.185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9626.185 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9627.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9629.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9630.325 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9631.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9633.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9634.845 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9635.845 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9637.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9639.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9640.345 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9640.845 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9642.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9643.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9644.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9645.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9647.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9647.845 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 511.8 | 2559000 | ACTION | 9647.845 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Queue | 351.8118 | 1759059.2259 | ACTION | 9647.845 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9647.8458 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9649.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9650.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9656.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9691.0891 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9693.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9695.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9696.2617 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9697.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9699.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9701.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9701.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9701.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9702.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9702.6783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9703.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9703.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9705.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9705.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9706.0583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9706.8183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9707.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9708.8183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9709.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9709.8183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9710.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9711.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9712.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9713.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9713.9583 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9714.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9714.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9715.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9715.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9717.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9717.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9718.4783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9719.4783 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9719.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9721.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9721.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9722.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9723.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9724.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9725.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9725.9783 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9726.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9726.4783 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9727.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9727.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9727.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9729.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9729.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9729.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9731.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9731.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9732.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9733.4783 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9733.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9734.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9735.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9736.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9737.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9738.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9739.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9740.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9741.895 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9742.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9744.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9746.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9748.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9750.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9750.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9751.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9752.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9754.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9756.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9758.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9760.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9762.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9763.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9763.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9764.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9781.895 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9787.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9788.3117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9788.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9790.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9791.6917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9792.4517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9794.4517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9795.4517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9796.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9798.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9799.5917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9801.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9803.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9804.1117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9805.1117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9806.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9807.8323 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9807.8331 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9808.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9809.6117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9810.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9811.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9813.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9813.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9815.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9816.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9817.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9818.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9820.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9825.5283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9865.5283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9870.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9871.945 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9872.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9874.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9875.325 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9876.085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9878.085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9879.085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9880.225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9882.225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9883.225 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9884.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9886.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9887.745 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9888.745 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9890.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9892.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9893.245 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9893.745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9895.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9896.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9897.245 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9898.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9900.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9900.745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9902.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9903.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9909.1617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9949.1617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9954.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9955.5783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9955.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9957.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9958.9583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9959.7183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9961.7183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9962.7183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9963.8583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9965.8583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9966.8583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9968.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9970.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9971.3783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9972.3783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9973.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9975.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9976.8783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9977.3783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9978.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9980.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9980.8783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9982.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9983.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9984.3783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9985.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9987.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9992.795 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10032.795 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10038.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10039.2117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10039.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10041.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10042.5917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10043.3517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10045.3517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10046.3517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10047.4917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10049.4917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10050.4917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10052.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10054.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10055.0117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10056.0117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10057.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10059.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10060.5117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10061.0117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10062.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10064.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10064.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10066.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10067.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10068.0117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10069.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10071.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10076.4283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10116.4283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10121.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10122.845 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10123.225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10125.225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10126.225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10126.985 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10128.985 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10129.985 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10131.125 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10133.125 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10134.125 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10135.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10137.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10138.645 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10139.645 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10141.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10143.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10144.145 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10144.645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10146.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10147.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10148.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10149.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10151.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10151.645 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 503.8 | 2519000 | ACTION | 10151.645 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Queue | 343.8118 | 1719059.2259 | ACTION | 10151.645 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10151.6458 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10153.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10154.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10160.0617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10194.8891 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10196.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10198.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10200.0617 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10200.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10202.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10204.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10205.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10205.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10206.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10206.4783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10206.8583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10207.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10208.8583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10209.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10209.8583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10210.6183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10211.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10212.6183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10213.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10213.6183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10214.7583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10215.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10216.7583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10217.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10217.7583 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10217.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10218.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10219.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10219.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10221.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10221.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10222.2783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10223.2783 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10223.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10224.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10225.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10226.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10227.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10227.7783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10228.2783 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10229.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10229.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10230.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10230.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10231.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10231.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10231.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10233.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10233.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10234.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10235.2783 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10235.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10236.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10237.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10238.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10239.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10241.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10242.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10243.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10243.695 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10243.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10245.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10247.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10249.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10251.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10253.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10254.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10255.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10256.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10258.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10260.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10262.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10264.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10266.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10266.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10267.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10268.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10283.695 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10289.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10290.1117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10290.4917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10292.4917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10293.4917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10294.2517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10296.2517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10297.2517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10298.3917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10300.3917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10301.3917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10302.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10304.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10305.9117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10306.9117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10308.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10310.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10311.4117 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10311.6323 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10311.6331 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10311.9117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10313.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10314.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10315.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10316.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10318.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10318.9117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10320.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10321.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10327.3283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10367.3283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10372.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10373.745 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10374.125 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10376.125 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10377.125 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10377.885 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10379.885 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10380.885 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10382.025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10384.025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10385.025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10386.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10388.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10389.545 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10390.545 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10392.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10394.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10395.045 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10395.545 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10397.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10398.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10399.045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10400.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10402.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10402.545 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10404.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10405.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10410.9617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10450.9617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10456.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10457.3783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10457.7583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10459.7583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10460.7583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10461.5183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10463.5183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10464.5183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10465.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10467.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10468.6583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10470.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10472.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10473.1783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10474.1783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10475.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10477.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10478.6783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10479.1783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10480.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10482.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10482.6783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10484.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10485.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10486.1783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10487.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10489.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10494.595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10534.595 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10540.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10541.0117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10541.3917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10543.3917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10544.3917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10545.1517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10547.1517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10548.1517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10549.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10551.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10552.2917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10553.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10555.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10556.8117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10557.8117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10559.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10561.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10562.3117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10562.8117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10564.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10565.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10566.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10567.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10569.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10569.8117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10571.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10572.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10578.2283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10618.2283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10623.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10624.645 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10625.025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10627.025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10628.025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10628.785 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10630.785 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10631.785 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10632.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10634.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10635.925 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10637.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10639.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10640.445 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10641.445 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10642.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10644.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10645.945 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10646.445 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10647.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10649.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10649.945 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 10653.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10655.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10656.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10657.445 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 505.8 | 2529000 | ACTION | 10657.445 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Queue | 345.8118 | 1729059.2259 | ACTION | 10657.445 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10657.4458 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10658.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10660.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10665.8617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 10700.6891 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10702.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10704.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10705.8617 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10706.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10708.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10710.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10711.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10711.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10712.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10712.2783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10712.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10712.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10714.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10714.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10715.6583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10716.4183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10716.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10718.4183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10718.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10719.4183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10720.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10720.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10722.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10722.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10723.5583 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10723.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10724.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10725.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10727.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10729.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10731.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 93750 | ACTION | 10732.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10733.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10734.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10735.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10735.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10736.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10736.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10737.0783 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10737.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10738.0783 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10739.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10739.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10741.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10741.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10742.5783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10743.0783 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10743.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10744.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10745.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10746.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10746.5783 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10747.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10748.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10748.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10748.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10749.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10749.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10750.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10751.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10751.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10753.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10753.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10755.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10757.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10758.495 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10759.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10760.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10761.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10761.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10763.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10765.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10767.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10769.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10771.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10772.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10773.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10774.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10798.495 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10803.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10804.9117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10805.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10807.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10808.2917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10809.0517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10811.0517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10812.0517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10813.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10815.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10816.1917 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 10817.4323 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10817.4331 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10817.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10819.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10820.7117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10821.7117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10823.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10825.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10826.2117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10826.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10828.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10829.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10830.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10831.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10833.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10833.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10835.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10836.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10842.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10882.1283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10887.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10888.545 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10888.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10890.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10891.925 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10892.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10894.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10895.685 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10896.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10898.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10899.825 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10901.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10903.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10904.345 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10905.345 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10906.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10908.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10909.845 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10910.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10911.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10913.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10913.845 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10915.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10916.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10917.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10918.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10920.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10925.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10965.7617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10971.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10972.1783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10972.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10974.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10975.5583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10976.3183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10978.3183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10979.3183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10980.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10982.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10983.4583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10984.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10986.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10987.9783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10988.9783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10990.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10992.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10993.4783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10993.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10995.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10996.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10997.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10998.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11000.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11000.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11002.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11003.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11009.395 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11049.395 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11054.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11055.8117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11056.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11058.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11059.1917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11059.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11061.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11062.9517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11064.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11066.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11067.0917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11068.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11070.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11071.6117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11072.6117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11074.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11076.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11077.1117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11077.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11079.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11080.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11081.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11082.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11084.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11084.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11086.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11087.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11093.0283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11133.0283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11138.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11139.445 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11139.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11141.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11142.825 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11143.585 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11145.585 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11146.585 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11147.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11149.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11150.725 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11152.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11154.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11155.245 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11156.245 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11157.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11159.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11160.745 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11161.245 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11162.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11164.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11164.745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11166.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11167.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11168.245 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 510.8 | 2554000 | ACTION | 11168.245 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Queue | 350.8118 | 1754059.2259 | ACTION | 11168.245 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11168.2458 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11169.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11171.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11176.6617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 11211.4891 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11213.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11215.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11216.6617 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11217.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11219.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11221.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11222.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11222.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11222.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11223.0783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11223.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11223.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11225.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11225.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11226.4583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11227.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11227.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11229.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11229.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11230.2183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11231.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11231.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11233.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11233.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11234.3583 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11234.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11235.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11235.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11235.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11237.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11237.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11238.8783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11239.8783 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11239.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11241.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11241.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11243.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11243.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11244.3783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11244.8783 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11245.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11246.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11246.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11247.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11247.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11248.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11248.3783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11249.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11250.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11251.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11251.8783 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11252.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11253.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11254.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11254.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11256.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11258.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11258.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11259.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11260.295 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11260.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11262.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11264.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11266.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11268.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11270.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11271.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11271.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11272.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11274.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11276.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11278.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11280.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11282.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11283.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11284.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11284.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11300.295 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11305.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11306.7117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11307.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11309.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11310.0917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11310.8517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11312.8517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11313.8517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11314.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11316.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11317.9917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11319.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11321.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11322.5117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11323.5117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11325.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11327.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11328.0117 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 11328.2323 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 11328.2331 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11328.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11330.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11331.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11332.0117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11333.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11335.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11335.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11337.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11338.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11343.9283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11383.9283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11389.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11390.345 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11390.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11392.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11393.725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11394.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11396.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11397.485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11398.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11400.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11401.625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11403.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11405.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11406.145 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11407.145 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11408.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11410.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11411.645 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11412.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11413.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11415.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11415.645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11417.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11418.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11419.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11420.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11422.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11427.5617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11467.5617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11472.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11473.9783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11474.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11476.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11477.3583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11478.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11480.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11481.1183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11482.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11484.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11485.2583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11486.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11488.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11489.7783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11490.7783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11492.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11494.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11495.2783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11495.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11497.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11498.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11499.2783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11500.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11502.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11502.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11504.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11505.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11511.195 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11551.195 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11556.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11557.6117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11557.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11559.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11560.9917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11561.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11563.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11564.7517 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 11566.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11567.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11569.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11570.8917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11572.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11574.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11575.4117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11576.4117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11577.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11579.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11580.9117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11581.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11582.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11584.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11584.9117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11586.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11587.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11588.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11589.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11591.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11596.8283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 54 | 562500 | ACTION | 11650.8283 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11690.8283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11696.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11697.245 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11697.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11699.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11700.625 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11701.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11703.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11704.385 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11705.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11707.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11708.525 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11710.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11712.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11713.045 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11714.045 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11715.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11717.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11718.545 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11719.045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11720.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11722.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11722.545 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11724.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11725.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11726.045 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 557.8 | 2789000 | ACTION | 11726.045 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Queue | 397.8118 | 1989059.2259 | ACTION | 11726.045 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11726.0458 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11727.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11729.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11734.4617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 11769.2891 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11771.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11773.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11774.4617 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11775.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11777.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11779.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11779.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11780.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11780.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11780.8783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11781.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11781.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11783.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11783.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11784.2583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11785.0183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11785.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11787.0183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11787.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11788.0183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11789.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11789.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11791.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11791.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11792.1583 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11792.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11793.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11793.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11793.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11795.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11796.6783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11797.6783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11799.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11801.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11802.1783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11802.6783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11804.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11805.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11806.1783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11807.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11809.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11809.6783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11811.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11812.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11818.095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 11837.0323 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 11837.0331 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11858.095 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11863.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11864.5117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11864.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11866.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11867.8917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11868.6517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11870.6517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11871.6517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11872.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11874.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11875.7917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11877.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11879.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11880.3117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11881.3117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11882.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11884.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11885.8117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11886.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11887.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11889.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11889.8117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11891.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11892.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11893.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11894.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11896.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11901.7283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 18 | 187500 | ACTION | 11919.7283 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11959.7283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11965.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11966.145 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11966.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11968.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11969.525 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11970.285 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11972.285 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11973.285 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11974.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11976.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11977.425 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11978.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11980.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11981.945 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11982.945 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11984.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11986.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11987.445 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11987.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11989.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11990.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11991.445 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11992.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11994.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11994.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11996.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11997.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12003.3617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 12043.3617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12048.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12049.7783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12050.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12052.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12053.1583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12053.9183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12055.9183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12056.9183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12058.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12060.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12061.0583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12062.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12064.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12065.5783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12066.5783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12068.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12070.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12071.0783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12071.5783 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 12073.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12075.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 12080.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12081.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12082.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12083.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12085.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12085.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12087.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12088.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12093.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 12133.995 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12139.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12140.4117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12140.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12142.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12143.7917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12144.5517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12146.5517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12147.5517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12148.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12150.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12151.6917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12153.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12155.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12156.2117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12157.2117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12158.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12160.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12161.7117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12162.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12163.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12165.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12165.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12167.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12168.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12169.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12170.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12172.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12177.6283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 12217.6283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12223.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12224.045 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12224.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12226.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12227.425 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12228.185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12230.185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12231.185 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12232.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12234.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12235.325 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12236.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12238.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12239.845 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12240.845 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12242.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12244.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12245.345 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12245.845 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12247.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12248.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12249.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12250.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12252.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12252.845 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 526.8 | 2634000 | ACTION | 12252.845 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Queue | 415.8118 | 2079059.2259 | ACTION | 12252.845 | TurbineInstallation | [15 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 12252.8458 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12254.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12255.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12261.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 12296.0891 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 12301.2617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12306.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12307.6783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12308.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12310.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12311.0583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12311.8183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12313.8183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12314.8183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12315.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12317.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12318.9583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12320.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12322.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12323.4783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12324.4783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12325.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12327.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12328.9783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12329.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12330.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12332.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12332.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12334.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12335.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12336.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12337.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12339.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12344.895 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 12384.895 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12390.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12391.3117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12391.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12393.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12394.6917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12395.4517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12397.4517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12398.4517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12399.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12401.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12402.5917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12404.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12406.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12407.1117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12408.1117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12409.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12411.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12412.6117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12413.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12414.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12416.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12416.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12418.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12419.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12420.1117 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 167.2667 | 836333.3333 | ACTION | 12420.1117 | TurbineInstallation | [15 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 12420.1125 | TurbineInstallation |  |  |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12421.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12423.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12428.5283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 12463.3557 | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12471.7716 | TurbineInstallation