## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 43.2432 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 45.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 45.5599 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 46.5599 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 49.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 50.283 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 50.2862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 51.2862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 52.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 54.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 55.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 56.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 23 | 383333.3333 | ACTION | 79.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 83.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 84.1029 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 88.1029 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 90.1029 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 90.4196 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 91.4196 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 94.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 95.1426 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 95.1459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 96.1459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 97.6459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 99.6459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 100.6459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 101.6459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 105.6459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 105.9625 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 109.2058 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 121.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 129.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 141.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 149.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 152.449 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 154.449 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 154.7657 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 155.7657 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 158.7657 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 159.7657 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 160.4888 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 160.492 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 161.492 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 20 | 333333.3333 | ACTION | 181.492 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 182.992 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 184.992 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 185.992 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 186.992 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 190.992 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 191.3087 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 193.3087 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 193.6253 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 194.6253 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 197.6253 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 198.3484 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 198.3517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 199.3517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 200.8517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 202.8517 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 203.8517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 204.8517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 208.8517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 209.1683 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 212.4116 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 224.4116 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 232.4116 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 244.4116 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 252.4116 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 255.6548 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 257.6548 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 257.9715 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 258.9715 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 261.9715 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 262.6945 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 262.6978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 263.6978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 265.1978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 267.1978 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 268.1978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 269.1978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 273.1978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 273.5145 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 275.5145 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 275.8311 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 276.8311 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 279.8311 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 280.5542 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 280.5574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 281.5574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 283.0574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 285.0574 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 286.0574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 287.0574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 291.0574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 291.3741 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 294.6174 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 306.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 314.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 326.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 334.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 337.8606 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 339.8606 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 340.1773 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 341.1773 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 344.1773 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 344.9003 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 344.9036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 345.9036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 347.4036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 349.4036 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 350.4036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 351.4036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 355.4036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 355.7202 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 357.7202 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 358.0369 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 359.0369 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 362.0369 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 362.76 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 362.7632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 363.7632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 365.2632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 367.2632 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 368.2632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 369.2632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 373.2632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 373.5799 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 376.8231 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 388.8231 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 396.8231 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 408.8231 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 416.8231 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 420.0664 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 422.0664 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 422.383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 423.383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 426.383 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 427.1061 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 427.1094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 428.1094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 429.6094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 431.6094 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 432.6094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 433.6094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 437.6094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 437.926 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 439.926 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 440.2427 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 441.2427 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 444.2427 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 444.9658 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 444.969 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 445.969 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 447.469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 449.469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 450.469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 451.469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 455.469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 455.7857 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 459.0289 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 471.0289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 479.0289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 491.0289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 499.0289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 502.2722 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 504.2722 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 504.5888 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 505.5888 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 508.5888 | MonopileInstallation
| WTIV | Delay | 83 | 1383333.3333 | ACTION | 591.5888 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 592.3119 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 592.3151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 593.3151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 594.8151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 596.8151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 597.8151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 598.8151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 602.8151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 603.1318 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 605.1318 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 605.4485 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 606.4485 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 609.4485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 610.1715 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 610.1748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 611.1748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 612.6748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 614.6748 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 615.6748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 616.6748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 620.6748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 620.9915 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 624.2347 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 636.2347 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 644.2347 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 656.2347 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 664.2347 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 667.4779 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 669.4779 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 669.7946 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 670.7946 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 673.7946 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 674.5177 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 674.5209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 675.5209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 677.0209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 679.0209 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 680.0209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 681.0209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 685.0209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 685.3376 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 687.3376 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 687.6543 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 688.6543 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 691.6543 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 692.3773 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 692.3806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 693.3806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 694.8806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 696.8806 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 697.8806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 698.8806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 702.8806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 703.1972 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 706.4405 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 718.4405 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 726.4405 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 738.4405 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 746.4405 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 749.6837 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 751.6837 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 752.0004 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 753.0004 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 756.0004 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 756.7235 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 756.7267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 757.7267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 759.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 761.2267 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 762.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 763.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 767.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 767.5434 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 769.5434 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 769.86 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 770.86 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 773.86 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 774.5831 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 774.5864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 775.5864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 777.0864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 779.0864 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 780.0864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 781.0864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 785.0864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 785.403 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 788.6463 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 800.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 808.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 820.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 828.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 831.8895 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 833.8895 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 834.2062 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 835.2062 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 838.2062 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 838.9292 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 838.9325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 839.9325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 841.4325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 843.4325 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 844.4325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 845.4325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 849.4325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 849.7492 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 851.7492 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 852.0658 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 853.0658 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 856.0658 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 856.7889 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 856.7921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 857.7921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 859.2921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 861.2921 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 862.2921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 863.2921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 867.2921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 867.6088 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 870.8521 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 882.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 913.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 921.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 933.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 941.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 945.0953 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 947.0953 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 947.412 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 948.412 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 951.412 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 952.135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 952.1383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 953.1383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 954.6383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 956.6383 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 957.6383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 958.6383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 962.6383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 962.955 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 964.955 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 965.2716 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 966.2716 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 969.2716 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 969.9947 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 969.9979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 970.9979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 972.4979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 974.4979 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 975.4979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 976.4979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 980.4979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 980.8146 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 984.0578 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 996.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1004.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1016.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 27 | 450000 | ACTION | 1043.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1051.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1054.3011 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1056.3011 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1056.6178 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1057.6178 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1060.6178 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1061.3408 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1061.3441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1062.3441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1063.8441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1065.8441 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1066.8441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1067.8441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1071.8441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1072.1607 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1074.1607 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1074.4774 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1075.4774 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1078.4774 | MonopileInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 1095.4774 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1096.2005 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1096.2037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1097.2037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1098.7037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1100.7037 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1101.7037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1102.7037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1106.7037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1107.0204 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1110.2636 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1122.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1130.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1142.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1150.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1153.5069 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1155.5069 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1155.8235 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1156.8235 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1159.8235 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1160.5466 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1160.5499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1161.5499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1163.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1165.0499 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1166.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 71 | 1183333.3333 | ACTION | 1237.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1238.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1242.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1242.3665 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1244.3665 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1244.6832 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1245.6832 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1248.6832 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1249.4063 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1249.4095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1250.4095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1251.9095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1253.9095 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1254.9095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1255.9095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1259.9095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1260.2262 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1263.4694 | MonopileInstallation
| WTIV | Delay | 20 | 333333.3333 | ACTION | 1283.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1295.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1303.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1315.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1323.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1326.7127 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1328.7127 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1329.0293 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1330.0293 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1333.0293 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 1334.0293 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1334.7524 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1334.7556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1335.7556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1337.2556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1339.2556 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1340.2556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1341.2556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1345.2556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1345.5723 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1347.5723 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1347.889 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1348.889 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1351.889 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1352.612 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1352.6153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1353.6153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1355.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1357.1153 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1358.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 1359.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1360.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1364.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1364.432 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1367.6752 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1379.6752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1387.6752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1399.6752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1407.6752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1410.9184 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1412.9184 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1413.2351 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1414.2351 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 20 | 333333.3333 | ACTION | 1434.2351 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1437.2351 | MonopileInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 1479.2351 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1479.9582 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1479.9614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1480.9614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1482.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1484.4614 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1485.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1486.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 1492.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1496.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1496.7781 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1498.7781 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1499.0948 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1500.0948 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1503.0948 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 1505.0948 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1505.8178 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1505.8211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1506.8211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1508.3211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1510.3211 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1511.3211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1512.3211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1516.3211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1516.6377 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1519.881 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1531.881 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1539.881 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1551.881 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1559.881 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1563.1242 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1565.1242 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1565.4409 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1566.4409 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1569.4409 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1570.164 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1570.1672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1571.1672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1572.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1574.6672 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1575.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1576.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 40 | 666666.6667 | ACTION | 1616.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1620.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1620.9839 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1622.9839 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1623.3005 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1624.3005 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1627.3005 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1628.0236 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1628.0269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1629.0269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 35 | 583333.3333 | ACTION | 1664.0269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1665.5269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1667.5269 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1668.5269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1669.5269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1673.5269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1673.8435 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1677.0868 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1689.0868 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1697.0868 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1709.0868 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1717.0868 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1720.33 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1722.33 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1722.6467 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1723.6467 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1726.6467 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1727.3697 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1727.373 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1728.373 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1729.873 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1731.873 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1732.873 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1733.873 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1737.873 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1738.1897 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1740.1897 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1740.5063 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1741.5063 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1744.5063 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1745.2294 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1745.2326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1746.2326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1747.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1749.7326 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1750.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1751.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 35 | 583333.3333 | ACTION | 1786.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1790.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1791.0493 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1794.2925 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1806.2925 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1814.2925 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1826.2925 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1834.2925 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1837.5358 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1839.5358 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1839.8525 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1840.8525 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1843.8525 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1844.5755 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1844.5788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1845.5788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1847.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1849.0788 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1850.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1851.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1855.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1855.3954 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1857.3954 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1857.7121 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1858.7121 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1861.7121 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1862.4352 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1862.4384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1863.4384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1864.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1866.9384 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1867.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1868.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1872.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1873.2551 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1876.4983 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1888.4983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1896.4983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1908.4983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1916.4983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1919.7416 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1921.7416 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1922.0582 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1923.0582 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1926.0582 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1926.7813 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1926.7846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1927.7846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1929.2846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1931.2846 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1932.2846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1933.2846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1937.2846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1937.6012 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1939.6012 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1939.9179 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1940.9179 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1943.9179 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1944.641 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1944.6442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1945.6442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1947.1442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1949.1442 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1950.1442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1951.1442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1955.1442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1955.4609 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1958.7041 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1970.7041 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1978.7041 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1990.7041 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1998.7041 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2001.9474 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2003.9474 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2004.264 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2005.264 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2008.264 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2008.9871 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2008.9903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2009.9903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2011.4903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2013.4903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2014.4903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2015.4903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2019.4903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2019.807 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2021.807 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2022.1237 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2023.1237 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2026.1237 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2026.8467 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2026.85 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2027.85 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2029.35 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2031.35 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2032.35 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2033.35 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2037.35 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2037.6667 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2040.9099 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2052.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2060.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2072.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2080.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2084.1531 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2086.1531 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2086.4698 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2087.4698 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2090.4698 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2091.1929 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2091.1961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2092.1961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2093.6961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2095.6961 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2096.6961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2097.6961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2101.6961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2102.0128 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2104.0128 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2104.3295 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2105.3295 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2108.3295 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2109.0525 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2109.0558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2110.0558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2111.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2113.5558 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2114.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 21 | 350000 | ACTION | 2135.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2136.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2140.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2140.8724 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2144.1157 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2156.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2164.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2176.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2184.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2187.3589 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2189.3589 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2189.6756 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2190.6756 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2193.6756 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2194.3987 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2194.4019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2195.4019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2196.9019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2198.9019 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2199.9019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2200.9019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2204.9019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2205.2186 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2207.2186 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2207.5352 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2208.5352 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2211.5352 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2212.2583 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2212.2616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2213.2616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2214.7616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2216.7616 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2217.7616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2218.7616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2222.7616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2223.0782 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2226.3215 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2238.3215 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2246.3215 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2258.3215 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2266.3215 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2269.5647 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2271.5647 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2271.8814 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2272.8814 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2275.8814 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2276.6044 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2276.6077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2277.6077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2279.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2281.1077 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2282.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2283.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 52 | 866666.6667 | ACTION | 2335.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2339.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2339.4244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2341.4244 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2341.741 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2342.741 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2345.741 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2346.4641 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2346.4673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2347.4673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2348.9673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2350.9673 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2351.9673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2352.9673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2356.9673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2357.284 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2360.5273 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2372.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 2403.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2411.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2423.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2431.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2434.7705 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2436.7705 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2437.0872 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2438.0872 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2441.0872 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2441.8102 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2441.8135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2442.8135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2444.3135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2446.3135 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2447.3135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2448.3135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2452.3135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2452.6301 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2454.6301 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2454.9468 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2455.9468 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2458.9468 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2459.6699 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2459.6731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2460.6731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2462.1731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2464.1731 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2465.1731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2466.1731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2470.1731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2470.4898 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2473.733 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2485.733 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2493.733 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2505.733 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2513.733 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2516.9763 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2518.9763 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2519.2929 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2520.2929 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2523.2929 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2524.016 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2524.0193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2525.0193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2526.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2528.5193 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2529.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2530.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2534.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2538.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2538.8359 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2540.8359 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2541.1526 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2542.1526 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2545.1526 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2545.8757 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2545.8789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2546.8789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2548.3789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2550.3789 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2551.3789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2552.3789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2556.3789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2556.6956 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2559.9388 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2571.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2579.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 2594.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2606.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2614.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2618.1821 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2620.1821 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2620.4987 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2621.4987 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2624.4987 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2625.2218 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2625.225 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2626.225 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2627.725 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2629.725 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2630.725 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2631.725 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2635.725 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2636.0417 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2638.0417 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2638.3584 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2639.3584 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2642.3584 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2644.3584 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2645.0814 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2645.0847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2646.0847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2647.5847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2649.5847 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2650.5847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2651.5847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2655.5847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2655.9014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 2655.9014 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2659.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2663.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2667.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2669.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2670.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2672.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2676.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2680.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2684.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 2699.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2700.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2702.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2703.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2707.1446 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2709.1446 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2709.4613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2712.4613 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 2713.4613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2714.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2720.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2723.2113 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2724.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2730.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2733.7113 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2734.7113 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2736.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2742.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2743.2113 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2744.2113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2745.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2749.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2750.2113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2751.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2755.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2756.2113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2757.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2761.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2761.5279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2763.5279 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2763.8446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2766.8446 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2767.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2773.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2776.5946 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 2790.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2792.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2798.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2801.0946 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2802.0946 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2803.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2809.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2810.5946 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2811.5946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2813.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2816.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2817.5946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2819.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2822.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2823.5946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2825.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2828.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2828.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2832.1545 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2836.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 2839.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2843.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2847.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2848.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2850.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2851.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2855.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2859.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2863.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2865.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2866.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2868.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2871.3978 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2873.3978 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2873.7144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2876.7144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2877.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 28 | 466666.6667 | ACTION | 2905.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2911.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2914.4644 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2915.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2921.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2924.9644 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2925.9644 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2927.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2933.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2934.4644 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2935.4644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2936.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2940.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2944.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2945.4644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2946.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2950.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2951.4644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2952.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2956.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2956.7811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2958.7811 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2959.0978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2962.0978 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2962.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2968.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2971.8478 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2973.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2979.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2982.3478 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2983.3478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2984.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2990.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2991.8478 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2992.8478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2994.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 29 | 483333.3333 | ACTION | 3023.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3026.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3027.8478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3029.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3032.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3033.8478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3035.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3038.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3039.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3042.4077 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3046.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3050.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 3081.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3085.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3086.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3088.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3089.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3093.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3097.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3101.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3103.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3104.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3106.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3109.6509 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3111.6509 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3111.9676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3114.9676 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3115.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3121.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3124.7176 | TurbineInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 3137.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3139.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3145.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3148.2176 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3149.2176 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3150.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3156.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3157.7176 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3158.7176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3160.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3163.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3164.7176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3166.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3169.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3170.7176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3172.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3175.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3176.0342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3178.0342 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3178.3509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3181.3509 | TurbineInstallation
| WTIV | Delay | 23 | 383333.3333 | ACTION | 3204.3509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3205.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3211.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3214.1009 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3215.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3221.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3224.6009 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3225.6009 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3227.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3233.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3234.1009 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3235.1009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3236.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3240.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3241.1009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3242.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3246.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3247.1009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3248.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3252.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3252.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3255.6608 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3259.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3263.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3267.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3269.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3270.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3272.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3276.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3280.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3284.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3285.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3287.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3288.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3291.9041 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3293.9041 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3294.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3297.2207 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3297.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3303.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3306.9707 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3308.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3314.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3317.4707 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3318.4707 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3319.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3325.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3326.9707 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3327.9707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3329.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3332.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3333.9707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3335.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3338.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3339.9707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3341.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3344.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3345.2874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3347.2874 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3347.6041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3350.6041 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3351.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3357.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3360.3541 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3361.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3367.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3370.8541 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3371.8541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3373.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3379.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3380.3541 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3381.3541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3382.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3386.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3387.3541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3388.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3392.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3393.3541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3394.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3398.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3398.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3401.914 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3405.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3409.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3413.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3415.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3416.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3418.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3422.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 46 | 766666.6667 | ACTION | 3468.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3472.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 24 | 400000 | ACTION | 3496.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3500.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3501.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3503.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3504.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3508.1572 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3510.1572 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3510.4739 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3513.4739 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3514.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3520.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3523.2239 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3524.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3530.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3533.7239 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3534.7239 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3536.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3542.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3543.2239 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3544.2239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3545.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3549.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3550.2239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3551.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3555.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3556.2239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3557.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3561.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3561.5406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3563.5406 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3563.8572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3566.8572 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3567.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3573.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3576.6072 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3578.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3584.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3587.1072 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3588.1072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3589.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3595.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3596.6072 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3597.6072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3599.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3602.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3603.6072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3605.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3608.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3609.6072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3611.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3614.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3614.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3618.1671 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3622.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3626.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3630.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3631.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3633.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3634.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3638.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3642.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3646.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3648.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3649.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3651.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3654.4104 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3656.4104 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3656.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3659.727 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3660.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3666.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3669.477 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3670.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 29 | 483333.3333 | ACTION | 3699.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3705.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3708.977 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3709.977 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3711.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3717.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3718.477 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3719.477 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3727.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3728.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 3750.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3754.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3755.477 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3756.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3760.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3761.477 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3762.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3766.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3766.7937 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3768.7937 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3769.1104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3772.1104 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3772.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3778.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3781.8604 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3783.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3789.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3792.3604 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3793.3604 | TurbineInstallation
| WTIV | Delay | 65 | 1083333.3333 | ACTION | 3858.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3859.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 3862.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3868.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3869.8604 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3870.8604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3872.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3875.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3876.8604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3878.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3881.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3882.8604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3884.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3887.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3888.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3891.4203 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3895.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3899.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3903.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3904.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3906.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3907.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3911.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3915.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3919.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3921.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3922.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3924.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3927.6635 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3929.6635 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3929.9802 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3932.9802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3933.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3939.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3942.7302 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3944.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3950.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3953.2302 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3954.2302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3955.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3961.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3962.7302 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3963.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3965.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3968.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3969.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3971.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3974.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3975.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3977.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3980.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3981.0469 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3983.0469 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3983.3635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3986.3635 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3987.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3993.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3996.1135 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3997.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4003.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4006.6135 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4007.6135 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4009.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4015.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4016.1135 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4017.1135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4018.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4022.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4023.1135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4024.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 4033.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4037.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4038.1135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4039.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4043.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4043.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4046.6734 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4050.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4054.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4058.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4060.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4061.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4063.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4067.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4071.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4075.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4076.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4078.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4079.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4082.9167 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4084.9167 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4085.2333 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4088.2333 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4088.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4094.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4097.9833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4099.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4105.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4108.4833 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4109.4833 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4110.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4116.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4117.9833 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4118.9833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4120.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4123.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4124.9833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4126.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4129.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4130.9833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4132.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4135.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4136.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4138.3 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4138.6167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4141.6167 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4142.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4148.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4151.3667 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4152.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4158.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4161.8667 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4162.8667 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4164.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4170.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4171.3667 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4172.3667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4173.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4177.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4178.3667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4179.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4183.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4184.3667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4185.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4189.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4189.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4192.9266 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4196.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4200.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4204.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4206.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4207.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4209.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4213.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4217.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4221.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4222.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4224.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4225.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4229.1698 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4231.1698 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4231.4865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4234.4865 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4235.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4241.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4244.2365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4245.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4251.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4254.7365 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4255.7365 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4257.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4263.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4264.2365 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4265.2365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4266.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4270.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4271.2365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4272.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4276.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4277.2365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4278.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4282.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4282.5532 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4284.5532 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4284.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4287.8698 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4288.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4294.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4297.6198 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4299.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4305.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4308.1198 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4309.1198 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4310.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4316.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4317.6198 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4318.6198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4320.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4323.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4324.6198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4326.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4329.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4330.6198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4332.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4335.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4335.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4339.1797 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4343.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4347.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4351.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4352.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4354.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4355.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4359.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4363.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4367.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4369.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4370.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4372.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4375.423 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4377.423 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4377.7397 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4380.7397 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4381.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4387.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4390.4897 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4391.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4397.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4400.9897 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4401.9897 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4403.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4409.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4410.4897 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4411.4897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4412.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4416.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4417.4897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4418.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4422.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4423.4897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4424.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4428.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4428.8063 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4430.8063 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4431.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4434.123 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4434.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4440.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4443.873 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4445.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4451.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4454.373 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4455.373 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4456.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4462.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4463.873 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4464.873 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4466.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4469.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4470.873 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4472.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4475.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4476.873 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4478.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4481.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4482.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4485.4329 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4489.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4493.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4497.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4498.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4500.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4501.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4505.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4509.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4513.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4515.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4516.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4518.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4521.6761 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4523.6761 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4523.9928 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4526.9928 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4530.9928 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4531.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 4540.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4546.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4549.7428 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4551.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4556.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4562.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4565.2428 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4566.2428 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4567.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4573.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4574.7428 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4575.7428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4577.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4580.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4581.7428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4583.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4586.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4587.7428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4589.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4592.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4593.0595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4595.0595 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4595.3761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4598.3761 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4599.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4605.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4608.1261 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4609.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4615.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4618.6261 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4619.6261 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4621.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4627.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4628.1261 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4629.1261 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4636.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4637.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 4659.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4663.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4664.1261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4665.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4669.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4670.1261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4671.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4675.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4675.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4678.686 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4682.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4686.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4690.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4692.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4693.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4695.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4699.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4703.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4707.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4708.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4710.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4711.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4714.9293 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4716.9293 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4717.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4720.246 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4727.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4727.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4731.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4737.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4740.996 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4742.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4748.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4751.496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4752.496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4753.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4759.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4760.996 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4761.996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4763.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 4805.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4808.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4809.996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4811.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4814.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4815.996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4817.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4820.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4821.3126 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4823.3126 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4823.6293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4826.6293 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4827.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4833.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4836.3793 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4837.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4843.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4846.8793 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4847.8793 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4849.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4855.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4856.3793 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4857.3793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4858.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4862.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4863.3793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4864.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4868.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4869.3793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4870.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4874.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4874.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4877.9392 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4881.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4885.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4889.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4891.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4892.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4894.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4898.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4902.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4906.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4907.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4909.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4910.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4914.1824 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4916.1824 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4916.4991 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4919.4991 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4920.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4927.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4933.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4936.2491 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4937.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4938.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4944.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4947.7491 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4948.7491 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4950.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4956.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4957.2491 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4958.2491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4959.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4963.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4964.2491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4965.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4969.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4970.2491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4971.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4975.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4975.5658 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4977.5658 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4977.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4980.8824 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4981.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4987.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4990.6324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4992.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4998.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5001.1324 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5002.1324 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5003.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5009.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5010.6324 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5011.6324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5013.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 5024.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5027.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5028.6324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5030.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5033.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5034.6324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5036.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5038.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5041.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5041.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5045.1924 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5049.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5053.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5057.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5058.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5060.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5061.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5065.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5069.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5073.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5075.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5076.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5078.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5081.4356 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5083.4356 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5083.7523 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5086.7523 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5087.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5093.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5096.5023 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5098.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5104.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5107.0023 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5108.0023 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5109.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5115.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5116.5023 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5117.5023 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5119.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5122.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5123.5023 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5125.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5128.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5129.5023 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5131.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5134.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5134.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5136.8189 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5137.1356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5140.1356 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5140.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5146.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5149.8856 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5151.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5157.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5160.3856 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5161.3856 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5162.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5168.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5169.8856 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5170.8856 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5172.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5175.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5176.8856 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5178.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5181.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5182.8856 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5184.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5187.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5188.2023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5191.4455 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5195.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5199.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5203.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5204.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5206.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5207.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5211.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5215.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5219.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5221.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5222.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5224.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5227.6887 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5229.6887 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5230.0054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5233.0054 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5233.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5239.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5242.7554 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5244.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5250.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5253.2554 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5254.2554 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5255.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5261.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5262.7554 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5263.7554 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5265.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5268.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5269.7554 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5271.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5274.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5275.7554 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5277.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5280.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5281.0721 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5283.0721 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5283.3887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5286.3887 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5287.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5293.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5296.1387 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5297.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5303.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5306.6387 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5307.6387 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5309.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5315.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5316.1387 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5317.1387 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5318.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5322.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5323.1387 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5324.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5328.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5329.1387 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5330.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5334.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5334.4554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5337.6987 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5341.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5345.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5349.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5351.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5352.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5354.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5358.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5362.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5366.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5367.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5369.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5370.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5373.9419 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5375.9419 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5376.2586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5379.2586 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5380.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5386.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5389.0086 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5390.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5396.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5399.5086 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5400.5086 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5402.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5408.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5409.0086 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5410.0086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5411.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5415.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5416.0086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5417.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5421.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5422.0086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5423.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5427.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5427.3252 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5429.3252 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5429.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5432.6419 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5433.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5439.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5442.3919 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5443.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 5447.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5453.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5456.8919 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5457.8919 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5459.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5465.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5466.3919 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5467.3919 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5472.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5473.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5477.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5478.3919 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5479.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5483.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5484.3919 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5485.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5489.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5489.7086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5492.9518 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5496.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5500.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5504.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5506.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5507.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5509.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5513.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5517.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5521.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5522.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5524.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5525.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5529.1951 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5531.1951 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5531.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5534.5117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5535.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5541.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5544.2617 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5545.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5551.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5554.7617 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5555.7617 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5557.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5563.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5564.2617 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5565.2617 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5566.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5570.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5571.2617 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5572.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5576.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5577.2617 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5578.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5582.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5582.5784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5584.5784 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5584.8951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5587.8951 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5588.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5594.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5597.6451 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5599.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5605.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5608.1451 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5609.1451 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5610.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5616.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5617.6451 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5618.6451 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5620.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5623.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5624.6451 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5626.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5629.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5630.6451 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5632.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5635.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5635.9617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5639.205 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5643.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5647.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5651.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5652.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5654.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5655.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5659.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5663.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5667.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5669.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5670.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5672.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5675.4482 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5677.4482 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5677.7649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5680.7649 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5681.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5687.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5690.5149 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5692.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5698.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5701.0149 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5702.0149 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5703.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5709.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5710.5149 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5711.5149 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5713.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5716.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5717.5149 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5719.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5722.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5723.5149 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5725.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5728.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5728.8315 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5730.8315 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5731.1482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5734.1482 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5734.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5740.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5743.8982 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5745.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5751.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5754.3982 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5755.3982 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5756.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5762.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5763.8982 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5764.8982 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5766.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5769.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5770.8982 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5772.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5775.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5776.8982 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5778.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5781.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5782.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5785.4581 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5789.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5793.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5797.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5798.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5800.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5801.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5805.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5809.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5813.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5815.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5816.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5818.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5821.7014 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5823.7014 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5824.018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5827.018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5827.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5833.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5836.768 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5838.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5844.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5847.268 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5848.268 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5849.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5855.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5856.768 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5857.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5859.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5862.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5863.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5865.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5868.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5869.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5871.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5874.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5875.0847 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5877.0847 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5877.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5880.4014 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5881.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5887.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5890.1514 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5891.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5897.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5900.6514 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5901.6514 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 5902.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5904.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5910.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5911.1514 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5912.1514 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5913.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5917.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5918.1514 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5919.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5923.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5924.1514 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5925.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5929.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5929.468 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5932.7113 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5936.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5940.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5944.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5946.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5947.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5949.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5953.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5957.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5961.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5962.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5964.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5965.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5968.9545 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5970.9545 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5971.2712 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5974.2712 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5975.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5981.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5984.0212 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5985.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5991.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5994.5212 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5995.5212 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6001.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6003.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6009.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6010.0212 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6011.0212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6012.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6016.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6017.0212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6018.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6022.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6023.0212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6024.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6028.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6028.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6030.3378 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6030.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6033.6545 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6034.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6040.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6043.4045 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6044.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6050.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6053.9045 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6054.9045 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6056.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6062.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6063.4045 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6064.4045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6065.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6069.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6070.4045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6071.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6075.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6076.4045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6077.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6081.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6081.7212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6084.9644 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6088.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6092.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6096.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6098.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6099.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6101.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6105.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6109.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6113.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6114.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6116.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6117.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6121.2077 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6123.2077 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6123.5243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6126.5243 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6127.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6133.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6136.2743 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6137.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6143.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6146.7743 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6147.7743 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6149.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6155.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6156.2743 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6157.2743 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6158.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6162.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6163.2743 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6164.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6168.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6169.2743 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6170.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6174.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6174.591 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6176.591 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6176.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6179.9077 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6180.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6186.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6189.6577 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6191.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6197.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6200.1577 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6201.1577 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6202.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6208.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6209.6577 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6210.6577 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6212.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6215.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6216.6577 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6218.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6221.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6222.6577 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6224.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6227.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6227.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6231.2176 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6235.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6239.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6243.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6244.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6246.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6247.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6251.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6255.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6259.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6261.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6262.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6264.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6267.4608 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6269.4608 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6269.7775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6272.7775 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6273.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6279.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6282.5275 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6284.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6290.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6293.0275 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6294.0275 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6295.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6301.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6302.5275 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6303.5275 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6305.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6308.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6309.5275 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6311.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6314.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6315.5275 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6317.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6320.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6320.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6322.8442 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6323.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6326.1608 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6326.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6332.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6335.9108 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6337.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6343.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6346.4108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6347.4108 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6348.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6354.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6355.9108 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6356.9108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6358.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6361.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6362.9108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6364.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6367.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6368.9108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6370.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6373.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6374.2275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6377.4707 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6381.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6385.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6389.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6390.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6392.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6393.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6397.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6401.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6405.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6407.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6408.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6410.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6413.714 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6415.714 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6416.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6419.0306 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6419.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6425.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6428.7806 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6430.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6436.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6439.2806 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6440.2806 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6441.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6447.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6448.7806 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6449.7806 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6451.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6454.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6455.7806 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6457.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6460.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6461.7806 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6463.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6466.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6467.0973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6469.0973 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6469.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6472.414 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6473.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6479.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6482.164 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6483.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6489.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6492.664 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6493.664 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6495.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6501.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6502.164 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6503.164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6504.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6508.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6509.164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6510.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6514.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6515.164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6516.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6520.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6520.4806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6523.7239 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6527.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6531.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6535.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6537.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6538.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6540.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6544.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6548.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6552.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6553.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6555.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6556.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6559.9671 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6561.9671 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6562.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6565.2838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6566.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6572.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6575.0338 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6576.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6582.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6585.5338 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6586.5338 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6588.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6594.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6595.0338 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6596.0338 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6597.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6601.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6602.0338 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6603.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 6606.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6610.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6611.0338 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6612.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6616.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6616.3505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6618.3505 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6618.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6621.6671 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6622.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6628.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6631.4171 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6632.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6638.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6641.9171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6642.9171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6644.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6650.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6651.4171 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6652.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6653.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6657.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6658.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6659.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6663.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6664.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6665.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6669.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6669.7338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6672.977 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6676.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6680.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6684.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6686.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6687.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6689.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6693.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6697.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6701.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6702.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6704.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6705.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6709.2203 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6711.2203 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6711.5369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6714.5369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6715.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6721.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6724.2869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6725.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6731.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6734.7869 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6735.7869 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6737.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6743.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6744.2869 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6745.2869 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6746.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6750.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6751.2869 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6752.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6756.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6757.2869 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6758.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6762.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6762.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6764.6036 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6764.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6767.9203 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6768.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6774.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6777.6703 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6779.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6785.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6788.1703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6789.1703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6790.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6796.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6797.6703 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6798.6703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6800.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6803.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6804.6703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6806.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6809.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6810.6703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6812.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6815.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6815.9869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation