## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 29 | 483333.3333 | ACTION | 89 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 109 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 112.2432 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 114.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 114.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 115.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 118.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 119.283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 119.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 120.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 121.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 123.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 124.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 125.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 129.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 130.1029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 132.1029 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 132.4196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 133.4196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 136.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 137.1426 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 137.1459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 138.1459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 139.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 141.6459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 142.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 143.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 147.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 147.9625 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 149.9625 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 150.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 151.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 154.2792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 155.0023 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 155.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 156.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 157.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 159.5055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 160.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 161.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 20 | 333333.3333 | ACTION | 181.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 185.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 185.8222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 187.8222 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 188.1389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 189.1389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 192.1389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 192.8619 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 192.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 193.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 195.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 197.3652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 198.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 199.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 203.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 203.6818 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 206.9251 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 218.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 226.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 238.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 246.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 258.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 266.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 278.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 286.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 290.1683 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 292.1683 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 292.485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 293.485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 296.485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 297.2081 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 297.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 298.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 299.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 301.7113 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 302.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 303.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 307.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 308.028 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 310.028 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 310.3446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 311.3446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 314.3446 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 315.3446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 316.0677 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 316.071 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 317.071 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 318.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 320.571 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 321.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 322.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 326.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 326.8876 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 328.8876 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 329.2043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 330.2043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 333.2043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 333.9274 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 333.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 334.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 336.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 338.4306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 339.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 340.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 344.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 344.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 346.7473 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 347.0639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 348.0639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 351.0639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 351.787 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 351.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 352.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 354.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 356.2903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 357.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 358.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 362.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 362.6069 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 365.8502 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 377.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 385.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 397.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 405.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 417.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 425.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 437.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 445.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 449.0934 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 451.0934 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 451.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 452.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 455.4101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 456.1331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 456.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 457.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 458.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 460.6364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 461.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 462.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 466.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 466.9531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 468.9531 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 469.2697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 470.2697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 473.2697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 473.9928 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 473.996 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 474.996 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 476.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 478.496 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 479.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 480.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 484.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 484.8127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 486.8127 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 487.1294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 488.1294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 491.1294 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 491.8524 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 491.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 492.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 494.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 496.3557 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 497.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 498.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 93 | 1550000 | ACTION | 591.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 595.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 595.6724 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 597.6724 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 597.989 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 598.989 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 601.989 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 602.7121 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 602.7153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 603.7153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 605.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 607.2153 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 608.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 609.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 613.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 613.532 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 616.7752 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 628.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 636.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 648.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 656.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 668.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 676.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 688.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 696.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 700.0185 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 702.0185 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 702.3352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 703.3352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 706.3352 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 707.0582 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 710.0582 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 710.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 711.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 712.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 714.5615 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 715.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 716.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 720.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 720.8781 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 722.8781 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 723.1948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 724.1948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 727.1948 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 727.9179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 727.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 728.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 730.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 732.4211 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 733.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 734.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 738.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 738.7378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 740.7378 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 741.0545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 742.0545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 745.0545 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 745.7775 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 745.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 746.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 748.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 750.2808 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 751.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 752.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 756.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 756.5974 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 758.5974 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 758.9141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 759.9141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 762.9141 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 763.6372 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 763.6404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 764.6404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 766.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 768.1404 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 769.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 770.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 774.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 774.4571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 777.7003 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 789.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 797.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 809.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 817.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 829.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 837.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 849.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 857.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 860.9436 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 862.9436 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 863.2602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 864.2602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 867.2602 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 867.9833 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 867.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 868.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 870.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 872.4866 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 873.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 874.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 878.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 878.8032 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 880.8032 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 881.1199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 882.1199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 885.1199 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 885.843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 885.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 886.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 917.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 919.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 921.3462 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 922.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 923.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 927.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 927.6629 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 929.6629 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 929.9795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 930.9795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 933.9795 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 934.7026 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 934.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 935.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 937.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 939.2059 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 940.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 941.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 945.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 945.5225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 947.5225 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 947.8392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 948.8392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 951.8392 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 952.5622 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 952.5655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 953.5655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 955.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 957.0655 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 958.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 959.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 963.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 963.3822 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 966.6254 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 978.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 986.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 998.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1006.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 37 | 616666.6667 | ACTION | 1043.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1055.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1063.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1075.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 1088.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1096.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1099.8687 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1101.8687 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1102.1853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1103.1853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1106.1853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1106.9084 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1106.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1107.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1109.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1111.4116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1112.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1113.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1117.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1117.7283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1119.7283 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1120.045 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1121.045 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1124.045 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1124.768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1124.7713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1125.7713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1127.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1129.2713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1130.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1131.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1135.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1135.588 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1137.588 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1137.9046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1138.9046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1141.9046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1142.6277 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1142.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1143.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1145.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1147.1309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1148.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1149.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1153.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1153.4476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1155.4476 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1155.7643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1156.7643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1159.7643 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1160.4873 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1160.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1161.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1162.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1164.9906 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1165.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 72 | 1200000 | ACTION | 1237.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1238.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1242.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1243.3072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1246.5505 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1258.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1266.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 1283.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1295.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1303.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1315.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1323.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1335.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1343.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1346.7937 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1348.7937 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1349.1104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1350.1104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1353.1104 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1353.8335 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1353.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1354.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 1359.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1361.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1363.3367 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1364.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1365.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1369.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1369.6534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1371.6534 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1371.9701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1372.9701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1375.9701 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1376.6931 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1376.6964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1377.6964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1379.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1381.1964 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1382.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1383.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1387.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1387.513 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1389.513 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1389.8297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1390.8297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1393.8297 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1394.5528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1394.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1395.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1397.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1399.056 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1400.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1401.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1405.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1405.3727 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1407.3727 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1407.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1408.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1411.6893 | MonopileInstallation
| WTIV | Delay | 68 | 1133333.3333 | ACTION | 1479.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1480.4124 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1480.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1481.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1482.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1484.9157 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1485.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1486.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 1492.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1496.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1497.2323 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1500.4756 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1512.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1520.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1532.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1540.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1552.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1560.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1572.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1580.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1583.7188 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1585.7188 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1586.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1587.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1590.0355 | MonopileInstallation
| WTIV | Delay | 26 | 433333.3333 | ACTION | 1616.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1616.7585 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1616.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1617.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1619.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1621.2618 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1622.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1623.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1627.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1627.5785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1629.5785 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1629.8951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1630.8951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1633.8951 | MonopileInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 1664.8951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1665.6182 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1665.6214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1666.6214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1668.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1670.1214 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1671.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1672.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1676.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1676.4381 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1678.4381 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1678.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1679.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1682.7548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1683.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1683.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1684.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1685.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1687.9811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1688.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1689.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1693.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1694.2978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1696.2978 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1696.6144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1697.6144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1700.6144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1701.3375 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1701.3407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1702.3407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1703.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1705.8407 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1706.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1707.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1711.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1712.1574 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1715.4007 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1727.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1735.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1747.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 32 | 533333.3333 | ACTION | 1779.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1787.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1799.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1807.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1819.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1827.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1830.6439 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1832.6439 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1832.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1833.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1836.9606 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1837.6836 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1837.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1838.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1840.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1842.1869 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1843.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1844.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1848.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1848.5035 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1850.5035 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1850.8202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1851.8202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1854.8202 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1855.5433 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1855.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1856.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1858.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1860.0465 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1861.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1862.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1866.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1866.3632 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1868.3632 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1868.6799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1869.6799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1872.6799 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1873.4029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1873.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1874.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1875.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1877.9062 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1878.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1879.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1883.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1884.2228 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1886.2228 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1886.5395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1887.5395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1890.5395 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1891.2626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1891.2658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1892.2658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1893.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1895.7658 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1896.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1897.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1901.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1902.0825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1905.3257 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1917.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1925.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1937.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1945.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1957.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1965.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1977.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1985.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1988.569 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1990.569 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1990.8856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1991.8856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1994.8856 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1995.6087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1995.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1996.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1998.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2000.112 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2001.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2002.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2006.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2006.4286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2008.4286 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2008.7453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2009.7453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2012.7453 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2013.4684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2013.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2014.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2015.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2017.9716 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2018.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2019.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2023.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2024.2883 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2026.2883 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2026.6049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2027.6049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2030.6049 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2031.328 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2031.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2032.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2033.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2035.8313 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2036.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2037.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2041.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2042.1479 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2044.1479 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2044.4646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2045.4646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2048.4646 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2049.1877 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2049.1909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2050.1909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2051.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2053.6909 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2054.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2055.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2059.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2060.0076 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2063.2508 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2075.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2083.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2095.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2103.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2115.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 18 | 300000 | ACTION | 2133.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2141.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2153.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2161.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2164.4941 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2166.4941 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2166.8107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2167.8107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2170.8107 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2171.5338 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2171.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2172.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2174.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2176.037 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2177.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2178.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2182.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2182.3537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2184.3537 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2184.6704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2185.6704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2188.6704 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2189.3934 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2189.3967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2190.3967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2191.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2193.8967 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2194.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2195.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2199.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2200.2134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2202.2134 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2202.53 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2203.53 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2206.53 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2207.2531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2207.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2208.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2209.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2211.7563 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2212.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2213.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2217.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2218.073 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2220.073 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2220.3897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2221.3897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2224.3897 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2225.1127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2225.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2226.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2227.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2229.616 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2230.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2231.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 2240.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2244.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2244.9327 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2248.1759 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2260.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2268.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2280.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2288.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 47 | 783333.3333 | ACTION | 2335.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2347.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2355.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2367.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2375.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3 | 50000 | ACTION | 2378.1759 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2382.1759 | MonopileInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 2382.4191 | MonopileInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 2396.4191 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2398.4191 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2398.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2399.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2403.7358 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2406.7358 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2408.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2409.4589 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2409.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2410.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2411.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2413.9621 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2414.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2415.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2419.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2420.2788 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2422.2788 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2422.5955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2423.5955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2426.5955 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2427.3185 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2427.3218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2428.3218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2429.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2431.8218 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2432.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2433.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2437.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2438.1384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2440.1384 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2440.4551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2441.4551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2444.4551 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2445.1782 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2445.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2446.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2447.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2449.6814 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2450.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2451.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2455.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2455.9981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2457.9981 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2458.3148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2459.3148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2462.3148 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2463.0378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2463.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2464.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2465.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2467.5411 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2468.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2469.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2473.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2473.8577 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2477.101 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2489.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2497.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2509.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2517.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2520.3442 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2522.3442 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2522.6609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2523.6609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2526.6609 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2527.384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2527.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2528.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2529.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2531.8872 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2532.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2534.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2535.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2539.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2540.2039 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2542.2039 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2542.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2543.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2546.5205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2547.2436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2547.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2548.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2549.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2551.7469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2552.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2553.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2557.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2558.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 2558.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2562.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2566.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2570.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2571.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2573.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2574.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2578.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2582.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2586.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2588.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 2594.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2595.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2597.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2601.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2605.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2609.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2610.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2612.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2613.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2617.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2621.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2625.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2627.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2628.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2630.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2634.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2638.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2642.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2643.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2645.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2646.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2649.8068 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2651.8068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2652.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2655.1234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2655.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2661.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2664.8734 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2666.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2672.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2675.3734 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2676.3734 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2677.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 2702.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2708.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2709.8734 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2710.8734 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2712.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2714.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2717.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2718.8734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2720.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2723.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2724.8734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2726.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2729.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2730.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2732.1901 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2732.5068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2735.5068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2736.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2742.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2745.2568 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2746.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2752.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2755.7568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2756.7568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2758.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2764.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2765.2568 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2766.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2767.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2771.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2772.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2773.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 16 | 266666.6667 | ACTION | 2789.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2793.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2794.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2795.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2799.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2799.5734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2801.5734 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2801.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2804.8901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2805.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2811.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2814.6401 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2816.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2822.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2825.1401 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2826.1401 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2827.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2833.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2834.6401 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2835.6401 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2839.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2841.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2844.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2845.6401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2847.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2850.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2851.6401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2853.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2856.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2856.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2858.9568 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2859.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2862.2734 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2863.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2869.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2872.0234 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2873.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 2904.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2910.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2913.5234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2914.5234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2916.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2922.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2923.0234 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2924.0234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2925.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2929.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2930.0234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2931.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2935.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2936.0234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2937.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 2940.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2944.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2944.3401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2946.3401 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2946.6568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2949.6568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 2950.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2956.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2959.4068 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 2960.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2966.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2969.9068 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2970.9068 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2972.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2978.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2979.4068 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2980.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2981.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2985.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2986.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2987.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2991.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2992.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2993.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 29 | 483333.3333 | ACTION | 3022.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3026.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3026.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3029.9667 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3033.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3037.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3041.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3043.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3044.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3046.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3050.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 30 | 500000 | ACTION | 3080.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3084.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3088.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3089.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3091.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3092.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3096.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3100.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3104.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3106.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3107.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3109.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3113.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3117.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3121.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3122.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3124.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3125.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3129.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3133.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3137.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3139.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3140.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3142.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3145.7099 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3147.7099 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3148.0266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3151.0266 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3151.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3157.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3160.7766 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3162.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3168.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3171.2766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3172.2766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3173.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3179.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3180.7766 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3181.7766 | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 3203.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3205.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3208.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3209.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3211.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3214.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3215.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3217.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3220.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3221.0933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3223.0933 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3223.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3226.4099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3227.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3233.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3236.1599 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3237.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3243.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3246.6599 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3247.6599 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3249.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3255.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3256.1599 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3257.1599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3258.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3262.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3263.1599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3264.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3268.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3269.1599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3270.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3274.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3274.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3276.4766 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3276.7933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3279.7933 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3280.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3286.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3289.5433 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3291.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3297.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3300.0433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3301.0433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3302.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3308.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3309.5433 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3310.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3312.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3315.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3316.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3318.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3321.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3322.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3324.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3327.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3327.8599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3329.8599 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3330.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3333.1766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3333.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3339.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3342.9266 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3344.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3350.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3353.4266 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3354.4266 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3355.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3361.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3362.9266 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3363.9266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3365.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3368.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3369.9266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3371.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3374.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3375.9266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3377.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3380.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3381.2433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3383.2433 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3383.5599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3386.5599 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3387.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3393.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3396.3099 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3397.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3403.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3406.8099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3407.8099 | TurbineInstallation
| WTIV | Delay | 60 | 1000000 | ACTION | 3467.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3469.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 27 | 450000 | ACTION | 3496.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3502.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3503.3099 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3504.3099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3505.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3509.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3510.3099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3511.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3515.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3516.3099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3517.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3521.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3521.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3524.8698 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3528.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3532.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3536.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3538.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3539.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3541.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3545.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3549.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3553.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3554.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3556.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3557.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3561.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3565.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3569.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3571.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3572.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3574.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3578.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3582.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3586.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3587.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3589.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3590.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3594.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3598.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3602.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3604.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3605.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3607.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3610.6131 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3612.6131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3612.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3615.9297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3616.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3622.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3625.6797 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3627.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3633.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3636.1797 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3637.1797 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3638.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3644.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3645.6797 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3646.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3648.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3658.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3661.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3662.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3664.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3667.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3668.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3670.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 29 | 483333.3333 | ACTION | 3699.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3702.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3702.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3704.9964 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3705.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3708.3131 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3709.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3715.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3718.0631 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 3727.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3728.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 3750.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3756.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3759.5631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3760.5631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3762.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3768.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3769.0631 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3770.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3771.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3775.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3776.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3777.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3781.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3782.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3783.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3787.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3787.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3789.3797 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3789.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3792.6964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3793.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 68 | 1133333.3333 | ACTION | 3861.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3867.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3870.4464 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3871.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3877.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3880.9464 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3881.9464 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3883.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3889.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3890.4464 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3891.4464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3892.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3896.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3897.4464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3898.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3902.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3903.4464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3904.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3908.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3908.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3910.7631 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3911.0797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3914.0797 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3914.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3920.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3923.8297 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3925.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3931.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3934.3297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3935.3297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3936.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3942.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3943.8297 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3944.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3946.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3949.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3950.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3952.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3955.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3956.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3958.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3961.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3962.1464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3964.1464 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3964.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3967.4631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 3968.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3974.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3977.2131 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 3978.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3984.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3987.7131 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3988.7131 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3990.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3996.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3997.2131 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3998.2131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3999.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4003.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4004.2131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4005.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4009.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4010.2131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4011.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4015.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4015.5297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4018.773 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4022.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4026.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4030.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4032.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4033.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4035.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4039.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4043.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4047.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4048.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4050.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4051.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4055.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4059.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4063.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4065.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4066.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4068.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4072.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4076.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4080.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4081.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4083.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4084.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4088.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4092.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4096.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4098.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4099.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4101.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4104.5162 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4106.5162 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4106.8329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4109.8329 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4110.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4116.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4119.5829 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4121.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4127.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4130.0829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4131.0829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4132.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4138.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4139.5829 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4140.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4142.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4145.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4146.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4148.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4151.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4152.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4154.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4157.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4157.8996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4159.8996 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4160.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4163.2162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4163.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4169.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4172.9662 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4174.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4180.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4183.4662 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4184.4662 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4185.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4191.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4192.9662 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4193.9662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4195.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4198.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4199.9662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4201.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4204.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4205.9662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4207.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4210.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4211.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4213.2829 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4213.5996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4216.5996 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4217.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4223.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4226.3496 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4227.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4233.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4236.8496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4237.8496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4239.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4245.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4246.3496 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4247.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4248.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4252.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4253.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4254.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4258.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4259.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4260.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4264.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4264.6662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4266.6662 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4266.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4269.9829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4270.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4276.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4279.7329 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4281.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4287.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4290.2329 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4291.2329 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4292.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4298.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4299.7329 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4300.7329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4302.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4305.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4306.7329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4308.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4311.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4312.7329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4314.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4317.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4318.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4320.0496 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4320.3662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4323.3662 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4324.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4330.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4333.1162 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4334.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4340.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4343.6162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4344.6162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4346.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4352.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4353.1162 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4354.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4355.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4359.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4360.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4361.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4365.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4366.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4367.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4371.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4371.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4374.6761 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4378.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4382.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4386.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4388.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4389.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4391.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4395.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4399.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4403.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4404.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4406.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4407.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4411.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4415.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4419.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4421.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4422.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4424.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4428.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4432.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4436.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4437.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4439.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4440.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4444.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4448.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4452.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4454.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4455.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4457.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4460.4194 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4462.4194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4462.736 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4465.736 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4466.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4472.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4475.486 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4476.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4482.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4485.986 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4486.986 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4488.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4494.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4495.486 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4496.486 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4497.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4501.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4502.486 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4503.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4507.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4508.486 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4509.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4513.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4513.8027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4515.8027 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4516.1194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4519.1194 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4519.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4525.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4528.8694 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4530.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4532.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4539.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4545.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4548.3694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4549.3694 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4551.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4552.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4555.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4561.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4562.8694 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4563.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4565.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4568.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4569.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4571.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4574.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4575.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4577.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4580.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4581.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4583.186 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4583.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4586.5027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4587.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4593.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4596.2527 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4597.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4603.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4606.7527 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4607.7527 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4609.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4615.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4616.2527 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4617.2527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4618.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4622.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4623.2527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4624.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4628.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4629.2527 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4635.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4636.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 4658.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4662.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4662.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4664.5694 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4664.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4667.886 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4668.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4674.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4677.636 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4679.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4685.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4691.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4694.136 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4695.136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4696.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4702.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4703.636 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4704.636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4706.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4709.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4710.636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4712.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 19 | 316666.6667 | ACTION | 4731.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4734.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4735.636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4737.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4740.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4740.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4742.9527 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4743.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4746.2694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4747.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4753.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4756.0194 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4757.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4763.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4766.5194 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4767.5194 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4771.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4773.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 32 | 533333.3333 | ACTION | 4805.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4811.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4812.0194 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4813.0194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4814.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4818.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4819.0194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4820.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4824.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4825.0194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4826.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4830.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4830.336 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4833.5793 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4837.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4841.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4845.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4847.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4848.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4850.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4854.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4858.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4862.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4863.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4865.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4866.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4870.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4874.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4878.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4880.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4881.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4883.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4887.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4891.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4895.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4896.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4898.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4899.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4903.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4907.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4911.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4913.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4914.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4916.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4919.3225 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4921.3225 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4921.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4924.6392 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4926.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4927.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4933.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4936.3892 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4937.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4943.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4946.8892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4947.8892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4949.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4955.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4956.3892 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4957.3892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4958.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4962.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4963.3892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4964.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4968.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4969.3892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4970.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4974.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4974.7059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4976.7059 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4977.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4980.0225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 4980.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4986.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4989.7725 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 4991.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4997.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5000.2725 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5001.2725 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5002.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5008.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5009.7725 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5010.7725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5012.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 5023.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5026.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5027.7725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5029.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5032.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5033.7725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5035.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5037.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5040.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5041.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5043.0892 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5043.4059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5046.4059 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5047.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5053.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5056.1559 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5057.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5063.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5066.6559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5067.6559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5069.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5075.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5076.1559 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5077.1559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5078.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5082.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5083.1559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5084.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5088.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5089.1559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5090.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5094.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5094.4725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5096.4725 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5096.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5099.7892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5100.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5106.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5109.5392 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5111.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5117.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5120.0392 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5121.0392 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5122.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5128.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5129.5392 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5130.5392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5132.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5135.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5136.5392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5138.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5141.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5142.5392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5144.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5147.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5147.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5149.8559 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5150.1725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5153.1725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5153.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5159.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5162.9225 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5164.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5170.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5173.4225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5174.4225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5175.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5181.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5182.9225 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5183.9225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5185.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5188.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5189.9225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5191.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5194.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5195.9225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5197.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5200.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5201.2392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5204.4824 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5208.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5212.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5216.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5217.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5219.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5220.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5224.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5228.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5232.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5234.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5235.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5237.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5241.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5245.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5249.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5250.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5252.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5253.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5257.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5261.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5265.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5267.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5268.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5270.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5274.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5278.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5282.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5283.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5285.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5286.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5290.2257 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5292.2257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5292.5424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5295.5424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5296.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5302.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5305.2924 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5306.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5312.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5315.7924 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5316.7924 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5318.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5324.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5325.2924 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5326.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5327.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5331.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5332.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5333.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5337.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5338.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5339.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5343.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5343.609 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5345.609 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5345.9257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5348.9257 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5350.9257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5351.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5357.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5360.6757 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5362.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5368.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5371.1757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5372.1757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5373.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5379.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5380.6757 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5381.6757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5383.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5386.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5387.6757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5389.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5392.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5393.6757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5395.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5398.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5398.9924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5400.9924 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5401.309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5404.309 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5405.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5411.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5414.059 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5415.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5421.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5424.559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5425.559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5427.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5433.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5434.059 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5435.059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5436.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5440.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5441.059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5442.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 5446.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5450.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5451.059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5452.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5456.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5456.3757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5458.3757 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5458.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5461.6924 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5462.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 5471.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5477.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5480.4424 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5481.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5487.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5490.9424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5491.9424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5493.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5499.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5500.4424 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5501.4424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5502.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5506.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5507.4424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5508.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5512.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5513.4424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5514.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5518.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5518.759 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5520.759 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5521.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5524.0757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5524.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5530.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5533.8257 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5535.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5541.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5544.3257 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5545.3257 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5546.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5552.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5553.8257 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5554.8257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5556.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5559.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5560.8257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5562.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5565.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5566.8257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5568.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5571.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5572.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5575.3856 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5579.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5583.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5587.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5588.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5590.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5591.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5595.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5599.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5603.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5605.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5606.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5608.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5612.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5616.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5620.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5621.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5623.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5624.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5628.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5632.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5636.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5638.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5639.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5641.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5645.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5649.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5653.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5654.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5656.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5657.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5661.1288 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5663.1288 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5663.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5666.4455 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5667.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5673.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5676.1955 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5677.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5683.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5686.6955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5687.6955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5689.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5695.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5696.1955 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5697.1955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5698.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5702.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5703.1955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5704.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5708.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5709.1955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5710.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5714.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5714.5122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5716.5122 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5716.8288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5719.8288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5720.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5726.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5729.5788 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5731.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5737.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5740.0788 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5741.0788 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5742.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5748.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5749.5788 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5750.5788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5752.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5755.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5756.5788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5758.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5761.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5762.5788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5764.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5767.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5767.8955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5769.8955 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5770.2122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5773.2122 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5773.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5779.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5782.9622 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5784.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5790.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5793.4622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5794.4622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5795.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5801.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5802.9622 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5803.9622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5805.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5808.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5809.9622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5811.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5814.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5815.9622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5817.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5820.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5821.2788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5823.2788 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5823.5955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5826.5955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5827.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5833.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5836.3455 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5837.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5843.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5846.8455 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5847.8455 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5849.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5855.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5856.3455 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5857.3455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5858.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5862.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5863.3455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5864.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5868.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5869.3455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5870.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5874.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5874.6622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5876.6622 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5876.9788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5879.9788 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 5880.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5886.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5889.7288 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 5891.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5897.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5900.2288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5901.2288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5902.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5908.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5909.7288 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5910.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5912.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5915.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5916.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5918.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5921.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5922.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5924.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5927.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5928.0455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5931.2887 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5935.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5939.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5943.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5944.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5946.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5947.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5951.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5955.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5959.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5961.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5962.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5964.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5968.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5972.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5976.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5977.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5979.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5980.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5984.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5988.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5992.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5994.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5995.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5997.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6001.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6005.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6009.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6010.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6012.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6013.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6017.032 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6019.032 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6019.3487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6022.3487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6023.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6029.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6032.0987 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6033.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6039.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6042.5987 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6043.5987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6045.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6051.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6052.0987 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6053.0987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6054.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6058.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6059.0987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6060.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6064.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6065.0987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6066.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6070.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6070.4153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6072.4153 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6072.732 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6075.732 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6076.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6082.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6085.482 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6086.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6092.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6095.982 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6096.982 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6098.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6104.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6105.482 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6106.482 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6107.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6111.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6112.482 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6113.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6117.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6118.482 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6119.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6123.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6123.7987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6125.7987 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6126.1153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6129.1153 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6129.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6135.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6138.8653 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6140.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 6144.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6150.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6153.3653 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6154.3653 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6155.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6161.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6162.8653 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6163.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6165.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6168.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6169.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6171.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6174.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6175.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6177.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6180.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6181.182 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6183.182 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6183.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6186.4987 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6187.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6193.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6196.2487 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6197.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6203.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6206.7487 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6207.7487 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6209.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6215.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6216.2487 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6217.2487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6218.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6222.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6223.2487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6224.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6228.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6229.2487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6230.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6234.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6234.5653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6236.5653 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6236.882 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6239.882 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6240.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6246.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6249.632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6251.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6257.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6260.132 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6261.132 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6262.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6268.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6269.632 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6270.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6272.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6275.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6276.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6278.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6281.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6282.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6284.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6287.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6287.9487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6291.1919 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6295.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6299.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6303.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6304.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6306.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6307.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6311.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6315.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6319.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6321.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6322.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6324.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6328.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6332.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6336.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6337.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6339.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6340.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6344.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6348.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6352.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6354.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6355.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6357.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6361.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6365.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6369.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6370.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6372.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6373.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6376.9351 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6378.9351 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6379.2518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6382.2518 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6383.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6389.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6392.0018 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6393.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6399.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6402.5018 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6403.5018 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6405.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6411.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6412.0018 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6413.0018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6414.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6418.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6419.0018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6420.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6424.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6425.0018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6426.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6430.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6430.3185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6432.3185 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6432.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6435.6351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6436.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6442.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6445.3851 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6446.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6452.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6455.8851 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6456.8851 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6458.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6464.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6465.3851 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6466.3851 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6467.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6471.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6472.3851 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6473.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6477.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6478.3851 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6479.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6483.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6483.7018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6485.7018 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6486.0185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6489.0185 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6489.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6495.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6498.7685 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6500.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6506.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6509.2685 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6510.2685 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6511.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6517.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6518.7685 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6519.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6521.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6524.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6525.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6527.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6530.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6531.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6533.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6536.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6537.0851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6539.0851 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6539.4018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6542.4018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6543.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6549.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6552.1518 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6553.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6559.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6562.6518 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6563.6518 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6565.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6571.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6572.1518 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6573.1518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6574.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6578.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6579.1518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6580.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6584.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6585.1518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6586.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6590.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6590.4685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6592.4685 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6592.7851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6595.7851 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 12500 | ACTION | 6596.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6602.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6605.5351 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 25000 | ACTION | 6607.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6613.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6616.0351 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6617.0351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6618.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6624.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6625.5351 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6626.5351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6628.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6631.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6632.5351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6634.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6637.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6638.5351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6640.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6643.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6643.8518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation