## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 28 | 291666.6667 | ACTION | 68 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 69 | MonopileInstallation
| WTIV | Transit | 3 | 31250 | ACTION | 72 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 73 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 74 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 75 | MonopileInstallation
| WTIV | Transit | 11 | 114583.3333 | ACTION | 86 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 89 | MonopileInstallation
| WTIV | Transit | 0.24324 | 2533.7838 | ACTION | 89.2432 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 91.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 91.5599 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 92.5599 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 95.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 96.283 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 96.2862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 97.2862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 98.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 100.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 101.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 102.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 106.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 107.1029 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 109.1029 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 109.4196 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 110.4196 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 113.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 114.1426 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 114.1459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 115.1459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 116.6459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 118.6459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 119.6459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 120.6459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 124.6459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 124.9625 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43 | 447916.6667 | ACTION | 167.9625 | MonopileInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 179.9625 | MonopileInstallation
| WTIV | Transit | 0.24324 | 2533.7838 | ACTION | 180.2058 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 181.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 193.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 201.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 213.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 221.2058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 264.449 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 266.449 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 266.7657 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 267.7657 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 270.7657 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 271.4888 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 271.492 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 272.492 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 273.992 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 275.992 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 276.992 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 277.992 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 281.992 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 282.3087 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 284.3087 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 284.6253 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 285.6253 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 288.6253 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 289.3484 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 289.3517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 290.3517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 291.8517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 293.8517 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 294.8517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 295.8517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 299.8517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 300.1683 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 343.4116 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 355.4116 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 363.4116 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 375.4116 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 383.4116 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 426.6548 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 428.6548 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 428.9715 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 429.9715 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 432.9715 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 433.6945 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 433.6978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 434.6978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 436.1978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 438.1978 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 439.1978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 440.1978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 444.1978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 444.5145 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 446.5145 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 446.8311 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 447.8311 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 450.8311 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 451.5542 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 451.5574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 452.5574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 454.0574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 456.0574 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 457.0574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 458.0574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 462.0574 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 462.3741 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 505.6174 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 517.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 74 | 770833.3333 | ACTION | 591.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 599.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 611.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 619.6174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 662.8606 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 664.8606 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 665.1773 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 666.1773 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 669.1773 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 669.9003 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 669.9036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 670.9036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 672.4036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 674.4036 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 675.4036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 676.4036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 680.4036 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 680.7202 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 682.7202 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 683.0369 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 684.0369 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 687.0369 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 687.76 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 687.7632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 688.7632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 690.2632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 692.2632 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 693.2632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 694.2632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 698.2632 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 698.5799 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 741.8231 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 753.8231 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 761.8231 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 773.8231 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 781.8231 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 825.0664 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 827.0664 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 827.383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 828.383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 831.383 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 832.1061 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 832.1094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 833.1094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 834.6094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 836.6094 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 837.6094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 838.6094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 842.6094 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 842.926 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 844.926 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 845.2427 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 846.2427 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 849.2427 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 849.9658 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 849.969 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 850.969 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 852.469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 854.469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 855.469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 856.469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 860.469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 860.7857 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 29 | 302083.3333 | ACTION | 889.7857 | MonopileInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 913.7857 | MonopileInstallation
| WTIV | Transit | 14.2432 | 148367.1171 | ACTION | 928.0289 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 940.0289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 948.0289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 960.0289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 968.0289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1011.2722 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1013.2722 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1013.5888 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1014.5888 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 29 | 302083.3333 | ACTION | 1043.5888 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1046.5888 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1047.3119 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1047.3151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1048.3151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1049.8151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1051.8151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1052.8151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1053.8151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1057.8151 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1058.1318 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1060.1318 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1060.4485 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1061.4485 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1064.4485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1065.1715 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1065.1748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1066.1748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1067.6748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1069.6748 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1070.6748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1071.6748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1075.6748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1075.9915 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 5 | 52083.3333 | ACTION | 1080.9915 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1081.9915 | MonopileInstallation
| WTIV | Transit | 4 | 41666.6667 | ACTION | 1085.9915 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 1088.9915 | MonopileInstallation
| WTIV | Transit | 34.2432 | 356700.4505 | ACTION | 1123.2347 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1135.2347 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1143.2347 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1155.2347 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1163.2347 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 3 | 31250 | ACTION | 1166.2347 | MonopileInstallation
| WTIV | Delay | 66 | 687500 | ACTION | 1232.2347 | MonopileInstallation
| WTIV | Transit | 40 | 416666.6667 | ACTION | 1272.2347 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 1281.2347 | MonopileInstallation
| WTIV | Transit | 0.24324 | 2533.7838 | ACTION | 1281.4779 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 1283.4779 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1285.4779 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1285.7946 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1286.7946 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1289.7946 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1290.5177 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1290.5209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1291.5209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1293.0209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1295.0209 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1296.0209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1297.0209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1301.0209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1301.3376 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1303.3376 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1303.6543 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1304.6543 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1307.6543 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1308.3773 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1308.3806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1309.3806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1310.8806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1312.8806 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1313.8806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1314.8806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1318.8806 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1319.1972 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1362.4405 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1374.4405 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1382.4405 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1394.4405 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1402.4405 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 12 | 125000 | ACTION | 1414.4405 | MonopileInstallation
| WTIV | Delay | 20 | 208333.3333 | ACTION | 1434.4405 | MonopileInstallation
| WTIV | Transit | 12 | 125000 | ACTION | 1446.4405 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1447.4405 | MonopileInstallation
| WTIV | Transit | 19.2432 | 200450.4505 | ACTION | 1466.6837 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1468.6837 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1469.0004 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1470.0004 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1473.0004 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 1479.0004 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1479.7235 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1479.7267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1480.7267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1482.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1484.2267 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1485.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1486.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 1492.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1496.2267 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1496.5434 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1498.5434 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1498.86 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1499.86 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1502.86 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 1505.86 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1506.5831 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1506.5864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1507.5864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1509.0864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1511.0864 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1512.0864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1513.0864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1517.0864 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1517.403 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1560.6463 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1572.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1580.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1592.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 1616.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1624.6463 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 10 | 104166.6667 | ACTION | 1634.6463 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1635.6463 | MonopileInstallation
| WTIV | Transit | 3 | 31250 | ACTION | 1638.6463 | MonopileInstallation
| WTIV | Delay | 22 | 229166.6667 | ACTION | 1660.6463 | MonopileInstallation
| WTIV | Transit | 30.2432 | 315033.7838 | ACTION | 1690.8895 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1692.8895 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1693.2062 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1694.2062 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1697.2062 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1697.9292 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1697.9325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1698.9325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1700.4325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1702.4325 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1703.4325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1704.4325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1708.4325 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1708.7492 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1710.7492 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1711.0658 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1712.0658 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1715.0658 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1715.7889 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1715.7921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1716.7921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1718.2921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1720.2921 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1721.2921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1722.2921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1726.2921 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1726.6088 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 28 | 291666.6667 | ACTION | 1754.6088 | MonopileInstallation
| WTIV | Delay | 25 | 260416.6667 | ACTION | 1779.6088 | MonopileInstallation
| WTIV | Transit | 15.2432 | 158783.7838 | ACTION | 1794.8521 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1806.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1814.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1826.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1834.8521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1878.0953 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1880.0953 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1880.412 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1881.412 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1884.412 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1885.135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1885.1383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1886.1383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1887.6383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1889.6383 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1890.6383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1891.6383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1895.6383 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1895.955 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1897.955 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1898.2716 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1899.2716 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1902.2716 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1902.9947 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1902.9979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1903.9979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1905.4979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1907.4979 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1908.4979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1909.4979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1913.4979 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1913.8146 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1957.0578 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1969.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1977.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1989.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1997.0578 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2040.3011 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2042.3011 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2042.6178 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2043.6178 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2046.6178 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2047.3408 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2047.3441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2048.3441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2049.8441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2051.8441 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2052.8441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2053.8441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2057.8441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2058.1607 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2060.1607 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2060.4774 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2061.4774 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2064.4774 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2065.2005 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2065.2037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2066.2037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2067.7037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2069.7037 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2070.7037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2071.7037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2075.7037 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2076.0204 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 42 | 437500 | ACTION | 2118.0204 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2120.0204 | MonopileInstallation
| WTIV | Transit | 1.2432 | 12950.4505 | ACTION | 2121.2636 | MonopileInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 2133.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2145.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2153.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2165.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2173.2636 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2216.5069 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2218.5069 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2218.8235 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2219.8235 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2222.8235 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2223.5466 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2223.5499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2224.5499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2226.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2228.0499 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2229.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2230.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 2240.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2244.0499 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2244.3665 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2246.3665 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2246.6832 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2247.6832 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2250.6832 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2251.4063 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2251.4095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2252.4095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2253.9095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2255.9095 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2256.9095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2257.9095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2261.9095 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2262.2262 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 32 | 333333.3333 | ACTION | 2294.2262 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 2304.2262 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 2305.2262 | MonopileInstallation
| WTIV | Delay | 30 | 312500 | ACTION | 2335.2262 | MonopileInstallation
| WTIV | Transit | 10.2432 | 106700.4505 | ACTION | 2345.4694 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2357.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2365.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2377.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 26 | 270833.3333 | ACTION | 2403.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2411.4694 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2454.7127 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2456.7127 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2457.0293 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2458.0293 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2461.0293 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2461.7524 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2461.7556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2462.7556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2464.2556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2466.2556 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2467.2556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2468.2556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2472.2556 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2472.5723 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2474.5723 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2474.889 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2475.889 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2478.889 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2479.612 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2479.6153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2480.6153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2482.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2484.1153 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2485.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2486.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2490.1153 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2490.432 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2533.6752 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2545.6752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2553.6752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2565.6752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2573.6752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 16 | 166666.6667 | ACTION | 2589.6752 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 2590.6752 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 2591.6752 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 2592.6752 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 2593.6752 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 2594.6752 | MonopileInstallation
| WTIV | Transit | 25.2432 | 262950.4505 | ACTION | 2619.9184 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2621.9184 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2622.2351 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2623.2351 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2626.2351 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2626.9582 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2626.9614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2627.9614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2629.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2631.4614 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2632.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2633.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2637.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2637.7781 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2639.7781 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2640.0948 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2641.0948 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2644.0948 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2644.8178 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2644.8211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2645.8211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2647.3211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2649.3211 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2650.3211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2651.3211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2655.3211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2655.6377 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 30 | 312500 | ACTION | 2685.6377 | MonopileInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 2699.6377 | MonopileInstallation
| WTIV | Transit | 13.2432 | 137950.4505 | ACTION | 2712.881 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2724.881 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2732.881 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2744.881 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2752.881 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2796.1242 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2798.1242 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2798.4409 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2799.4409 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2802.4409 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2803.164 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2803.1672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2804.1672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2805.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2807.6672 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2808.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2809.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2813.6672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2813.9839 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2815.9839 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2816.3005 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2817.3005 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2820.3005 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2821.0236 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2821.0269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2822.0269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2823.5269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2825.5269 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2826.5269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2827.5269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2831.5269 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2831.8435 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 6 | 62500 | ACTION | 2837.8435 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2839.8435 | MonopileInstallation
| WTIV | Transit | 37.2432 | 387950.4505 | ACTION | 2877.0868 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2889.0868 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2897.0868 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2909.0868 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2917.0868 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2960.33 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2962.33 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2962.6467 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2963.6467 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2966.6467 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2967.3697 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2967.373 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2968.373 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2969.873 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2971.873 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2972.873 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2973.873 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2977.873 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2978.1897 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2980.1897 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2980.5063 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2981.5063 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2984.5063 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2985.2294 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2985.2326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2986.2326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2987.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2989.7326 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2990.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2991.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2995.7326 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2996.0493 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 12 | 125000 | ACTION | 3008.0493 | MonopileInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 3023.0493 | MonopileInstallation
| WTIV | Transit | 29 | 302083.3333 | ACTION | 3052.0493 | MonopileInstallation
| WTIV | Delay | 29 | 302083.3333 | ACTION | 3081.0493 | MonopileInstallation
| WTIV | Transit | 2.2432 | 23367.1171 | ACTION | 3083.2925 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3095.2925 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3103.2925 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3115.2925 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3123.2925 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3166.5358 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3168.5358 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3168.8525 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3169.8525 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3172.8525 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3173.5755 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3173.5788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3174.5788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3176.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3178.0788 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3179.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3180.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 3204.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3208.0788 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3208.3954 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3210.3954 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3210.7121 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3211.7121 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3214.7121 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3215.4352 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3215.4384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3216.4384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3217.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3219.9384 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3220.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3221.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 3224.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3228.9384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3229.2551 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3272.4983 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3284.4983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3292.4983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3304.4983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3312.4983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3355.7416 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3357.7416 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3358.0582 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3359.0582 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3362.0582 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3362.7813 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3362.7846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3363.7846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3365.2846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3367.2846 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3368.2846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3369.2846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3373.2846 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3373.6012 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3375.6012 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3375.9179 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3376.9179 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3379.9179 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3380.641 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3380.6442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3381.6442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3383.1442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3385.1442 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3386.1442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3387.1442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3391.1442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3391.4609 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 31 | 322916.6667 | ACTION | 3422.4609 | MonopileInstallation
| WTIV | Delay | 44 | 458333.3333 | ACTION | 3466.4609 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3467.4609 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3468.4609 | MonopileInstallation
| WTIV | Transit | 5 | 52083.3333 | ACTION | 3473.4609 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3474.4609 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3475.4609 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3477.4609 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3478.4609 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 3488.4609 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3489.4609 | MonopileInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 3496.4609 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3499.7041 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3511.7041 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3519.7041 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3531.7041 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3539.7041 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3582.9474 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3584.9474 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3585.264 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3586.264 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3589.264 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3589.9871 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3589.9903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3590.9903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3592.4903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3594.4903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3595.4903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3596.4903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3600.4903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3600.807 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3602.807 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3603.1237 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3604.1237 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3607.1237 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3607.8467 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3607.85 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3608.85 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3610.35 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3612.35 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3613.35 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3614.35 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3618.35 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3618.6667 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3661.9099 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3673.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3681.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3693.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3701.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 22 | 229166.6667 | ACTION | 3723.9099 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3724.9099 | MonopileInstallation
| WTIV | Transit | 21.2432 | 221283.7838 | ACTION | 3746.1531 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3748.1531 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3748.4698 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3749.4698 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3752.4698 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3753.1929 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3753.1961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3754.1961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3755.6961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3757.6961 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3758.6961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3759.6961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3763.6961 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3764.0128 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3766.0128 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3766.3295 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3767.3295 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3770.3295 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3771.0525 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3771.0558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3772.0558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3773.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3775.5558 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3776.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3777.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3781.5558 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3781.8724 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 23 | 239583.3333 | ACTION | 3804.8724 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3805.8724 | MonopileInstallation
| WTIV | Transit | 18 | 187500 | ACTION | 3823.8724 | MonopileInstallation
| WTIV | Delay | 35 | 364583.3333 | ACTION | 3858.8724 | MonopileInstallation
| WTIV | Transit | 2.2432 | 23367.1171 | ACTION | 3861.1157 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3862.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3874.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3882.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3894.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3902.1157 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3945.3589 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3947.3589 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3947.6756 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3948.6756 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3951.6756 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3952.3987 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3952.4019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3953.4019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3954.9019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3956.9019 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3957.9019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3958.9019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3962.9019 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3963.2186 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3965.2186 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3965.5352 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3966.5352 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3969.5352 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3970.2583 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3970.2616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3971.2616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3972.7616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3974.7616 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3975.7616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3976.7616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3980.7616 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3981.0782 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4024.3215 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4036.3215 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4044.3215 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4056.3215 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4064.3215 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4107.5647 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4109.5647 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4109.8814 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4110.8814 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4113.8814 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4114.6044 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4114.6077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4115.6077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4117.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4119.1077 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4120.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4121.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4125.1077 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4125.4244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4127.4244 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4127.741 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4128.741 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4131.741 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4132.4641 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4132.4673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4133.4673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4134.9673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4136.9673 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4137.9673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4138.9673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4142.9673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4143.284 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4186.5273 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4198.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4206.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4218.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4226.5273 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4269.7705 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4271.7705 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4272.0872 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4273.0872 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4276.0872 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4276.8102 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4276.8135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4277.8135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4279.3135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4281.3135 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4282.3135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4283.3135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4287.3135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4287.6301 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4289.6301 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4289.9468 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4290.9468 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4293.9468 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4294.6699 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4294.6731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4295.6731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4297.1731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4299.1731 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4300.1731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4301.1731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4305.1731 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4305.4898 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4348.733 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4360.733 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4368.733 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4380.733 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4388.733 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4431.9763 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4433.9763 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4434.2929 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4435.2929 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4438.2929 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4439.016 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4439.0193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4440.0193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4441.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4443.5193 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4444.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4445.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4449.5193 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4449.8359 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4451.8359 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4452.1526 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4453.1526 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4456.1526 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4456.8757 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4456.8789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4457.8789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4459.3789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4461.3789 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4462.3789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4463.3789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4467.3789 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4467.6956 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4510.9388 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4522.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4530.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4542.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4550.9388 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4594.1821 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4596.1821 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4596.4987 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4597.4987 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4600.4987 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4601.2218 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4601.225 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4602.225 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4603.725 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4605.725 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4606.725 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4607.725 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4611.725 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4612.0417 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4614.0417 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4614.3584 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4615.3584 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4618.3584 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4619.0814 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4619.0847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4620.0847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4621.5847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4623.5847 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4624.5847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4625.5847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4629.5847 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4629.9014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 4629.9014 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4633.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4637.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4641.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4643.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4644.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4646.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4650.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4654.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4658.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4659.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4661.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4662.9014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4666.1446 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4668.1446 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4668.4613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4671.4613 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4672.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4678.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4681.2113 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4682.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 4686.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4692.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4695.7113 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4696.7113 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4698.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4704.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4705.2113 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4706.2113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4707.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4711.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4712.2113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4713.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 19 | 197916.6667 | ACTION | 4732.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4736.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4737.2113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4738.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4742.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4742.5279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4744.5279 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4744.8446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4747.8446 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4748.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4754.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4757.5946 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4759.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4765.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4768.0946 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4769.0946 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 4772.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4773.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 32 | 333333.3333 | ACTION | 4805.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4811.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4812.5946 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4813.5946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4815.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4818.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4819.5946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4821.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4824.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4825.5946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4827.0946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4830.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4830.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4834.1545 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4838.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4842.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4846.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4847.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4849.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4850.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4854.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4858.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4862.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4864.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4865.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4867.1545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4870.3978 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4872.3978 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4872.7144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4875.7144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4876.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4882.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4885.4644 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4886.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4892.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4895.9644 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4896.9644 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4898.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4904.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4905.4644 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4906.4644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4907.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4911.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4912.4644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4913.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4917.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4918.4644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4919.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 4926.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4930.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4930.7811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4932.7811 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4933.0978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4936.0978 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4937.0978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4937.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4943.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4946.8478 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4948.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4954.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4957.3478 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4958.3478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4959.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4965.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4966.8478 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4967.8478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4969.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4972.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4973.8478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4975.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4978.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4979.8478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4981.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4984.8478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4985.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4988.4077 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4992.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4996.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5000.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5001.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5003.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5004.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5008.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5012.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5016.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5018.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5019.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5021.4077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 2 | 20833.3333 | ACTION | 5023.4077 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 5024.4077 | TurbineInstallation
| WTIV | Transit | 1.2432 | 12950.4505 | ACTION | 5025.6509 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5027.6509 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5027.9676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5030.9676 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5031.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5037.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 5038.7176 | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5041.7176 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5043.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5049.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5052.2176 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5053.2176 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5054.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5060.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5061.7176 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5062.7176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5064.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5067.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5068.7176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5070.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5073.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5074.7176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5076.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5079.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5080.0342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5082.0342 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5082.3509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5085.3509 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5086.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5092.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5095.1009 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5096.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5102.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5105.6009 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5106.6009 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5108.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5114.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5115.1009 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5116.1009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5117.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5121.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5122.1009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5123.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5127.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5128.1009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5129.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5133.1009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5133.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5136.6608 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5140.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5144.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5148.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5150.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5151.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5153.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5157.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5161.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5165.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5166.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5168.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5169.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5172.9041 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5174.9041 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5175.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5178.2207 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5178.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5184.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5187.9707 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5189.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5195.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5198.4707 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5199.4707 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5200.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5206.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5207.9707 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5208.9707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5210.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5213.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5214.9707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5216.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5219.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5220.9707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5222.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5225.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5226.2874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5228.2874 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5228.6041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5231.6041 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5232.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5238.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5241.3541 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5242.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5248.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5251.8541 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5252.8541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5254.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5260.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5261.3541 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5262.3541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5263.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5267.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5268.3541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5269.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5273.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5274.3541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5275.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5279.3541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5279.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5282.914 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5286.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5290.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5294.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5296.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5297.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5299.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5303.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5307.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5311.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5312.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5314.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5315.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5319.1572 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5321.1572 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5321.4739 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5324.4739 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5325.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5331.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5334.2239 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5335.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5341.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5344.7239 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5345.7239 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 5351.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5353.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5359.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5360.2239 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5361.2239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5362.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5366.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5367.2239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5368.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5372.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5373.2239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5374.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5378.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5378.5406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5380.5406 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5380.8572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5383.8572 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5384.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5390.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5393.6072 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5395.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5401.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5404.1072 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5405.1072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5406.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5412.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5413.6072 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5414.6072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5416.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5419.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5420.6072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5422.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5425.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5426.6072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5428.1072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5431.6072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5431.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5435.1671 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5439.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5443.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5447.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5448.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5450.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5451.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5455.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5459.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5463.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5465.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5466.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5468.1671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 5470.1671 | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5473.4104 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5475.4104 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5475.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5478.727 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5479.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5485.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5488.477 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5489.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5495.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5498.977 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5499.977 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5501.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5507.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5508.477 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5509.477 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5510.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5514.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5515.477 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5516.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5520.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5521.477 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5522.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5526.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5526.7937 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5528.7937 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5529.1104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5532.1104 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5532.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5538.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5541.8604 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5543.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5549.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5552.3604 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5553.3604 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5554.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5560.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5561.8604 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5562.8604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5564.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5567.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5568.8604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5570.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5573.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5574.8604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5576.3604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5579.8604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5580.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5583.4203 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5587.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5591.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5595.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5596.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5598.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5599.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5603.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5607.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5611.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5613.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5614.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5616.4203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5619.6635 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5621.6635 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5621.9802 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5624.9802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5625.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5631.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5634.7302 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5636.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5642.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5645.2302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5646.2302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5647.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5653.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5654.7302 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5655.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5657.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5660.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5661.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5663.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5666.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5667.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5669.2302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5672.7302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5673.0469 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5675.0469 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5675.3635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5678.3635 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5679.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5685.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5688.1135 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5689.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5695.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5698.6135 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5699.6135 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5701.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5707.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5708.1135 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5709.1135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5710.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5714.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5715.1135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5716.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5720.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5721.1135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5722.6135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5726.1135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5726.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5729.6734 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5733.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5737.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5741.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5743.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5744.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5746.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5750.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5754.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5758.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5759.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5761.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5762.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5765.9167 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5767.9167 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5768.2333 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5771.2333 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5771.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5777.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5780.9833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5782.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5788.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5791.4833 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5792.4833 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5793.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5799.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5800.9833 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5801.9833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5803.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5806.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5807.9833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5809.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5812.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5813.9833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5815.4833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5818.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5819.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5821.3 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5821.6167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5824.6167 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5825.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5831.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5834.3667 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5835.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5841.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5844.8667 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5845.8667 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5847.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5853.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5854.3667 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5855.3667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5856.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5860.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5861.3667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5862.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5866.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5867.3667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5868.8667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5872.3667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5872.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5875.9266 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5879.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5883.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5887.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5889.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5890.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5892.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5896.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5900.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5904.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5905.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5907.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5908.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5912.1698 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5914.1698 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5914.4865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5917.4865 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5918.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5924.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5927.2365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5928.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5934.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5937.7365 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5938.7365 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5940.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5946.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5947.2365 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5948.2365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5949.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5953.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5954.2365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5955.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5959.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5960.2365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5961.7365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5965.2365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5965.5532 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5967.5532 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5967.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5970.8698 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5971.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5977.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5980.6198 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5982.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5988.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5991.1198 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5992.1198 | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 6001.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6002.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6008.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6009.6198 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6010.6198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6012.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6015.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6016.6198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6018.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6021.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6022.6198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6024.1198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6027.6198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6027.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6031.1797 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6035.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6039.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6043.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6044.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6046.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6047.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6051.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6055.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6059.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6061.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6062.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6064.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6067.423 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6069.423 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6069.7397 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6072.7397 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6073.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6079.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6082.4897 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6083.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6089.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6092.9897 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6093.9897 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6095.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6101.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6102.4897 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6103.4897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6104.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6108.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6109.4897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6110.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6114.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6115.4897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6116.9897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6120.4897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6120.8063 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6122.8063 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6123.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6126.123 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6126.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6132.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6135.873 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6137.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6143.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6146.373 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6147.373 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6148.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6154.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6155.873 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6156.873 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6158.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6161.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6162.873 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6164.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6167.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6168.873 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6170.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6173.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6174.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6177.4329 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6181.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6185.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6189.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6190.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6192.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6193.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6197.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6201.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6205.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6207.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6208.9329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6210.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6213.6761 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6215.6761 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6215.9928 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6218.9928 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6219.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6225.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6228.7428 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6230.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6236.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6239.2428 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6240.2428 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6241.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6247.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6248.7428 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6249.7428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6251.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6254.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6255.7428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6257.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6260.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6261.7428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6263.2428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6266.7428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6267.0595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6269.0595 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6269.3761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6272.3761 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6273.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6279.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6282.1261 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6283.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6289.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6292.6261 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6293.6261 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6295.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6301.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6302.1261 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6303.1261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6304.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6308.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6309.1261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6310.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6314.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6315.1261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6316.6261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6320.1261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6320.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6323.686 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6327.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6331.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6335.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6337.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6338.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6340.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6344.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6348.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6352.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6353.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6355.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6356.686 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6359.9293 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6361.9293 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6362.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6365.246 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6365.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6371.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6374.996 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6376.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6382.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6385.496 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6386.496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6387.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6393.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6394.996 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6395.996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6397.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6400.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6401.996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6403.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6406.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6407.996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6409.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6412.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6413.3126 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6415.3126 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6415.6293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6418.6293 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6419.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6425.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6428.3793 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6429.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6435.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6438.8793 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6439.8793 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6441.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6447.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6448.3793 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6449.3793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6450.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6454.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6455.3793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6456.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6460.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6461.3793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6462.8793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6466.3793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6466.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6469.9392 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6473.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6477.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6481.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6483.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6484.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6486.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6490.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6494.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6498.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6499.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6501.4392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6502.9392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6506.1824 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6508.1824 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6508.4991 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6511.4991 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6512.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6518.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6521.2491 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6522.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6528.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6531.7491 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6532.7491 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6534.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6540.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6541.2491 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6542.2491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6543.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6547.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6548.2491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6549.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 6551.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6555.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6556.2491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6557.7491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6561.2491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6561.5658 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6563.5658 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6563.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6566.8824 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6567.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6573.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6576.6324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6578.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6584.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6587.1324 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6588.1324 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6589.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6595.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6596.6324 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6597.6324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6599.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6602.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6603.6324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6605.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6606.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6609.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6610.6324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6612.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6615.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6615.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6619.1924 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6623.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6627.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6631.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6632.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6634.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6635.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6639.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6643.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6647.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6649.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6650.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6652.1924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6655.4356 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6657.4356 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6657.7523 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6660.7523 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6661.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6667.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6670.5023 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6672.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6678.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6681.0023 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6682.0023 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6683.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6689.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6690.5023 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6691.5023 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6693.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6696.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6697.5023 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6699.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6702.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6703.5023 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6705.0023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6708.5023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6708.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6710.8189 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6711.1356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6714.1356 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6714.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6720.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6723.8856 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6725.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6731.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6734.3856 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6735.3856 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6736.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6742.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6743.8856 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6744.8856 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6746.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6749.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6750.8856 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6752.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6755.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6756.8856 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6758.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6761.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6762.2023 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6765.4455 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6769.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6773.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6777.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6778.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6780.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6781.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6785.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6789.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6793.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6795.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6796.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6798.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6801.6887 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6803.6887 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6804.0054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6807.0054 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6807.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6813.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6816.7554 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6818.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6824.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6827.2554 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6828.2554 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6829.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6835.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6836.7554 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6837.7554 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6839.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6842.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6843.7554 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6845.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6848.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6849.7554 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6851.2554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6854.7554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6855.0721 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6857.0721 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6857.3887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6860.3887 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6861.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6867.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6870.1387 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6871.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6877.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6880.6387 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6881.6387 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6883.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6889.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6890.1387 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6891.1387 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6892.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6896.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6897.1387 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6898.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6902.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6903.1387 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6904.6387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6908.1387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6908.4554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6911.6987 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6915.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6919.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6923.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6925.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6926.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6928.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6932.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6936.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6940.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6941.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6943.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6944.6987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6947.9419 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6949.9419 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6950.2586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6953.2586 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6954.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6960.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6963.0086 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6964.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6970.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6973.5086 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6974.5086 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6976.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6982.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6983.0086 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6984.0086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6985.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6989.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6990.0086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6991.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6995.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6996.0086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6997.5086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7001.0086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7001.3252 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7003.3252 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7003.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7006.6419 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7007.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7013.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7016.3919 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7017.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7023.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7026.8919 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7027.8919 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7029.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7035.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7036.3919 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7037.3919 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7038.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7042.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7043.3919 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7044.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7048.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7049.3919 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7050.8919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7054.3919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7054.7086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7057.9518 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7061.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7065.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7069.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7071.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7072.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7074.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7078.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7082.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7086.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7087.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7089.4518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7090.9518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7094.1951 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7096.1951 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7096.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7099.5117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7100.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7106.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7109.2617 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7110.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7116.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7119.7617 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7120.7617 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7122.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7128.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7129.2617 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7130.2617 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7131.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7135.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7136.2617 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7137.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7141.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7142.2617 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7143.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7147.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7147.5784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7149.5784 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7149.8951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7152.8951 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7153.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7159.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7162.6451 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7164.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7170.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7173.1451 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7174.1451 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7175.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7181.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7182.6451 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7183.6451 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7185.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7188.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7189.6451 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7191.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7194.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7195.6451 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7197.1451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7200.6451 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7200.9617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7204.205 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7208.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7212.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7216.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7217.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7219.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7220.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7224.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7228.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7232.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7234.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7235.705 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7237.205 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7240.4482 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7242.4482 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7242.7649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7245.7649 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7246.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7252.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7255.5149 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7257.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7263.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7266.0149 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7267.0149 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7268.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7274.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7275.5149 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7276.5149 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7278.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7281.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7282.5149 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7284.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7287.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7288.5149 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7290.0149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7293.5149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7293.8315 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7295.8315 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7296.1482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7299.1482 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7299.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7305.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7308.8982 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7310.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7316.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7319.3982 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7320.3982 | TurbineInstallation
| WTIV | Delay | 34 | 354166.6667 | ACTION | 7354.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7355.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 7365.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7371.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7372.8982 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7373.8982 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7375.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7378.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7379.8982 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7381.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7384.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7385.8982 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7387.3982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7390.8982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7391.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7394.4581 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7398.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7402.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7406.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7407.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7409.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7410.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7414.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7418.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7422.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7424.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7425.9581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7427.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7430.7014 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7432.7014 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7433.018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7436.018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7436.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7442.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7445.768 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7447.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7453.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7456.268 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7457.268 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7458.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7464.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7465.768 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7466.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7468.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7471.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7472.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7474.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7477.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7478.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7480.268 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7483.768 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7484.0847 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7486.0847 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7486.4014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7489.4014 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7490.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7496.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7499.1514 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7500.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7506.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7509.6514 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7510.6514 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7512.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7518.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7519.1514 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7520.1514 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7521.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7525.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7526.1514 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7527.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7531.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7532.1514 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7533.6514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7537.1514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7537.468 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7540.7113 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7544.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7548.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7552.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7554.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7555.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7557.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7561.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7565.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7569.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7570.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7572.2113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7573.7113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7576.9545 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7578.9545 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7579.2712 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7582.2712 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7583.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7589.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7592.0212 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7593.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7599.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 19 | 197916.6667 | ACTION | 7618.5212 | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7621.5212 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7622.5212 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7624.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 7636.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7642.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7643.0212 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7644.0212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7645.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7649.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7650.0212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7651.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7655.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7656.0212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7657.5212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7661.0212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7661.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7663.3378 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7663.6545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7666.6545 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7667.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7673.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7676.4045 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7677.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7683.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7686.9045 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7687.9045 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7689.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7695.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7696.4045 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7697.4045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7698.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7702.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7703.4045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7704.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7708.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7709.4045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7710.9045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7714.4045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7714.7212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7717.9644 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7721.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7725.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7729.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7731.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7732.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7734.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7738.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7742.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7746.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7747.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7749.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7750.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7754.2077 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7756.2077 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7756.5243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7759.5243 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7760.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7766.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7769.2743 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7770.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7776.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7779.7743 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7780.7743 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7782.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7788.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7789.2743 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7790.2743 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7791.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7795.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7796.2743 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7797.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7801.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7802.2743 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7803.7743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7807.2743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7807.591 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7809.591 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7809.9077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7812.9077 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7813.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7819.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7822.6577 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7824.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7830.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7833.1577 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7834.1577 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7835.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7841.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7842.6577 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7843.6577 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7845.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7848.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7849.6577 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7851.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7854.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7855.6577 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7857.1577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7860.6577 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7860.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7864.2176 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7868.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7872.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7876.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7877.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7879.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7880.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7884.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7888.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7892.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7894.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7895.7176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7897.2176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 7900.4608 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7902.4608 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7902.7775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7905.7775 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7906.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7912.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7915.5275 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7917.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 20 | 208333.3333 | ACTION | 7937.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7943.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7946.0275 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7947.0275 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7948.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7954.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7955.5275 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7956.5275 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7958.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7961.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7962.5275 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7964.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7967.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7968.5275 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7970.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7973.5275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7973.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7975.8442 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7976.1608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7979.1608 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7979.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7985.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7988.9108 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7990.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7996.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7999.4108 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8000.4108 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8001.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8007.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8008.9108 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8009.9108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8011.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8014.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8015.9108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8017.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 8020.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8023.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8024.9108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8026.4108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8029.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8030.2275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8033.4707 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8037.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8041.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8045.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8046.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8048.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8049.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8053.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8057.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8061.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8063.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8064.9707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8066.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8069.714 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8071.714 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8072.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8075.0306 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8075.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8081.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8084.7806 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8086.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8092.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8095.2806 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8096.2806 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8097.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8103.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8104.7806 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8105.7806 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8107.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8110.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8111.7806 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8113.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8116.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8117.7806 | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 8124.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8126.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8129.7806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8130.0973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8132.0973 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8132.414 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8135.414 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8136.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8142.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8145.164 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8146.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8152.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8155.664 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8156.664 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8158.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8164.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8165.164 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8166.164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8167.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8171.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8172.164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8173.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8177.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8178.164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8179.664 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8183.164 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8183.4806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8186.7239 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8190.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8194.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8198.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8200.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8201.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8203.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8207.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8211.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8215.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8216.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8218.2239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8219.7239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8222.9671 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8224.9671 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8225.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8228.2838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8229.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8235.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8238.0338 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8239.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8245.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8248.5338 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8249.5338 | TurbineInstallation
| WTIV | Delay | 39 | 406250 | ACTION | 8288.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8290.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8296.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8297.0338 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8298.0338 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8299.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8303.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8304.0338 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8305.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8309.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8310.0338 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8311.5338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8315.0338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8315.3505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8317.3505 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8317.6671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8320.6671 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8321.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 32 | 333333.3333 | ACTION | 8353.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8359.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8362.4171 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8363.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8369.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8372.9171 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8373.9171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8375.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8381.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8382.4171 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8383.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8384.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8388.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8389.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8390.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8394.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8395.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8396.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8400.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8400.7338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8403.977 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8407.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8411.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 8418.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8422.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8424.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8425.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8427.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8431.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8435.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8439.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8440.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8442.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8443.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8447.2203 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8449.2203 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8449.5369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8452.5369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8453.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8459.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8462.2869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8463.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8469.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8472.7869 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8473.7869 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8475.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8481.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8482.2869 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8483.2869 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8484.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8488.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8489.2869 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8490.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8494.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8495.2869 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8496.7869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8500.2869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8500.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8502.6036 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8502.9203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8505.9203 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8506.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8512.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8515.6703 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8517.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8523.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8526.1703 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8527.1703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8528.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8534.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8535.6703 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8536.6703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8538.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8541.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8542.6703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8544.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8547.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8548.6703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8550.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8553.6703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8553.9869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation