## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 72 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 80 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 92 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 100 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 112 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 120 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 123.2432 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 128.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 133.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 134.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 137.6599 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 142.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 143.383 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 143.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 144.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 147.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 162.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 164.3862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 165.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 166.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 170.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 175.8029 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 180.8029 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 186.2196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 187.2196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 190.2196 | MonopileInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 196.2196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 196.9426 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 196.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 197.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 23 | 383333.3333 | ACTION | 220.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 235.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 237.9459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 238.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 239.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 243.9459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 249.3625 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 254.3625 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 259.7792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 260.7792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 263.7792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 264.5023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 264.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 265.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 280.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 282.5055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 283.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 284.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 288.5055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 293.9222 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 298.9222 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 304.3389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 305.3389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 308.3389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 309.0619 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 309.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 310.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 325.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 327.0652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 328.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 329.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 333.0652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 338.4818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 343.4818 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 348.8985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 349.8985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 352.8985 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 353.6216 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 353.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 354.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 369.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 371.6248 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 372.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 373.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 377.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 383.0415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 388.0415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 393.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 394.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 397.4582 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 398.1812 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 398.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 399.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 414.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 416.1845 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 417.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 418.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 422.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 427.6011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 430.8444 | MonopileInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 439.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 451.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 453.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 461.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 473.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 481.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 493.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 501.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 513.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 521.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 533.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 541.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 553.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 561.8444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 565.0876 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 570.0876 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 575.5043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 576.5043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 579.5043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 580.2274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 580.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 581.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 596.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 598.2306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 599.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 600.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 604.2306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 609.6473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 614.6473 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 620.0639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 621.0639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 624.0639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 624.787 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 624.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 625.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 640.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 642.7903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 643.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 644.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 648.7903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 654.2069 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 659.2069 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 664.6236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 665.6236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 668.6236 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 669.3467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 669.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 670.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 685.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 687.3499 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 688.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 689.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 693.3499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 698.7666 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 703.7666 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 709.1832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 710.1832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 713.1832 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 713.9063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 713.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 714.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 729.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 731.9096 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 732.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 733.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 737.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 743.3262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 748.3262 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 753.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 754.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 757.7429 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 758.466 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 758.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 759.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 116666.6667 | ACTION | 766.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 781.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 783.4692 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 784.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 785.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 789.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 794.8859 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 799.8859 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 805.3025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 806.3025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 809.3025 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 810.0256 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 810.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 811.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 826.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 828.0288 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 829.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 830.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 834.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 839.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 842.6888 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 854.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 862.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 874.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 882.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 885.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 897.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 905.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 917.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 925.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 937.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 945.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 957.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 965.6888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 968.932 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 973.932 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 979.3487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 980.3487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 983.3487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 984.0717 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 984.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 985.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1000.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1002.075 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1003.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1004.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1008.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1013.4917 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1018.4917 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1023.9083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1024.9083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1027.9083 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1028.6314 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1028.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1029.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1044.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1046.6346 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1047.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1048.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1052.6346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1058.0513 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1063.0513 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1068.468 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1069.468 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1072.468 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1073.191 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1073.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1074.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1089.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1091.1943 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1092.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1093.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1097.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1102.6109 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1107.6109 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1113.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1114.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1117.0276 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1117.7507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1117.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1118.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1133.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1135.7539 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1136.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1137.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1141.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1147.1706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1152.1706 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1157.5873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1158.5873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1161.5873 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1162.3103 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1162.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1163.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1178.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1180.3136 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1181.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1182.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1186.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1191.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1196.7302 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1202.1469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1203.1469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1206.1469 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1206.87 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1206.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1207.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1222.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1224.8732 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1225.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1226.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1230.8732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1236.2899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1239.5331 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1251.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1259.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1271.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1279.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1291.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1299.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1311.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1319.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1331.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1339.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1351.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1359.5331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1362.7764 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1367.7764 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1373.193 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1374.193 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1377.193 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1377.9161 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1377.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1378.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1393.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1395.9194 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1396.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1397.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1401.9194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1407.336 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1412.336 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1417.7527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1418.7527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1421.7527 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1422.4758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1422.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1423.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1438.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1440.479 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1441.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1442.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1446.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1451.8957 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1456.8957 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1462.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1463.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1466.3123 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1467.0354 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1467.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1468.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1483.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1485.0387 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1486.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1487.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1491.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1496.4553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1501.4553 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1506.872 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1507.872 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1510.872 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1511.5951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1511.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1512.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1527.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1529.5983 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1530.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1531.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1535.5983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1541.015 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1546.015 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1551.4316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1552.4316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1555.4316 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1556.1547 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1556.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1557.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 1560.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1575.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1577.158 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1578.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1579.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1583.158 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1588.5746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1593.5746 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1598.9913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1599.9913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1602.9913 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1603.7144 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1603.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1604.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1619.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1621.7176 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1622.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1623.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1627.7176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1633.1343 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1636.3775 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1648.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1656.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1668.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1676.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1688.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1696.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1708.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1716.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1728.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1736.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1748.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1756.3775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1759.6208 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1764.6208 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1770.0374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1771.0374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1774.0374 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1774.7605 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1774.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1775.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1790.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1792.7637 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1793.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1794.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1798.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1804.1804 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1809.1804 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1814.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1815.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1818.5971 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1819.3201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1819.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1820.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1835.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1837.3234 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1838.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1839.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1843.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1848.7401 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1853.7401 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1859.1567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1860.1567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1863.1567 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1863.8798 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1863.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1864.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1879.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1881.883 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1882.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1883.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1887.883 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1893.2997 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1898.2997 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1903.7164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1904.7164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1907.7164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1908.4394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1908.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1909.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1924.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1926.4427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1927.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1928.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1932.4427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1937.8594 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1942.8594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1948.276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1949.276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1952.276 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1952.9991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1953.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1954.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 12 | 200000 | ACTION | 1966.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1981.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1983.0023 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1984.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1985.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1989.0023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1994.419 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1999.419 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2004.8357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2005.8357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2008.8357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2009.5587 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2009.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2010.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 2021.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2036.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2038.562 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2039.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2040.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2044.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2049.9787 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2053.2219 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2065.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2073.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2085.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2093.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2105.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2113.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2125.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2133.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2145.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2153.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2165.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2173.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2176.4651 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2181.4651 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2186.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2187.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2190.8818 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2191.6049 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2191.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2192.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2207.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2209.6081 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2210.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2211.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2215.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2221.0248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2226.0248 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2231.4415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2232.4415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2235.4415 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2236.1645 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2236.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2237.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2252.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2254.1678 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2255.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2256.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2260.1678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2265.5844 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2270.5844 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2276.0011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2277.0011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2280.0011 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2280.7242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2280.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2281.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2296.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2298.7274 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2299.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2300.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2304.7274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2310.1441 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2315.1441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2320.5608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2321.5608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2324.5608 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2325.2838 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2325.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2326.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2341.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2343.2871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2344.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2345.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2349.2871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2354.7037 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2359.7037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2365.1204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2366.1204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2369.1204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2369.8435 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2369.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2370.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2385.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2387.8467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2388.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2389.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2393.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2399.2634 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2404.2634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2409.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2410.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2413.6801 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2414.4031 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2414.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2415.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2430.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2432.4064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2433.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2434.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2438.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2443.823 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2447.0663 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2459.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2467.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2479.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2487.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2499.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2507.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2519.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2527.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2539.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2547.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2559.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2567.0663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2570.3095 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2575.3095 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2580.7262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2581.7262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2584.7262 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2585.4493 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2585.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2586.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2601.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2603.4525 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2604.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2605.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2609.4525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2614.8692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2619.8692 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2625.2858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2626.2858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2629.2858 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2630.0089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2630.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2631.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2646.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2648.0122 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2649.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2650.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2654.0122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2659.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2664.4288 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2669.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2670.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2673.8455 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2674.5686 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2674.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2675.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2690.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2692.5718 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2693.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2694.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2698.5718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2703.9885 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2708.9885 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2714.4051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2715.4051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2718.4051 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2719.1282 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2719.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2720.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 60 | 1000000 | ACTION | 2780.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2795.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2797.1315 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2798.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2799.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2803.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2808.5481 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2813.5481 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2818.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2819.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2822.9648 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2823.6878 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2823.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2824.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2839.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2841.6911 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2842.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2843.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2847.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2853.1078 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2858.1078 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2863.5244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2864.5244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2867.5244 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2868.2475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2868.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2869.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2884.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2886.2507 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2887.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2888.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2892.2507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2897.6674 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2900.9107 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2912.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2920.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2932.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2940.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2952.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2960.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2972.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2980.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2992.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3000.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3012.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 21 | 350000 | ACTION | 3033.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3041.9107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3045.1539 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3046.1539 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3051.1539 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3056.5706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3057.5706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3060.5706 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3061.2936 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3061.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3062.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3077.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3079.2969 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3080.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3081.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3085.2969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3090.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3095.7136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3101.1302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3102.1302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3105.1302 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3105.8533 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3105.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3106.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3121.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3123.8565 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3124.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3125.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3129.8565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3135.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3140.2732 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3145.6899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3146.6899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3149.6899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3150.4129 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3150.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3151.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3166.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3168.4162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3169.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3170.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3174.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3179.8328 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3184.8328 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3190.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3191.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3194.2495 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3194.9726 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3194.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3195.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3210.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3212.9758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3213.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3214.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3218.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3224.3925 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3229.3925 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3234.8092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3235.8092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3238.8092 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3239.5322 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3239.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3240.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3255.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3257.5355 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3258.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3259.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3263.5355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3268.9521 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3273.9521 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3279.3688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3280.3688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3283.3688 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3284.0919 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3284.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3285.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3300.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3302.0951 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3303.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3304.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3308.0951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3313.5118 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3316.755 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3328.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3336.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 16 | 266666.6667 | ACTION | 3352.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3364.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3372.755 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3375.9983 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3380.9983 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3386.4149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3387.4149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3390.4149 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3391.138 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3391.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3392.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3407.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3409.1413 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3410.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3411.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3415.1413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3420.5579 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3425.5579 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3430.9746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3431.9746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 3434.9746 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3435.9746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3436.6977 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3436.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3437.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 3452.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 3454.7009 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3455.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3456.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3460.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3466.1176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 3466.1176 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3468.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3470.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3472.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3474.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3476.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3476.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3477.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3478.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3480.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3482.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3484.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3486.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3488.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3489.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3489.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3490.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3492.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3494.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3496.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3498.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3500.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3501.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3502.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3502.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3504.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3506.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3508.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3510.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3512.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3513.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3514.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3515.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3517.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3519.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3521.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3523.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3525.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3525.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3526.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3527.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3529.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3531.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3533.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3535.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3537.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3538.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3538.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3539.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3542.8608 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3547.8608 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3553.2775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3554.2775 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3554.6575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3556.6575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3557.6575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3558.4175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3560.4175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3561.4175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3562.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3564.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3565.5575 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3567.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3569.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3570.0775 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3571.0775 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3572.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3574.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3575.5775 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3576.0775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3577.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3579.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3579.5775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3581.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3582.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3583.0775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3584.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3586.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3591.4942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3596.4942 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3601.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3602.9108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3603.2908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3605.2908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3606.2908 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3607.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3609.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3610.0508 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3611.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3612.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3614.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3615.1908 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 3626.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3627.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3629.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3631.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3632.7108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3633.7108 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3635.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3637.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3638.2108 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3638.7108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3640.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3641.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3642.2108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3643.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3645.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3645.7108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3647.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3648.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3654.1275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3659.1275 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3664.5442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3665.5442 | TurbineInstallation
| WTIV | Delay | 37 | 616666.6667 | ACTION | 3702.5442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3702.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3704.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3705.9242 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3706.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3708.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3709.6842 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3710.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3712.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3713.8242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3715.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3717.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3718.3442 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3719.3442 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3720.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3722.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3723.8442 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3724.3442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3725.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3727.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3727.8442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3729.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3730.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3731.3442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3732.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3734.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3739.7608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3744.7608 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3750.1775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3751.1775 | TurbineInstallation
| WTIV | Delay | 16 | 266666.6667 | ACTION | 3767.1775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3767.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3769.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3770.5575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3771.3175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3773.3175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3774.3175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3775.4575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3777.4575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3778.4575 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3779.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3781.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3782.9775 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3783.9775 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3785.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3787.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3788.4775 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3788.9775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3790.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3791.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3792.4775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3793.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3795.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3795.9775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3797.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3798.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3804.3942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3809.3942 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3814.8108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3815.8108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3816.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3818.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3819.1908 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3819.9508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3821.9508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3822.9508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3824.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3826.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3827.0908 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 3831.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3832.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3833.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3835.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3836.6108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3837.6108 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3839.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3841.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3843.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3844.1108 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3844.6108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3846.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3847.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3848.1108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3849.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3851.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3851.6108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3853.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3854.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3860.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3865.0275 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3870.4442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3871.4442 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3871.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3873.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3874.8242 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3875.5842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3877.5842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3878.5842 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3879.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3881.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3882.7242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3884.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3886.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3887.2442 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3888.2442 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3889.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3891.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3892.7442 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3893.2442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3894.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3896.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3896.7442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3898.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3899.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3900.2442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3901.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3903.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3908.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3911.9041 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3913.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3915.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3917.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3919.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3921.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3922.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3923.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3924.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3926.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3928.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3930.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3932.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3934.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3934.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3935.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3936.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3938.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3940.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3942.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3944.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3946.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3947.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3947.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3948.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3950.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3952.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3954.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3956.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3958.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3959.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3960.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3960.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3962.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3964.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3966.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3968.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3970.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3971.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3972.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3973.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3975.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3977.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3979.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3981.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3983.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3983.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3984.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3985.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3988.6473 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3993.6473 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3999.064 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4000.064 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4000.444 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4002.444 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4003.444 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4004.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4006.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4007.204 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4009.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4010.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4012.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4014.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4015.344 | TurbineInstallation
| WTIV | Delay | 45 | 750000 | ACTION | 4060.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4061.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4063.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4064.864 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4065.864 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4067.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4069.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4070.364 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4070.864 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4072.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4073.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4074.364 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4075.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4077.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4077.864 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4079.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4082.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4083.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4089.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4094.2806 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4099.6973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4100.6973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4101.0773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4103.0773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4104.0773 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4104.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4106.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4107.8373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4108.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4110.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4111.9773 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4113.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4115.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4116.4973 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4117.4973 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4118.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4120.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4121.9973 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4122.4973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4123.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4125.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4125.9973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4127.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4128.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4129.4973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4130.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4132.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4137.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4142.914 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4148.3306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4149.3306 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4149.7106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4151.7106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4152.7106 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4153.4706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4155.4706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4156.4706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4157.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4159.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4160.6106 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4162.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4164.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4165.1306 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4166.1306 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4167.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4169.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4170.6306 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4171.1306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4172.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4174.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4174.6306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4176.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4177.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4178.1306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4179.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4181.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4186.5473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4191.5473 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4196.964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4197.964 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4202.964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4203.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4205.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4206.344 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4207.104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4209.104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4210.104 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4211.244 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4213.244 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4214.244 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4215.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4217.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4218.764 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4219.764 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4221.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4223.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4224.264 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4224.764 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4226.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4227.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4228.264 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4229.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4231.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4231.764 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4233.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4234.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4240.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4245.1806 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4250.5973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4251.5973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4251.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4253.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4254.9773 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4255.7373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4257.7373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4258.7373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4259.8773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4261.8773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4262.8773 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4264.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4266.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4267.3973 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4268.3973 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4269.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 4279.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4281.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4282.8973 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4283.3973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4284.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4286.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4286.8973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4288.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4289.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4290.3973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4291.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4293.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4298.814 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4303.814 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4309.2306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4310.2306 | TurbineInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 4327.2306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4327.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4329.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4330.6106 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4331.3706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4333.3706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4334.3706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4335.5106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4337.5106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4338.5106 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4340.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4342.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4343.0306 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4344.0306 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4345.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4347.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4348.5306 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4349.0306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4350.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4352.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4352.5306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4354.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4355.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4356.0306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4357.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4359.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4364.4473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4367.6906 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4369.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4371.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4373.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4375.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4377.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4378.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4379.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4379.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4381.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4383.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4385.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4387.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4389.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4390.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4391.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4392.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 4402.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4404.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4406.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4408.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4410.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4412.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4412.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4413.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4414.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4416.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4418.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4420.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4422.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4424.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4425.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4425.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4426.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4428.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4430.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4432.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4434.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4436.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4437.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4438.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4438.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4440.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4442.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4444.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4446.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4448.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4449.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4450.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4451.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4454.4338 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4459.4338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4464.8505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4465.8505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4466.2305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4468.2305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4469.2305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4469.9905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4471.9905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4472.9905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4474.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4476.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4477.1305 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4478.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4480.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4481.6505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4482.6505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4484.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4486.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4487.1505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4487.6505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4489.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 4550.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4551.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4552.1505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4553.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4555.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4555.6505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4557.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4558.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4564.0671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4569.0671 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4574.4838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4575.4838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4575.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4577.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4578.8638 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4579.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4581.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4582.6238 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4586.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4587.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 18 | 300000 | ACTION | 4605.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4607.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4608.7638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4610.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4612.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4613.2838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4614.2838 | TurbineInstallation
| WTIV | Delay | 84 | 1400000 | ACTION | 4698.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4699.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4702.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4704.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4705.7838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4706.2838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4707.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4709.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4709.7838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4711.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4712.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4713.2838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4714.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4716.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4721.7005 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4726.7005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4732.1171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4733.1171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4733.4971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4735.4971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4736.4971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4737.2571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4739.2571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4740.2571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4741.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4743.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4744.3971 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4745.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4747.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4748.9171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4749.9171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4751.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4753.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4754.4171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4754.9171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4756.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4757.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4758.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4759.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4761.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4761.9171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4763.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4764.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4770.3338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4775.3338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4780.7505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4781.7505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4782.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4784.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4785.1305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4785.8905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4787.8905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4788.8905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4790.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4792.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4793.0305 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4794.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4796.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4797.5505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4798.5505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4800.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4802.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4803.0505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4803.5505 | TurbineInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 4834.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4836.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4837.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4838.0505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4839.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4841.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4841.5505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4843.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4844.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4849.9671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4854.9671 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4860.3838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4861.3838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4861.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4863.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4864.7638 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4865.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4867.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4868.5238 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4869.6638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4871.6638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4872.6638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4874.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4876.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4877.1838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4878.1838 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4879.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4881.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4882.6838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4883.1838 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4888.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4889.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4891.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4891.6838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4893.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4894.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4895.1838 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4896.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4897.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4899.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4904.6005 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4909.6005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4915.0171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4916.0171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4916.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4918.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4919.3971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4920.1571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4922.1571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4923.1571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4924.2971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4926.2971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4927.2971 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4928.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4930.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4931.8171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4932.8171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4934.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4936.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4937.3171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4937.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4939.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4940.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4941.3171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4942.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4944.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4944.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4946.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4947.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4953.2338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4956.477 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4958.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4960.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4962.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4964.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4966.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4967.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4967.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4968.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4970.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4972.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4974.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4976.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4978.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4979.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4980.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4980.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4982.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4984.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4986.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4988.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4990.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4991.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4992.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4993.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4995.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4997.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4999.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5001.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5003.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5003.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5004.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5005.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5007.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5009.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5011.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5013.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5015.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5016.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5016.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5017.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5019.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5021.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5023.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5025.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5027.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5028.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5029.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5029.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5033.2203 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5038.2203 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5043.6369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5044.6369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5045.0169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5047.0169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5048.0169 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5048.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5050.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5051.7769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5052.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5054.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5055.9169 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5057.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5059.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5060.4369 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5061.4369 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 5065.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5066.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5068.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5069.9369 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5070.4369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5071.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5073.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5073.9369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5075.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5076.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5077.4369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5078.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5080.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5085.8536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5090.8536 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5096.2703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5097.2703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5097.6503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5099.6503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5100.6503 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5101.4103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5103.4103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5104.4103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5105.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5107.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5108.5503 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5110.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5112.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5113.0703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5114.0703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5115.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5117.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5118.5703 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5119.0703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5120.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5122.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5122.5703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5124.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5125.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5126.0703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5127.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5129.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5134.4869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5139.4869 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5144.9036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5145.9036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5146.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1263 | 21050000 | ACTION | 6409.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6411.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6412.2836 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6413.0436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6415.0436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6416.0436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6417.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6419.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6420.1836 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6421.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6423.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6424.7036 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6425.7036 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6427.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6429.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6430.2036 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6430.7036 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6431.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6433.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6434.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6435.2036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6436.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6438.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6438.7036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6440.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6441.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6447.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6452.1203 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6457.5369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6458.5369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6458.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6460.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6461.9169 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6462.6769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6464.6769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6465.6769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6466.8169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6468.8169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6469.8169 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6471.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6473.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6474.3369 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6475.3369 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6476.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6478.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6479.8369 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6480.3369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6481.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6483.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6483.8369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6485.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6486.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6487.3369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6488.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6490.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6495.7536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6500.7536 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 6512.7536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6518.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6519.1703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6519.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6521.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6522.5503 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6523.3103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6525.3103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6526.3103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6527.4503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6529.4503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6530.4503 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6531.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6533.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6534.9703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6535.9703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6537.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6539.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6540.4703 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6540.9703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6542.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6543.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6544.4703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6545.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6547.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6547.9703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6549.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6550.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6556.3869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6561.3869 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6566.8036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6567.8036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6568.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6570.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6571.1836 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6571.9436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6573.9436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6574.9436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6576.0836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6578.0836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6579.0836 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6580.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6582.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6583.6036 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6584.6036 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6586.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6588.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6589.1036 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6589.6036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6591.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6592.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6593.1036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6594.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6596.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6596.6036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6598.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6599.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6605.0203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6608.2635 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6610.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6612.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6614.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6616.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6618.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6619.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6619.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6620.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6622.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6624.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6626.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6628.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6630.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6631.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6632.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6632.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6634.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6636.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6638.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6640.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6642.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6643.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6644.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6645.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6647.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6649.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6651.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6653.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6655.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6655.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6656.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6657.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6659.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6661.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6663.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6664.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6666.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6668.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6669.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6669.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6670.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6672.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6674.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6676.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6678.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6680.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6681.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6682.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6682.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6686.0068 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6691.0068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6696.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6697.4234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6697.8034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6699.8034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6700.8034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6701.5634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6703.5634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6704.5634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6705.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6707.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6708.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6710.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6712.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6713.2234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6714.2234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6715.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6717.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6718.7234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6719.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6720.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6722.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6722.7234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6724.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6725.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6726.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6727.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6729.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6734.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6739.6401 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6745.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6751.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6752.0568 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6758.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6758.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6760.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6761.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6762.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6764.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6765.1968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6766.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6768.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6769.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6770.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6772.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6773.8568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6774.8568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6776.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6778.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6779.3568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6779.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6781.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6782.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6783.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6784.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6786.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6786.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6788.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6789.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6795.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6800.2734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6805.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6806.6901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6807.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6809.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6810.0701 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 6824.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6824.8301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6826.8301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6827.8301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6828.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6830.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6831.9701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6833.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6835.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6836.4901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6837.4901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6838.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6840.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6841.9901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6842.4901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6843.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6845.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6845.9901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6847.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6848.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6849.4901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6850.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6852.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6857.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6862.9068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6868.3234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6869.3234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6869.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6871.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6872.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6873.4634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6875.4634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6876.4634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6877.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6879.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6880.6034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6882.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6884.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6885.1234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6886.1234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6887.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6889.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6890.6234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6891.1234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6892.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6894.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6894.6234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6896.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6897.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6898.1234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6899.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6901.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6906.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 6911.5401 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6916.5401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6921.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6922.9568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6923.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6925.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6926.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6927.0968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6929.0968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6930.0968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6931.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6933.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6934.2368 | TurbineInstallation
| WTIV | Delay | 41 | 683333.3333 | ACTION | 6975.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6976.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6978.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6979.7568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6980.7568 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 6983.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6985.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6987.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6988.2568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6988.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6990.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6991.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6992.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6993.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6995.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6995.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6997.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6998.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7004.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7009.1734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7014.5901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7015.5901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7015.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7017.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7018.9701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7019.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7021.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7022.7301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7023.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7025.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7026.8701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7028.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7030.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7031.3901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7032.3901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7033.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7035.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7036.8901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7037.3901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7038.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7040.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7040.8901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7042.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7043.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7044.3901 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7049.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7050.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7052.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7054.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7059.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7064.8068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 1 | 16666.6667 | ACTION | 7065.8068 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7066.8068 | TurbineInstallation
| WTIV | Transit | 2.2432 | 37387.3874 | ACTION | 7069.05 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7071.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7073.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7075.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7077.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7079.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7079.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7080.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7081.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7083.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7085.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7087.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7089.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7091.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7092.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7092.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7093.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7095.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7097.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7099.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7101.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7103.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7104.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7105.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7105.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7107.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7109.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7111.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7113.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7115.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7116.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7117.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7118.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7120.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7122.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7124.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7126.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7128.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7128.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7129.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7130.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7132.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7134.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7136.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7138.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7140.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7141.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7141.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7142.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7145.7933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7150.7933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7156.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7157.2099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7157.5899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7159.5899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7160.5899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7161.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7163.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7164.3499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7165.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7167.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7168.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7170.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7172.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7173.0099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7174.0099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7175.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7177.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7178.5099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7179.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7180.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7182.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7182.5099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7184.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7185.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7186.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7187.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7189.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7194.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7199.4266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7204.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7205.8433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7206.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7208.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7209.2233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7209.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7211.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7212.9833 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 7221.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7223.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 7229.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7231.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7232.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7233.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7235.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7236.6433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7237.6433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7239.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7241.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7242.1433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7242.6433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7244.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7245.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7246.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7247.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7249.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7249.6433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7251.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7252.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7258.0599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7263.0599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7268.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7269.4766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7269.8566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7271.8566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7272.8566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7273.6166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7275.6166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7276.6166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7277.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7279.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7280.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7282.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 16 | 266666.6667 | ACTION | 7298.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7300.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7301.2766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7302.2766 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 7306.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7307.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7309.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7310.7766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7311.2766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7312.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7314.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7314.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7316.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7317.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7318.2766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7319.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7321.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7326.6933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7331.6933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7337.1099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7338.1099 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7339.1099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7339.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 7348.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7350.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7351.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7352.2499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7354.2499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7355.2499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7356.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7358.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7359.3899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7360.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7362.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7363.9099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7364.9099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7366.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7368.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7369.4099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7369.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7371.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7372.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7373.4099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7374.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7376.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7376.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7378.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7379.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7385.3266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7390.3266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7395.7433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7396.7433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7397.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7399.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7400.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7400.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7402.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7403.8833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7405.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 7466.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7468.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7469.0233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7470.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7472.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7473.5433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7474.5433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7476.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7478.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7479.0433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7479.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7481.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7482.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7483.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7484.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7486.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7486.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7488.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7489.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7494.9599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7499.9599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7505.3766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7506.3766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7506.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7508.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7509.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7510.5166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7512.5166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7513.5166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7514.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7516.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7517.6566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7519.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7521.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7522.1766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7523.1766 | TurbineInstallation
| WTIV | Delay | 26 | 433333.3333 | ACTION | 7549.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7550.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7552.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7553.6766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7554.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7555.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7557.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7557.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7559.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7560.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7561.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7562.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7564.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7569.5933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7572.8365 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7574.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7576.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7578.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7580.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7582.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7583.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7584.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7585.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7587.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7589.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7591.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7593.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7595.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7595.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7596.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7597.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7599.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7601.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7603.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7605.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7607.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7608.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7608.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7609.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7611.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7613.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7615.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7617.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7619.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7620.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7621.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7621.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7623.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7625.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7627.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7629.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7631.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7632.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7633.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7634.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7636.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7638.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7640.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7642.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7644.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7644.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7645.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7646.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7649.5797 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7654.5797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7659.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7660.9964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7661.3764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7663.3764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7664.3764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7665.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7667.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7668.1364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7669.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7674.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7676.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7677.2764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7678.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7680.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7681.7964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7682.7964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7684.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7686.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7687.2964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7687.7964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7689.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7690.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7691.2964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7692.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7694.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7694.7964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7696.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7697.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7703.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7708.2131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7713.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7714.6297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7715.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7717.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7718.0097 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7725.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7725.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7727.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7728.7697 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 7731.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7732.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7734.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7735.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7737.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7739.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7740.4297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7741.4297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7742.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7744.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7745.9297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7746.4297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7747.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7749.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7749.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7751.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7752.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7753.4297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7754.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7756.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7761.8464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7766.8464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7772.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7773.2631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7773.6431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7775.6431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7776.6431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7777.4031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7779.4031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7780.4031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7781.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7783.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7784.5431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7786.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7788.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7789.0631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7790.0631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7791.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7793.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7794.5631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7795.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7796.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7798.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7798.5631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7800.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7801.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7802.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7803.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7805.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7810.4797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7815.4797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7820.8964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7821.8964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7822.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7824.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7825.2764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7826.0364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7828.0364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7829.0364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7830.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7832.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7833.1764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7834.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7836.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7837.6964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7838.6964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7840.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7842.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7843.1964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7843.6964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7845.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7846.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7847.1964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7848.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7850.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7850.6964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7852.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7853.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7859.1131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7864.1131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7869.5297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7870.5297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7870.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7872.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7873.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7874.6697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7876.6697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7877.6697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7878.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7880.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7881.8097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7883.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7885.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7886.3297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7887.3297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7888.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7890.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7891.8297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7892.3297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7893.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7895.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7895.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7897.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7898.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7899.3297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7900.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7902.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7907.7464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7912.7464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7918.1631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7919.1631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7919.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7921.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7922.5431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7923.3031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7925.3031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7926.3031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7927.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7929.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7930.4431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7931.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7933.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7934.9631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7935.9631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7937.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7939.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7940.4631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7940.9631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7942.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7943.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7944.4631 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7945.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7946.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7948.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7948.9631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7950.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7951.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7957.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7960.623 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7962.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7964.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7966.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7968.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7970.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7971.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7972.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7972.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7974.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7976.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7978.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7980.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7982.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7983.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7984.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7985.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7987.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7989.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7991.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7993.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7995.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7995.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7996.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7997.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7999.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8001.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8003.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8005.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8007.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8008.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8008.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8009.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8011.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8013.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8015.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8017.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8019.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8020.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8021.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8021.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8023.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8025.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8027.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8029.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8031.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8032.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8033.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8034.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8037.3662 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8042.3662 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 8051.3662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8056.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8057.7829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8058.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8060.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8061.1629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8061.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8063.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8064.9229 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8066.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8068.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 8073.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8075.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8076.0629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8077.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8079.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8080.5829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8081.5829 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8085.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8087.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8089.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8090.0829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8090.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8092.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8093.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8094.0829 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8095.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8096.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8098.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8098.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8100.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8101.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8106.9996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8111.9996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8117.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8118.4162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8118.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8120.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8121.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8122.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8124.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8125.5562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8126.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8128.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8129.6962 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 8171.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8173.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8175.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8176.2162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8177.2162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8178.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8180.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8181.7162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8182.2162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8183.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8185.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8185.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8187.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8188.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8189.2162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8190.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8192.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8197.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8202.6329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8208.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8209.0496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8209.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8211.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8212.4296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8213.1896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8215.1896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8216.1896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8217.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8219.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8220.3296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8221.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8223.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8224.8496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8225.8496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8227.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8229.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8230.3496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8230.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8232.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8233.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8234.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8235.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8237.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8237.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8239.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8240.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8246.2662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8251.2662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8256.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8257.6829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8258.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8260.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8261.0629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8261.8229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8263.8229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8264.8229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8265.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8267.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8268.9629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8270.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8272.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8273.4829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8274.4829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8275.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8277.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8278.9829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8279.4829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8280.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8282.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8282.9829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8284.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8285.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8286.4829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8287.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 27 | 450000 | ACTION | 8314.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8316.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8317.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8322.8996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8327.8996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8333.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8334.3162 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 8341.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8341.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8343.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8344.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8345.4562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8347.4562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8348.4562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8349.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8351.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8352.5962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8354.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8356.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8357.1162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8358.1162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8359.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8361.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8362.6162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8363.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8364.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8366.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8366.6162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8368.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8369.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8370.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8371.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8373.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8378.5329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8383.5329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8388.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8389.9496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8390.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8392.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8393.3296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8394.0896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8396.0896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8397.0896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8398.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8400.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8401.2296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8402.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8404.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8405.7496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8406.7496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8408.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8410.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8411.2496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8411.7496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8413.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8414.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8415.2496 | TurbineInstallation
| WTIV | Delay | 36 | 600000 | ACTION | 8451.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8452.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8454.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8454.7496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8456.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8457.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8463.1662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8466.4095 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8468.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8470.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8472.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8474.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8476.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8477.1595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8477.9095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8478.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8480.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8482.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8484.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8486.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8488.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8489.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8490.1595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8490.9095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8494.1527 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8499.1527 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8504.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8505.5694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8505.9494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8507.9494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8508.9494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8509.7094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8511.7094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8512.7094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8513.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8515.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8516.8494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8518.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8520.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8521.3694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8522.3694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8523.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8525.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8526.8694 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8527.3694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8528.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8530.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8530.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8532.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8533.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8534.3694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8535.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8537.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8542.786 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8547.786 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8553.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8554.2027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8554.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8556.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8557.5827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8558.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8560.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8561.3427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8562.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8564.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8565.4827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8567.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8569.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8570.0027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8571.0027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8572.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8574.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8575.5027 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8576.0027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8577.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8579.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8579.5027 | TurbineInstallation
| WTIV | Delay | 23 | 383333.3333 | ACTION | 8602.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8604.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8605.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8606.0027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8607.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8609.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8614.4194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5